GOVERNMENT OF CHHATTISGARH

NATIONAL HIGHWAY ZONE P.W.D.

# BID DOCUMENT

# VOLUME – I

| NAME OF WORK | # : | Short term maintenance to Raipur-Balodabazar-Sarangarh Road section of NH-130B from Km 51.900 to Km 86.000 in the state of Chhattisgarh |
| --- | --- | --- |
| NAME AND ADDRESS OF THE CONTRACTOR WHO DOWN LOADED THE BID DOCUMENTS. | # : | # ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------ |

Office of the Chief Engineer

National Highway Zone, P.W.D. Chhattisgarh.

CONTENTS

## Description                                                                                                                Page No.

Introduction                                                                                                      1

Section 1	Notice Inviting Tender                                                                                      5

Section 2	Instructions to Bidders (ITB) and Appendix to ITB				  11

Section 3	Qualification Information							  31

Section 4	Forms of  Bank  Guarantees, Letter  of  Acceptance  (LoA) and  Agreement     41

Section 5	General Conditions of Contract (GCC) and Contract Data			  51

Section 6	Addendum to General Conditions of Contract				  77

Section 7	Road Maintenance Standards and Specifications for Road			  81

Maintenance Works, Part-I and Part II

Section 8	Drawings and Schedule of Drawings					  91

Section 9	Financial Bid Form and Bill of Quantities					  95

# SECTION – 1

# NOTICE INVITING TENDER

40/CE/NH/TC/44-23/2025       SYSTEM TENDER ID: 2025_MoRTH_862690_1   Date: 02.06.2025

| # Availability of bid documents from | # : | # 02.06.2025 to 23.06.2025 |
| --- | --- | --- |
| # Date of Pre-bid meeting | # : | # 09.06.2025 at 15:00 Hrs |
| # Deadline for submission of original documents and bid | : | 24.06.2025 at 17:30 Hrs |
| # Opening of technical bids | # : | # 25.06.2025 at 11:30 Hrs |
| # Opening of financial bids | : | Intimated later |
| # Validity of bids | # : | # 120 Days |

OFFICE OF THE CHIEF ENGINEER,

NATIONAL HIGHWAY ZONE, PWD, RAIPUR (C.G.)

Tel:- 0771-4051075, Fax. 0771-4023057 email- cenhr@rediffmail.com

Nit No. 40/CE/NH/TC/44-23/2025     SYSTEM TENDER ID: 2025_MoRTH_862690_1  Date: 02.06.2025

NOTICE INVITING TENDER

- The Chief Engineer NH Zone P.W.D. Raipur Chhattisgarh on behalf of Ministry of Road Transport & Highways, Government of India (the “Authority”) hereby invites Single Percentage Rate Bids through e-tendering from experienced firms/organizations for maintenance works and activities for the following sections of the National Highways.

| Sl. No. | Section | Length (km) | Estimated Cost (incl. GST) (Rs. Lakh) | Bid Security (Rs. Lakh) | Contract Duration* (month) |
| --- | --- | --- | --- | --- | --- |
| 1. | Short term maintenance to Raipur-Balodabazar-Sarangarh Road section of NH-130B from Km 51.900 to Km 86.000 in the state of Chhattisgarh. | 34.100 | 174.71 | 1.74 | 12 Months |

(*Out of which Quantity Based Road maintenance and road property Maintenance shall be completed in 2 months except Bituminous work, Shoulder Work, Road Marking and painting work which shall be completed in 2 months after monsoon season. and the performance-based repair and maintenance as prescribed in RFP shall be spread through 12 months)

## Cost of bid Documents (Non-Refundable)	: Rs. 11,800/- (Rupees Eleven thousand		 Eight Hundred only Incl GST),

- e-Tender Processing fee (Non-Refundable)	: Nil

- The preliminary requirements (detailed requirements are given in the Bid Documents) of bidding firm/contractor for above work are mentioned as under :-

| Average Annual Turn-over during last 3 years | Work of similar nature during last 5 years (completed works satisfactorily as a prime contractor, completed not less than 90% of contract value) |
| --- | --- |
| Minimum Average Annual Turnover Rs174.71 lakhs | Single work of Rs. 87.36 lakhs (minimum 50% of estimated cost of work) (or) Two similar works each of Rs. 61.15 lakhs (minimum 35% of estimated cost of work) (or) Three similar works each of Rs. 43.68 lakhs (minimum 25% of estimated cost of work) |

- The Scope of Work includes the routine maintenance of all the assets and facilities existing within Right of Way (ROW) on the above-mentioned section including maintenance of carriageway, shoulders, median, bridges, culverts, drains, footpaths, road signage, plantation etc., Providing Pavement Repairs and maintenance and carrying out other works as specified in the bid documents.

- To participate in the bidding, it is mandatory for the Bidders to get registered their firm with e-procurement portal https://eprocure.gov.in/eprocure/app to have user ID & password which has to be obtained free of cost. Following may kindly be noted:

- Registration with e-procurement portal should be valid at least up to the date of submission of BID.

- BIDs can be submitted only during the validity of registration.

The Bidders shall update their project and other details on the portal on a regular basis and apply to the tenders via the portal.

Bidders are also required to get registered their firm with Bidder Information Management System (BIMS) Portal.

The detailed bid documents can be viewed on the website https://eprocure.gov.in from 02/06/2025 to 23/06/2025 (upto 17:30 Hrs).

- The complete BID document can be viewed / downloaded from official portal of the CPPP website (eprocure.gov.in/eprocure/app) from 02/06/2025 to 23/06/2025 (upto 17:30 Hrs IST). The amendments/ clarifications to the Bid Document if any, will be hosted on the above website. The bidder is required to submit, along with its BID, the cost of BID/RFP document, i.e. Rs.11,800/- (Rupees Eleven Thousand Eight Hundred only), to Employer’s account through Bharat Kosh, as mentioned below:

| S. No. | Particulars | Details |
| --- | --- | --- |
| 1. | Link of Bharat Kosh | bharatkosh.gov.in |
| 2. | Pay and Accounts Officer (PAO) | PAO Code – “002192” Regional Pay & Accounts Officer (NH) Bhopal, |
| 3. | Drawing and Disbursing Officer (DDO) | DDO Code - “205810” Engineer Liaison Officer, Ministry of Road Transport & Highway, Raipur |

- The Bid should be submitted online in the prescribed format given on the website. No other mode of submission is acceptable.

- The authorized signatory holding Power of Attorney shall only be the Digital Signatory. In case authorized signatory holding Power of Attorney and Digital Signatory are not the same, the bid shall be considered non-responsive.

- The last date for online submission of the Bid is 23/06/2025 (upto 17:30 Hrs IST).  (as mentioned on the e-portal only) (“Bid Due Date”). Bidder must submit its Financial Bid and Technical Bid on CPPP e-procurement portal within the above deadline. The bids would be opened on 25/06/2025 at 11:30 Hrs.  online at Office of the Chief Engineer-cum-Regional Officer, MoRTH, Raipur Chhattisgarh, representatives of the bidders who choose to attend, may attend the online opening of the bids at Office of the Chief Engineer-cum-Regional Officer, MoRTH, Raipur Chhattisgarh on the date and time as mentioned above. However, such representatives shall be allowed to attend the opening of the bids only if they produce letter of authority on the letterhead of the bidder, at the time of opening of bids as mentioned above.

- The amount of Bid Security is Rs. 1.74 Lakhs.

- The period of validity of bid is 120 days from the deadline of submission of bid.

For any clarification, the office of the undersigned may be contacted.

- ATTN. OF:			Mr. M.L. Uraon

DESIGNATION: 		Chief Engineer (NH)

ADDRESS: 			NH Zone, PWD, Pension Bada, Raipur Chhattisgarh

FAX NO: 			0771-4023057

E-MAIL ADDRESS: 		cenhr@rediffmail.com

(ii)   ATTN. OF:			Mr. Abhijeet Kumar

DESIGNATION: 		Superintending Engineer-Regional Officer, MoRTH

ADDRESS: 			NH Campus, Pension Bada Raipur

FAX NO: 			0771-2436637

E-MAIL ADDRESS: 		romorthraipur@gmail.com

Chief Engineer

National Highway Zone,

Public Works Department

Pension Bada, Raipur (CG) - 492001

Phone/ Fax 0771 - 4051075, 4062744/ 4023057

e-mail: cenhr@rediffmail.com; cenhraipur@gmail.com

# SECTION-2

INSTRUCTIONS TO BIDDERS (ITB)

AND APPENDIX TO ITB

## SECTION – 2

## INSTRUCTIONS TO BIDDERS (ITB)

TABLE OF CLAUSES

| Clause | A. General | Clause | D. Submission of bids |
| --- | --- | --- | --- |
| 1. | Scope of Bid | 20. | Deadline for Submission of Bids |
|  |  | 21. | Late Submission of Documents in Physical Form |
| 2. | Source of Funds | 22. | Modification and Withdrawal of Bids |
| 3. | Eligible Bidders |  | E. Bid Opening, Clarification of bids and Evaluation |
| 4. | Qualification of the Bidder | 23. | Bid Opening, Clarification of Bids and Evaluation |
| 5. | One Bid per Bidder | 24. | Process to be Confidential |
| 6. | Cost of Bidding | 25. | Contacting the Employer |
| 7. | Site Visit | 26. | Examination of Bids and Determination of Responsiveness |
|  | B. Bidding Documents | 27. | Correction of Errors |
| 8. | Content of Bidding Documents | 28. | Evaluation and Comparison of Financial Bids |
| 9. | Clarifications on Bidding Documents |  | F. Award of Contract |
| 10. | Amendment of Bidding Documents | 29. | Award Criteria |
|  | C. Preparation of bids | 30. | Employer’s Right to Accept any Bid and to Reject any or all Bids |
| 11. | Language of Bid | 31. | Notification of Award and Signing of Agreement |
| 12. | Documents Comprising the Bid | 32. | Performance Security |
| 13. | Bid Prices | 33. | Advances |
| 14. | Currencies of Bid and Payment |  | G. Corrupt or Fraudulent Practices |
| 15. | Bid Validity | 34. | Corrupt or Fraudulent Practices |
| 16. | Earnest Money/Bid Security/ Forfeiture/Debarment |  | H. Labour Laws and Fundamental breach |
| 17. | Alternative Proposals by Bidders | 35. | Labour Laws and Regulations |
| 18. | Format and Signing of Bid | 36. | Fundamental Breach and other Obligations |
| 19. | Marking of Bids |  | Appendix to ITB |

A. GENERAL

- Scope of Bid

  - The Employer (as defined in the Appendix  to ITB) invites Single Percentage Rate bids through the process of e-tendering for works as described in these documents and referred to as “the Works”. The name and identification number of the Works is as defined in the Appendix to ITB.

  - The successful Bidder will be expected to complete the Works by the intended

Completion Date specified in the Contract Data.

  - Throughout these Bidding Documents, the terms “bid” and “tender” and their derivatives (bidder/tenderer, bid/tender, bidding/tendering, etc.) are synonymous.

## Source of Funds

  - The expenditure under this contract will be met by the Ministry of Road Transport & Highways through its Chief Engineer-cum-Regional Officer, MoRTH, Raipur Chhattisgarh.

## Eligible bidders

  - This Invitation for Bids is open to all bidders meeting the qualification requirements

Prescribed in Clause 4 of ITB.

  - Any entity which has been black listed or barred by the Central or any State Government or any public sector undertaking, autonomous body or any authority under the Central or State Government, from participating in any project, and the bar subsists as on the date of Application shall not be eligible to submit the bid.

## Qualification of the Bidder

  - All bidders shall furnish the following information and documents with their Bids in Section-3, Qualification Information, unless otherwise stated in the Appendix to ITB.

- Scanned copies of original documents defining the constitution or legal status, place of registration, and principal place of business; scanned copy of written power of attorney of the signatory of the Bid to commit the Bidder; and original copy of Written Power of Attorney to be submitted in the envelope of physical form. (refer Clause 12.2 of ITB).

- Scanned copy of total monetary value of civil engineering construction and maintenance works performed for each of the last three years duly certified by Chartered Accountant;

- Scanned  copy of experience certificate in works of a similar nature and size for each of the last five years with certificates from the concerned officer of the rank of Executive Engineer or equivalent or higher;

- Scanned copy of evidence of availability (either owned or leased or rented) of items of construction and maintenance equipment named in Clause 4.3 B(b) (i).

- Scanned copy of details of the technical personnel proposed to be employed for the Contract having the qualifications defined in Clause 4.3 B (b) (ii).

- Scanned  copy of reports on the financial standing of the Bidder, and a certificate from Chartered Accountant as a proof of turnover for the last three years;

- Scanned copy of information regarding any litigation or arbitration during the last five years in which the Bidder is involved, the parties concerned, the disputed amount, and the present status;

- Undertaking that the bidder is not affiliated to the firm or entity that has been hired or employed by the Employer for preparation of bid documents or to supervise the contract.

  - Bids from joint ventures/consortiums are not allowed.

  - A    To qualify for award of the contract, each bidder in its name should have the following;-

### achieved a minimum average annual financial turnover (in all classes of civil engineering construction and maintenance works only) equal to the amount indicated in NIT during last three years ending 31s March of the previous financial year duly certified by Chartered Accountant.

- satisfactorily completed (not less than 90% of contract value), as a prime contractor or as a partner of JV for similar works during last five years ending last day of month previous to the one in which bids are invited, either of the following:

- Three similar completed works costing not less than amount equal to Rs. 43.68  Lakhs  each.

- Two similar completed works costing not less than amount equal to Rs. 61.15   Lakhs each.

- One similar completed work costing  not less than amount equal to Rs. 87.35  Lakhs

(The similar work constitutes construction/maintenance of roads)

The following escalation factors shall be used to bring the value of such completed works to the level of current financial year (2025-26):

| Financial Year | 2023-24 | 2022-23 | 2021-22 | 2020-21 | 2019-20 |
| --- | --- | --- | --- | --- | --- |
| Multiplying Factor | 1.1 | 1.21 | 1.33 | 1.46 | 1.61 |

  - B       (a) Each bidder must upload the scanned copies of following documents along with the submission of online bid:

    - An affidavit on a Stamp Paper, duly attested from the Notary Public, that the Information furnished with the bid documents is correct in all respects; and

    - Such other certificates as defined in Section-3.

Failure to submit the certificates/documents as specified above shall make the bid

Non-responsive

- Each bidder must demonstrate for this work:

    - evidence of availability (either owned or leased or rented) of the key equipment for this work as stated in the Appendix to ITB.

    - availability of personnel with qualification and experience as stated in the Appendix to ITB.

  - Bidders who meet the minimum qualification criteria will be qualified only if their available bid capacity is more than the total bid value. The available bid capacity will be calculated as under:

Available Bid capacity = (A* N* 2.5 - B) Where.

A = Maximum value of civil engineering works executed in any one year during

the last three years (escalation factor as specified in this section shall be used to bring the maximum value of civil engineering works to the level of current financial year i.e., 2025-26) taking into account the completed as well as  works in progress.

N = Number of years prescribed for completion of the works for which bid is invited.

B = Value (escalation factor as specified in this section shall be used to bring the value to the level of current financial year i.e. 2025-26) of existing commitments and on-going works to be completed during the next 01 years (period of completion of the works for which bid is invited).

  - Even though the bidders meet the above qualifying criteria, they are subject to be disqualified if they have:

    - made misleading or false representations in the forms, statements, affidavits and attachments submitted in proof of the qualification requirements; and/or

    - record of poor performance such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history, or financial failures etc. or debarring from work etc.

## One Bid per Bidder

  - Each Bidder shall submit only one Bid for the Works. A Bidder who submits more than One Bid will cause such bids to be disqualified.

## Cost of Bidding

  - The Bidder shall bear all costs associated with the preparation and submission of his Bid, and the Employer will, in no case, be responsible or liable for those costs.

## Site Visit

  - The Bidder, at his own cost, responsibility and risk, is encouraged  to visit, examine and familiarize himself with the Site of Works and its surroundings including source of earth, water, road aggregates, availability of labour etc. and obtain all information that may be necessary for preparing the Bid and entering into a contract for undertaking the maintenance Works. The costs of visiting the site shall be at the Bidder’s own expense. For this purpose, he may contact the person whose contact details are given in the Appendix to ITB.

## B. BIDDING DOCUMENTS

- Content of bidding Documents

  - The set of bidding documents comprises the documents listed below and addenda (if any) issued in accordance with Clause 10:

## Section 1:	Notice Inviting Tender

Section 2:	Instructions to Bidders (ITB) and Appendix to ITB

Section 3:	Qualification Information

Section 4:	Forms of Bank Guarantee, Letter of Acceptance (LOA) and Agreement Section 5:	General Conditions of Contract and Contract Data

Section 6:	Addendum to General Conditions of Contract

Section 7:	Road Maintenance Standards and Specifications for Road Maintenance Work, Part-I and Part-II

Section 8:	Drawings and Schedule of Drawings

Section 9:	Financial bid form and Bill of Quantities

  - The bidder is expected to examine carefully all instructions, conditions of contract, contract data, forms, scope, road maintenance Standards and Specifications, bill of quantities, etc. in the Bid Documents. Failure to comply with the requirements of Bid Documents shall be at the bidder’s own risk. Pursuant to Clause 26 here of, Bids, which are not substantially responsive to the requirements of the Bid Documents, shall be rejected.

## Clarifications on Bid Documents

  - A prospective Bidder requiring any clarification on the Bid Documents may notify the Employer in writing or through e-tender portal at the Employer’s address indicated in the notice inviting Tender. The Employer will respond to any such request for clarification received earlier than 10 days prior to the deadline for submission of Bids. Copies of the Employer’s response will be hosted on website including a description of the queries but without identifying its source.

  - Pre-Bid Meeting

    - The Bidder’s authorized representative is invited to attend a pre-bid meeting, if it is indicated in the Appendix to ITB. The purpose of the pre-bid meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage.

    - The bidder is requested to submit any questions in writing so as to reach the Employer not later than one week before the meeting.

    - Minutes of the meeting, including the text of the questions raised (without identifying the source of the enquiry) and the responses given will be posted without delay on website. Any modifications of the bid documents listed in Clause 8.1, which may become necessary as a result of the pre-bid meeting or which are required in the opinion of the Employer shall be made by the Employer exclusively through the issue of an Addendum pursuant to Clause 10 and not through the minutes of the pre-bid meeting.

    - Non-attendance at the pre-bid meeting will not b e   a cause for disqualification of a bidder.

## Amendment of Bidding Documents

  - Before the deadline for submission of bids, the Employer may modify the Bidding Documents by issuing addenda.

  - Any addendum thus issued shall be part of the Bidding Documents and shall be hosted on e-tendering portal. Bidders are advised to keep themselves updated of all the addenda issued on e-tendering portal by daily checking the e-tendering portal and the Employer does not assume any responsibility in case the bidder fails to do so and does not take any action, if required, with respect to any relevant addendum.

  - To give prospective bidders reasonable time to take an addendum into account in preparing their bids, the Employer shall extend, as necessary, the deadline for submission of bids, in accordance with Clause 20.3.

## C. PREPARATION OF BIDS

- Language of bid

  - All documents relating to the Bid shall be in English.

## Documents comprising the bid

  - The e-bid submitted by the bidder shall be in two separate parts namely Part-I and Part-II. Part-I shall be named Technical Bid and shall comprise of information submitted in Section-3. Part-II shall be named Financial Bid and shall comprise of Bill of Quantities- Bill no.1 to 3.

  - Documents to be submitted in physical form must be delivered by [12.00 Hrs] on Bid Due Date [00.00.2025].

Though, the scanned copies of following documents is required to be uploaded during submission of e-bid on the e-tendering portal as per Clause 12.1 above, however, following original documents in physical form shall be submitted in a sealed envelope on or before the Bid Due Date [00.00.2025].@ 12.00 Hrs] at the address indicated in Clause 20, duly superscribed "Name of Work, Bid Due Date and time". Name and address of the bidder should also be indicated on the envelope

- Copy of Acknowledgement for Tender Submission and EMD/Bid Security

- Bid Document Fee

- Written Power of Attorney of the signatory (whose digital signature certificate is

used during e-tender submission) of the bidder to commit the Bid.

- Affidavit duly notarized (as per the format provided in Section-3)

- Integrity Pact

  - The following documents, which are not submitted with the bid, will be deemed to be part of the bid.

- Notice Inviting Tender

- Instructions to the Bidders and Appendix to ITB

- General Conditions of Contract and Contract Data

- Addendum to General Conditions of Contract

- Road Maintenance Standards and Specifications for Road Maintenance Works,

- Part-I and Part-II

- Drawings and Schedule of Drawings

## Bid Prices

  - The Contract shall be for the whole Works, as described in Clause 1.1 based on the Bill of Quantities- Bill no. 1 to 3 submitted by the Bidder.

  - The Bidder shall quote single percentage rate above/below the BoQ/scheduled rates on appropriate format enclosed as part of tender document on e-tender portal of the CPPP website (eprocure.gov.in/eprocure/app).

  - All duties, taxes, including GST, royalties and other levies payable by the Contractor under the Contract, or for any other cause, shall be included in the rates, prices, and total bid price submitted by the Bidder.

  - The rates and prices quoted by the Bidder shall be fixed for the duration of the Contract and shall not be subject to adjustment.

## Currencies of Bid and Payment

All payments shall be made in Indian Rupees.

## Bid Validity

  - Bids shall remain valid for a period of 120 days after the deadline date for bid submission specified in Clause 20. A bid valid for a shorter period shall be rejected by the Employer as non- responsive.

  - In exceptional circumstances, prior to expiry of the original time limit, the Employer may request that the Bidders may extend the period of validity for a specified additional period. The request and the Bidders’ responses shall be made in writing. A Bidder may refuse the request without forfeiting his Bid Security. A Bidder agreeing to the request will not be required or permitted to modify his bid, but will be required to extend the validity of his Bid Security for a period of the extension, and in compliance with Clause 16 in all respects.

## Earnest Money/Bid Security /Forfeiture/Debarment

  - The Bidder shall furnish, as part of the Bid, Earnest Money/Bid Security, in the amount as specified in the NIT. (Bank guarantee/demand draft must be in favor of the Employer.

  - The Earnest Money shall, at the bidder’s option, be in the form of bank Guarantee/Demand Draft only (the other forms will not be acceptable) of any scheduled commercial bank approved by RBI having a net worth of not less than Rs. 500 crore as per the latest annual report of the bank and must be in the name of Employer. In case of foreign bank (issued by a branch in India), the net worth in respect of the Indian operations shall only be taken into account. It shall be valid for 45 days beyond the validity of the bid. Any bid having Bid Security for lesser value and shorter validity period shall be treated as non-responsive.

- Bank Guarantee or Demand Draft receipts, in the name of the Employer, from following banks would be accepted: -

  - State Bank of India or its subsidiaries,

  - Any Indian Nationalised Bank

  - IDBI/ICICI Bank

  - A Foreign Bank (issued by a branch outside India) with a counter guarantee from SBI or its subsidiaries or any Indian Nationalised Bank.

  - Any Scheduled Commercial Bank approved by RBI having a net worth of not less than Rs. 500 crore as per the latest Annual Report of the Bank. In the case of a Foreign Bank (issued by a branch in India), the net worth in respect of the Indian operations shall only be taken into account.

- The acceptance of the guarantees shall also be subject to the conditions that the capital adequacy of the Bank shall not be less than the latest norms prescribed by RBI.

- The bank guarantee issued by a Cooperative Bank shall not be accepted.

  - Any Bid not accompanied by an acceptable Earnest Money, shall be rejected by the Employer as non-responsive.

  - The Earnest Money of unsuccessful bidders will be returned within 28 days of the end of the Bid validity period specified in Sub-Clause 15.1.

  - The Earnest Money of the successful Bidder will be discharged when the Bidder has signed the Agreement and furnished the required Performance Security.

  - The Bid Security /Earnest Money will be forfeited:

- if the Bidder withdraws the Bid after its submission during the period of Bid validity;

- in the case of a successful Bidder, if the Bidder fails within the specified time limit to

  - sign the Agreement; and/or

  - furnish the required Performance Security.

  - In case of forfeiture of Bid Security, the bidder shall also be debarred from participation in the works of MoRTH and State PWD (NH) division for a period of 1 year.

## Alternative Proposals by bidders

  - Bidder shall submit offers that fully comply with the requirement of the Bidding Documents. Conditional offer or alternate offer will not be considered further in the process of evaluation and such a bid will be declared non-responsive.

## Format and Signing of bid

  - The Bidder shall submit e-bid comprising the documents as described in Clause 12 of the ITB.

  - The documents as stipulated in Clause 12.2 (i), (ii), (iii) (iv) and (v) to be submitted in the physical form along with the demand draft for fees/security shall be typed or written in ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. All the pages of the documents as mentioned here shall be signed by the person/persons signing the Bid. Documents as mentioned here shall contain no overwriting, alterations or additions, except those to comply with instructions, issued by the Employer or as necessary to correct errors made by the Bidder, in which case such corrections shall be made by scoring out the cancelled portion, writing the correction and signing and dating it along with the stamp by the person or persons signing the Bids

## SUBMISSION OF BIDS

## Marking of bids

  - The documents to be submitted in physical form as per Clause 12.2 ((i), (ii), (iii), (iv) and (v)) of ITB shall be submitted in a sealed Envelope super scribed as “Documents in Physical Form” at the top left corner.

In case of any discrepancy between documents submitted online and documents submitted in the physical form, the documents submitted in physical form shall prevail over the documents submitted through online process.

## Deadline for Submission of bids

  - The Bidder shall ensure that the complete e-Bid is uploaded on the e-tender portal on or before the Bid Due Date and before the time specified in NIT/e-portal. The Bidder is further required to submit Documents in Physical Form on or before the Bid Due Date and before the time of submission as specified in NIT, at the following address:

- ATTN. OF:			Mr. M.L. Uraon

DESIGNATION: 		Chief Engineer (NH)

ADDRESS: 			NH Zone, PWD, Pension Bada, Raipur Chhattisgarh

FAX NO: 			0771-4023057

E-MAIL ADDRESS: 		cenhr@rediffmail.com

(ii)   ATTN. OF:			Mr. Abhijeet Kumar

DESIGNATION: 		Superintending Engineer-Regional Officer, MoRTH

ADDRESS: 			NH Campus, Pension Bada Raipur

FAX NO: 			0771-2436637

E-MAIL ADDRESS: 		romorthraipur@gmail.com

In the event of the specified date for the submission of Documents in Physical Form being declared a holiday for the Employer, the same will be received up to the specified time on the next working day.

  - The Employer assumes no responsibility for inability of a bidder to submit bids through the Employer’s e-tendering portal on account of delay in submission at bidder’s end. Bidders shall ensure that they submit the bid well before the “Bid Due Date and Time of Bid-Submission”. The Employer shall not be responsible if bidder is not able to submit the bid on account of failure in network/internet connection or any other reason whatsoever.

  - The Employer may extend the deadline for submission of bids by issuing an amendment in accordance with Clause 10, in which case all rights and obligations of the Employer and the bidders previously subject to the original deadline will then be subject to the new deadline.

## Late Submission of Documents in Physical Form:

  - Any document in physical form if received by the Employer after the deadline prescribed in Clause 20 will be returned unopened to the Bidder and also the e-bid submitted by such Bidder shall not be considered.

## Modification and Withdrawal of Bids

  - Bidders may modify or withdraw their e-bids as directed on the e-tendering portal, before the Bid Due Date and time as prescribed in Clause 20.

  - No bid may be modified after the deadline for online submission of bids.

  - Withdrawal or modification of a Bid between the deadline for submission of bids and the expiration of the original period of bid validity specified in Clause 15.1 or as extended pursuant to Clause 15.2 shall result in the forfeiture of the Bid Security pursuant to Clause 16.

  - Bidders may modify the prices of their bids before deadline of online submission of bid.

  - No Late and delayed bids after Bid Due Date and time shall be permitted in e-tendering portal System. Time being displayed on e-Tendering Portal shall be final and binding on bidders and bids have to be submitted by bidders considering this time only and not the time as per their location/country.

## BID OPENING, CLARIFICATION OF BIDS AND EVALUATION

## Bid Opening, Clarification of Bids and Evaluation

  - Bid opening shall be carried out in two stages. Firstly, Part-I ‘Technical Bid’ of all the Bidders received (except those received late) shall be opened on the date and time mentioned in Notice Inviting Tender (NIT). Part-II’ Financial Bid’ of those bidders whose technical bid has been determined to be substantially responsive shall be opened on a subsequent date through online process of e-tendering, which will be notified to such bidders.

The Employer will open the “Technical Bid” of all the Bids received (except those received late), in the presence of the Bidders/Bidders’ representatives who choose to attend at the time, date and place specified in the NIT. In the event of the specified date for the submission of bids being declared a holiday for the Employer, the Bids will be opened at the appointed time and location on the next working day.

  - In all cases, the amount of Earnest Money, forms and validity shall be announced. Thereafter, the Employer at the opening as the Employer may consider appropriate, will announce the Bidders’ names and such other details.

  - The Employer will prepare minutes of the Bid opening, including the information disclosed to those present in accordance with this Clause 23.

  - The bids accompanied with valid Bid Security , bid document fee, Tender processing fee will be taken up for evaluation with respect to the Qualification Information and other information furnished in Part I of the bid pursuant to Clause 12.1.

As soon as possible, the Evaluation Committee will finalize the list of responsive bidders whose financial bids are eligible for consideration. However, to assist in the examination, evaluation of technical bids, the Employer may at his discretion, ask any bidder for clarification of his bid, however, no additional documents in support of clarification will be entertained.

  - The Employer shall inform the bidders about the result of technical evaluation by uploading on the web portal giving 7 days’ time for objections, if any, from the bidders. The Employer shall finalize the evaluation of technical bids after due consideration of objections received and intimate the bidders, whose Technical Bids are found responsive, of the date, time and place of opening of the Financial Bids. The Bidders so informed, or their representative, may attend the event of opening of Financial Bids.

  - At the time of the opening of the ‘Financial Bid’, the names of the bidders whose bids were found responsive in accordance with Clause 23.5 will be announced. The financial bids of only these bidders will be opened. The responsive bidders’ names, the Bid prices, the total amount of each bid, pursuant to Clause 22 and such other details as the Employer may consider appropriate will be announced by the Employer at the time of bid opening.

  - The Employer shall prepare the minutes of the opening of the Financial Bids.

## Process to be Confidential

  - Information relating to the examination, clarification, evaluation, and comparison of bids and recommendations for the award of a contract shall not be disclosed to bidders or any other person not officially concerned with such process until the award to the successful Bidder has been announced. Any attempt by a Bidder to influence the Employer’s processing of bids or award decisions may result in the rejection of his Bid

## Contacting the Employer

  - Any effort by the Bidder to influence the Employer in the Employer’s bid evaluation,  bid comparison or contract award decisions may result in the rejection of the Bidders’ bid.

## Examination of bids and Determination of Responsiveness

  - During the detailed evaluation of “Technical Bids”, the Employer will determine whether each Bid.

- Meets the eligibility criteria defined in Clauses 3 and 4;

- contains the required documents in physical form and the documents uploaded by the bidder are in order; and

- is substantially responsive to the requirements of the Bidding Documents. During the detailed evaluation of  the “Financial Bids”, the responsiveness of the Bids will be further determined with respect to the remaining bid conditions, i.e., bill of quantities, Specifications and drawings etc.

## Correction of Errors

  - Financial Bids determined to be substantially responsive will be checked by the Employer for any arithmetic errors. Errors will be corrected by the Employer as follows:

a)	Where there is a discrepancy between the rates in figures and words, the rates in

words will govern; and

  - The amount stated in the Financial Bid will be corrected as per Clause 27.1 and shall be binding upon the Bidder. If the Bidder does not accept the corrected amount, the Bid shall be rejected and the Bid Security shall be forfeited in accordance with Clause 16.6 (b).

## Evaluation and Comparison of Financial bids

  - The Employer will evaluate and compare only the bids determined to be substantially responsive in accordance with Clause 26.

  - If the Bid of the successful Bidder is Seriously unbalanced in relation to the Employer’s estimate of the cost of work to be performed under the contract, the Employer may require that an Additional Performance Security in addition to Performance Security as set forth in Clause 32 may be obtained at the expense of the successful Bidder to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. The amount of the Additional Performance Security as decided by the Employer shall be final, binding and conclusive on the bidder.

## AWARD OF CONTRACT

## Award Criteria

  - Subject to Clause 31, the Employer will award the Contract to the Bidder whose Bid has been determined to be substantially responsive according to the bidding documents and who has offered the lowest evaluated Bid price.

## Employer’s Right to Accept any bid and to Reject any or all bids

  - Notwithstanding Clause 29, the Employer reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all bids, at any time prior to the award of Contract, without there by incurring any liability to the affected Bidder or bidders or any obligation to inform the affected Bidder or bidders of the grounds for the Employer’s action.

## Notification of Award and Signing of Agreement.

  - The Bidder whose Bid has been accepted will be notified of the award by the Employer prior to expiration of the Bid validity period by e-mail or facsimile confirmed by registered letter. This letter (here in after and in the Part I General Conditions of Contract called the “Letter of Acceptance”) will state the sum that the Employer will pay to the Contractor in consideration of the execution, completion and maintenance of the Works, and of routine maintenance of roads by the Contractor as prescribed by the Contract (here in after and in the Contract called the “Contract Price”).

  - The notification of award will constitute the formation of the Contract, subject only to the furnishing of a performance security in accordance with the provisions of Clause 32.

  - The Agreement will incorporate all agreements between the Employer and the successful Bidder. It will be signed by the Employer and the successful Bidder after the performance security is furnished.

  - Upon furnishing of the Performance Security by the successful Bidder, the Employer will promptly notify the other Bidders that their Bids have been unsuccessful.

## Performance Security

  - Within 10 (ten) days of receipt of Letter of Acceptance, the successful Bidder shall furnish to the Employer an irrevocable and unconditional guarantee from a Bank in the form set forth in Section 4 (Form of Bank Guarantee for Performance Security) for an amount equal to 3% (three percent) of the Bid Price. In case of unbalanced bids mentioned below, the Selected Bidder, along with the Performance Security, shall also furnish to the Authority an irrevocable and unconditional guarantee from a Bank in the same form towards the Additional Performance Security for an amount calculated as under:

- If the Bid Price offered by the Selected Bidder is lower than 20% of the Estimated Project Cost/Cost put to tender, the Additional Performance Security shall be calculated @ 20% of the difference in the (i) Estimated Project Cost (as mentioned in RFP)-20% of the Estimated Project Cost and (ii) the Bid Price offered by the Selected Bidder.

(ii)	Maximum Limit of additional performance security shall be limited to 3% of the Bid price offered by the selected bidder.

(iii)	This Additional Performance Security shall be treated as part of the Performance Security.

- Bank Guarantee, in the name of the Employer, from following banks would be accepted: -

- State Bank of India or its subsidiaries,

- Any Indian Nationalised Bank

- lDBl/ICICI Bank

- A Foreign Bank (issued by a branch outside India) with a counter guarantee from SBI or its subsidiaries or any Indian Nationalised Bank.

- Any Scheduled Commercial Bank approved by RBI having a net worth of not less than Rs. 500 crore as per the latest Annual Report of the Bank. In the case of a Foreign Bank (issued by a branch in India), the net worth in respect of the Indian operations shall only be taken into account.

- The acceptance of the guarantees shall also be subject to the conditions that the capital adequacy of the Bank shall not be less than the latest norms prescribed by RBI.

- The bank guarantee issued by a Cooperative Bank shall not be accepted.

  - The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. The Additional Performance Security shall be valid until 28 (twenty eight) days after Project Completion Date.

  - For avoidance of any doubt, in case of failure of submission of Performance Security within the stipulated time period, the award shall be deemed to be cancelled/ withdrawn. Thereupon all rights, privileges, claims and entitlements of the Contractor under or arising out of the Award shall be deemed to have been waived by, and to have ceased with the concurrence of the Contractor, and the Award shall be deemed to have been withdrawn by the Employer.

  - The agreement will be executed within 10 days of receipt of Performance Security and Additional performance Security, if any as per Clause above.

- Advances

33.1		The Employer will provide Mobilization Advance as provided in Part I General Conditions of Contract.

## CORRUPT OR FRAUDULENT PRACTICES

- Corrupt or Fraudulent Practices

  - The bidders and their respective officers, employees, agents and advisers shall observe the highest standard of ethics during the bidding process. Notwithstanding anything to the contrary contained herein, the Employer may reject any bid  without being liable in any manner whatsoever to the bidder if it determines that the bidder has, directly or indirectly or through an agent, engaged in corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice in the bidding process.

  - Without prejudice to the rights of the Employer under Clause 34.1 herein above, if any bidder is found by the Employer to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice during the bidding process, such bidder shall not be eligible to participate in any tender issued by the Employer during a period of 2 (two) years from the date such bidder is found by the Employer to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice, as the case may be.

  - For the purposes of this Clause 34, the following terms shall have the meaning herein after respectively assigned to them:

- “corrupt practice” means  the offering, giving, receiving, or  soliciting, directly or indirectly, of anything of value to influence the actions of any person connected with the bidding process (for avoidance of doubt, offering of employment  to, or employing, or engaging in any manner whatsoever, directly or indirectly, any official of the Employer who is or has been associated in any manner, directly or indirectly, with the bidding process or has dealt with matters concerning the Contract or arising therefrom, before or after the execution thereof, at any time prior to the expiry of one year from the date such official resigns or retires from or otherwise ceases to be in the service of the Employer, shall be deemed to constitute influencing the actions of a person connected with the bidding process); engaging in any manner whatsoever, whether during the bidding process or after the award or after the execution of the Contract, as the case may be, any person in respect of any matter relating to the Works, who at any time has been or is a legal, financial or technical adviser of the Employer in relation to any matter concerning the Works;

- “fraudulent practice” means a misrepresentation or omission of facts or suppression of facts or disclosure of incomplete facts, in order to influence the bidding process;

- “coercive practice” means impairing or harming or threatening to impair or harm, directly or indirectly, any person or property to influence any person’s participation or action in the bidding process;

- “undesirable practice” means establishing contact with any person connected with or employed or engaged by the Employer with the objective of canvassing, lobbying or in any manner influencing or attempting to influence the bidding process; and

- “Restrictive practice” means forming a cartel or arriving at any understanding or arrangement among bidders with the objective of restricting or manipulating  a full and fair competition in the bidding process.

The Employer requires the Bidder/Contractor to strictly observe the laws against fraud and corruption enforced in India, namely Prevention of Corruption Act, 1988.

## LABOUR LAWS AND FUNDAMENTAL BREACH

- Labour Laws and Regulations

  - The Bidders shall be aware of the provisions of various Labour Laws, Regulations and Welfare Measures applicable for Construction Workers in India, and other obligations stated in the Conditions of Contract.

## Fundamental breach and other obligations

  - The Bidders shall be aware of the provisions of Fundamental Breach and other obligations stated in the Conditions of Contract.

Appendix to ITB

[THE EMPLOYER SHOULD COMPLETE THIS APPENDIX

BEFORE ISSUING THE BID DOCUMENTS]

ITB Clause Reference

1.1)	The Employer is Superintending Engineer, NH Zone P.W.D., Raipur Circle, NH Campus, Pension Bada, Raipur (C.G.),

1.1)	Name and identification number of Works is “Short term maintenance to Raipur-Balodabazar-Sarangarh Road section of NH-130B from Km 51.900 to Km 86.000 in the state of Chhattisgarh” ( Job No.:  …………………….)

[(4.3. B(b) (i). ]	The key equipment to be deployed on contract work.

(For bituminous pavement and earthwork)

- Deleted

- Deleted

- Deleted

- Static Roller (8/10T)					1

- Small Roller/ Compactor				1

- Bitumen/ Emulsion Sprayer				1

- Mechanical Broom (1250 sqm per hour)		1

- Air Compressor						2

- Grade/ Backhoe loader					1

- Water Tanker						2

- Dewatering Pumps					2

- Tipper/ dumper Truck					2

- Mini hot mix plant (6/10 T/Hr capacity)		1

- Deleted

- Deleted

Other equipment

Note:  The bidder must upload scanned copy of the documentary evidence in support of his owning/ leased/rented of the above equipment. In case the bidder proposes to hire or take the above equipment on lease, he should, along with the lease/rent agreement, attach the proof of ownership of this equipment with the company/entity from whom the equipment are proposed to be hired on lease/rent. Any conditional evidence of deployment of above equipment or inadequate proof as required for any of the equipment shall make the bid non-responsive and financial bid shall not be opened.

[4.3 b (b) (ii)] The Number of Technical Personnel, Qualifications and Experience will be as follows:

| S. No. | Personnel | Qualification | Particular Experience (minimum requirement) | No. of Persons |
| --- | --- | --- | --- | --- |
| 1 | Project Manager | Degree in Civil Engineering | 5 years as Project Manager on Highway, Bridge construction / Maintenance works | 1 |
| 2 | Site Engineer-cum- Surveyor Engineer cum Material Engineer | Degree in Civil Engineering | 4 years on Highway Construction/Maintenance works | 1 |
| 3 | Incident cum Road Property Manager cum Route Operation Manager | Graduate from a recognized University | 3 years on Highway Property Management and Maintenance | 1 |
| 4 | Road Safety Auditor | Road Safety Audit Certificate from appropriate approved Govt. agency | 5 years experience | 3 days in every 3 months |

Note: The signed CVs must be uploaded along with the bid. Non-compliance of the above or non-furnishing of the CV as above or conditional deployment of any of the above personnel or proposal to employ lesser number of personnel than above shall make the bid non-responsive and financial bid shall not be opened.

## [9.2.1] - Pre-bid meeting shall be held on ……………… at ………….. Hrs

Photo

Format of Curriculum Vitae (CV) For Proposed Key Staff

- Proposed Position	:

- Name of Staff	:

- Date of Birth		:				(Please furnish proof of age)

- Nationality		:

- Educational Qualification:

(Summarize college/university and other specialized education of staff member, giving names of schools, dates attended and degrees obtained).

(Please furnish proof of qualification)

Contact Address with Phone and Mobile numbers:

- Membership of Professional Societies:

- Publication		:

(List of details of major technical reports/papers published in recognized national and international journals)

- Employment Record:

(Starting with present position, list in reversed order, every employment held. List of all positions held by staff member since graduation, giving dates, names of employing organization, title of positions held and locations of assignments. For experience period of specific assignment must be clearly mentioned, also given client references, where appropriate).

- Summary of the CV

(Furnish a summary of the above CV. The information in the summary shall be precise and accurate. The information in the summary will have bearing on the evaluation of the CV).

- Education:

- Field of Diploma/Graduation and year

- Field of Post Graduation and year

- Any other specific qualification

- Experience

- Total experience in highways:			Years

- Responsibilities held:

- Years

- Years

- Years

- Relevant Experience:		Years

- Permanent Employment with the Firm (Yes/No):

If yes, how many years:

If no, what is the employment Arrangement with Firm?

Certification:

- I am willing to work on the project and I will be available for entire duration of the project assignment and I will not engage myself in any other assignment during the currency of this assignment on the project.

- I, the undersigned, certify that to the best of my knowledge and belief, this bio-data correctly describes me, my qualification and my experience.

Signature of the Candidate

Place:

Date:

Signature of the Authorized Representative of the firm

Place:

Date:

Note:	Each page of the CV shall be signed in ink by both the staff member and the Authorized Representative of the firm.

# SECTION -3

# QUALIFICATION INFORMATION

SECTION -3

QUALIFICATION INFORMATION

The information to be filled in by the Bidder in this section and documents submitted in physical form will be used for the purposes of post qualification as provided for in Clause 4 of the Instructions to Bidders. This information will not be incorporated in the Contract.

## QUALIFICATION INFORMATION

- For Individual bidders

  - a)	Year of Constitution

  - Legal status of Bidder (Proprietorship/Partnership or Pvt. Ltd. firm)

[Upload scanned copy of original]

  - Place of registration:

  - Principal place of  business:

  - Power of Attorney of signatory of Bid [Upload scanned copy and also supply Original

copy in envelope of physical form]]

  - Total value of Civil Engineering construction and/or maintenance works performed in the last three years (in Rs. …………Lakh).

Refer ITB Clause 4.4 A (a)

(Upload scanned copies of certificate from Chartered Accountant and also supply original certificate from Chartered Accountant)

Year	Total value of work performed (Rs. Lac)

2020-21

2021-22

2022-23

  - (a) Work performed as prime contractor/ JV partner provided further that all other qualification criteria are satisfied (in the same name) of a similar nature during the last five years as per ITB Clause 4.3A(b).

| Project Name | Name of the Employer* | Description of work | Value of Contract (Rs. in Lac) | Date of issue of work order | Stipulated period of completion | Actual date of completion* | Remarks explaining reasons for delay in work Completed |
| --- | --- | --- | --- | --- | --- | --- | --- |

* Upload certificate(s) from the Employer (to be given by an officer not below the rank of Executive Engineer or equivalent or higher and also supply original or certified copy in physical form envelope)

Note: 	In case of sub-contractor a certificate from the Executive Engineer or equivalent of the Prime Employer should be obtained from whom an approval for subcontractor has been obtained.

1.4 (b) Information on Bid Capacity (works for which bids have been submitted and accepted and works which are yet to be completed) as on the date 7 days before the last date for bid submission (as per Clause 4.4 of the ITB).

- Existing commitments and on-going works (B)

| Description of work | Place & State | Contract No. | Name & Address of Employer | Value of Contract (Rs Cr) | Stipulated Period of Completion | Value of works* remaining to be completed (Rs Cr) | Escalation factor | Anticipated date of completion | Escalated value of remaining work during completion period of work for which bids are invited |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |

  - Upload certificate (s) from the Engineer(s)-in-Charge of the rank of Executive Engineer or equivalent & also supply original or certified copy of certificate in physical form envelope.

- Details of works for which bid submitted and accepted (i.e. where contract signing is pending)

| Description of works | Place & State | Name & Address of Employer | Date of issue of Letter of Acceptance (LOA) * | Value given in LOA | Stipulated period for completion | Value of work during completion period of work for which bids are invited |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |

  - Upload copy of  LOA

- Bid Capacity (Bidder shall calculate, mention his bid capacity and enclose the supporting calculation)

A	=	Rs.	lakh (enclose the details)

N	=	years

B	=	Rs.	lakh (enclose the details)

available bid capacity  =	AxNx2.5 – B

=	Rs.	Lakhs

  - Availability of Key Equipment essential for carrying out  the Works [Ref. Clause 4.3(B) (b)(i)]. The Bidder should list all the information requested below.

| Item of Equipment | Requirement |  | Availability Proposals |  | Page No of the proof attached |
| --- | --- | --- | --- | --- | --- |
|  | No. | Capacity | Owned/Leased rented | Age/ Condition |  |

Note: The bidder must upload the documentary evidence in support of his owning/leased/rented of the above equipment. In case the bidder proposes to hire or take the above equipment on lease, he should, along with the lease/rent agreement, attach the proof of ownership of these equipment with the company/entity from whom the equipment are proposed to be hired on lease/rent. Any conditional evidence of deployment of above equipment or inadequate proof as required for any of the equipment shall make the bid non-responsive and financial bid shall not be opened.

  - Qualification and Experience of Key Personnel required for administration and execution of the Contract [Ref. Clause 4.3 (b) (b) (ii)]. upload biographical data for technical personnel (Refer also to Clause. 4.1 (e) of Instructions to bidders).

(Refer also to Sub Clause 9.1 of the General Conditions of Contract).

| Position | Name | Qualification | Total Professional Experience (Years) | Experience in the proposed position (Years) |
| --- | --- | --- | --- | --- |

Note: The signed CVs of the Technical Personnel must be uploaded along with the bid. Non- compliance of the above or non-furnishing of the CV as above or conditional deployment of any of the above personnel or proposal to employ lesser number of personnel than above shall make the bid non-responsive and financial bid shall not be opened.

  - Information on litigation history in which the Bidder is involved.

| Other Party | Employer | Cause of Dispute | Amount involved (Rs lakh) | Remarks showing Present Status |
| --- | --- | --- | --- | --- |

- Bidders should upload the scanned copy of the following affidavits/undertakings as per formats enclosed hereinafter and also send original copy of Affidavit/ Undertakings: -

- Affidavit (it should be on stamp paper attested by Notary Public)

- Undertaking regarding availability of minimum cash amounting to 25% of the value of work during implementation of the Contract towards working capital.

- Undertaking that the Bids shall remain valid for the period specified in Clause 15.1

AFFIDAVIT

- I, the undersigned, do hereby certify that all the statements made in the enclosed attachments are true and correct.

- The undersigned also hereby certifies that neither our firm M/s

have abandoned any work in India nor any contract awarded to us for such works have been rescinded, during last five years prior to the date of this bid.

- The undersigned hereby Authorize(s) and request(s) any bank, person, firm or corporation to furnish pertinent information deemed necessary and requested by the Employer to verify this statement or regarding our competence and general reputation.

- The undersigned understands and agrees that further qualifying information may be requested, and agrees to furnish any such information at the request of the Employer and within the prescribed time.

(Signed by an Authorized Representative of the Firm)

Name of the Representative

Name of Firm

Date

To be notarized by Notary

## UNDERTAKING

I, the undersigned do hereby undertake that our firm M/s  	 										  shall maintain availability of minimum cash amounting to 25% of the value of the work during implementation of the Contract towards the working capital.

(Signed by an Authorized Representative of the Firm)

Name of the Representative

Name of Firm

Date

## UNDERTAKING

I, the undersigned do hereby undertake that our firm M/s  	  								agree to abide by this bid for a period of  120  days after the date fixed for receiving the same and it shall be binding on us and may be accepted at any time before the expiration of that period.

(Signed by an Authorized Representative of the Firm)

Name of the Representative

Name of Firm

Date

# SECTION-4

FORMS OF BANK GUARANTEES

LETTER OF ACCEPTANCE (LOA) AND AGREEMENT

SECTION-4

FORMS OF BANK GUARANTEES

LETTER OF ACCEPTANCE (LOA) AND AGREEMENT

FORM OF BANK GUARANTEE FOR BID SECURITY

WHEREAS  	                                                                                                            (Name	of Tenderer)  (hereinafter  called  the  Tenderer)  wishes  to  submit  his  tender  for  Short Term maintenance  work of  Raipur-Balodabazar-Sarangarh Road section of NH-130B  from Km 51.900 to Km 86.000  in the state of Chhattisgarh herein after called “the Tender” KNOW ALL MEN by these present that we 		(Name of Bank) of  		  (Name of country) having our registered office at (		) (hereinafter called the ‘Bank’) are bound unto the ------------------------ (hereinafter called “the Employer”) in the sum of Rs. 		(Rupees  		  	) *for which payment can truly be made to the said Employer. The Bank bind themselves, their successors and assigns by these present with the common seal of the Bank this day 			of 	and undertake to pay the amount of  	 Rs 		( Rs.in words 		) to the Employer upon receipt of his first written demand without the Employer having to substantiate his demand.

The conditions of this obligation are:

- If the tenderer withdraws his tender during the period of Tender validity specified in

the Form of Tender.

Or

- If the Tenderer having been notified of the acceptance of his Tender by the Employer

during the period of tender validity.

  - fails or refuses to execute the Form of Agreement in accordance with the Instructions to Bidders, if required; or

  - fails or refuses to furnish the Performance Security, in accordance with the Instructions to Bidders.

We undertake to pay to the Employer up to the above amount upon receipt of his first written demand, without the employer having to substantiate his demand, provided that in his demand the Employer will note that the amount claimed by him is due to him owing to the occurrence of any one of the above conditions, specifying the occurred condition or conditions.

This guarantee will remain in force up to and including the date 45 days beyond the validity of the bid as stated in the Instructions to Bidders or as it may be extended by the Employer, at any time prior to the closing date for submission of the Tenders Notice of which extension to the Bank is hereby waived. Any demand in respect of this guarantee should be made on the Bank on or before the date of expiry of this guarantee.

Notwithstanding anything contained herein before, our liability under this guarantee is restricted to Rs.                              (Rs. 	                       in words) and the guarantee shall remain valid till

. Unless a claim or a demand in writing is served upon us on or  before

all our liability under this guarantee shall cease.

SIGNATURE OF AUTHORISED REPRESENTATIVE OF THE BANK

NAME AND DESIGNATION 	                                                EMPLOYEE CODE NUMBER

SEAL OF THE BANK

SIGNATURE OF THE WITNESS (IF THIS IS TO BE WITNESSED AS PER BANK’S POLICY)

NAME OF THE WITNESS

ADDRESS OF THE WITNESS

## FORM OF BANK GUARANTEE FOR PERFORMANCE SECURITY

To

Superintending Engineer, NH Circle, P.W.D., Raipur Zone

NH Campus, Pension Bada, Raipur (C.G.),

WHEREAS……………………………………………… (name and address of contractor) hereinafter called “the Contractor” has undertaken, in pursuance of Letter of Acceptance No. ………………………. Dated ………………. to execute………………………. (name of Contract and brief description of Works) (hereinafter called “the Contract”).

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee:

NOW THEREOF we hereby affirm that we are the guarantor and responsible to you on behalf of the Contractor, up to a total amount of Rs……………… (amount of guarantee) (Rupees…	(in words) and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ……………….. (amount of guarantee) as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the works to be performed there under or of any of the contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until 60 days from the date of expiry of the Defects Liability Period.

Notwithstanding anything contained herein before, our liability under this guarantee is restricted to Rs. 	(Rs. 	in words) and the guarantee shall remain valid till  	. Unless a claim or a demand in writing is served upon us on or before  	 all our liability under this guarantee shall cease.

Signature and seal of the Guarantor with Name, Designation, Employee Code Number and Telephone Number………………………………………………………

Name of the Issuing	Name of the Controlling

Bank/Branch-------------------	Branch/Bank------------------------------

Address and Telephone Number	Address and Telephone Number………….

Date………………………….

In the presence of (if this is to be witnessed as per bank’s policy) …………………………………

1………………………………………………………………………………………… (Name, Address and Occupation)

2………………………………………………………………………………………… (Name, Address and Occupation)

An amount shall be inserted by the Guarantor, representing the percentage of the Contract Price

specified in the Contract and denominated in Indian Rupees.

## FORM OF BANK GUARANTEE FOR ADDITIONAL PERFORMANCE SECURITY

To

Superintending Engineer, NH Circle, P.W.D., Raipur Zone

NH Campus, Pension Bada, Raipur (C.G.),

WHEREAS……………………………………………… (name and address of contractor) hereinafter called “the Contractor” has undertaken, in pursuance of Letter of Acceptance No. ………………………. Dated ………………. to execute………………………. (name of Contract and brief description of Works) (hereinafter called “the Contract”).

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee:

NOW THEREOF we hereby affirm that we are the guarantor and responsible to you on behalf of the Contractor, up to a total amount of Rs……………… (amount of guarantee) (Rupees…	(in words) and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of ……………….. (amount of guarantee) as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the works to be performed there under or of any of the contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition or modification.

This guarantee shall be valid until 28 (twenty eight) days after Project Completion Date.

Notwithstanding anything contained herein before, our liability under this guarantee is restricted to Rs. 	(Rs. 	in words) and the guarantee shall remain valid till  	. Unless a claim or a demand in writing is served upon us on or before  	 all our liability under this guarantee shall cease.

Signature and seal of the Guarantor with Name, Designation, Employee Code Number and Telephone Number………………………………………………………

Name of the Issuing	Name of the Controlling

Bank/Branch-------------------	Branch/Bank------------------------------

Address and Telephone Number	Address and Telephone Number………….

Date………………………….

In the presence of (if this is to be witnessed as per bank’s policy) …………………………………

1………………………………………………………………………………………… (Name, Address and Occupation)

2………………………………………………………………………………………… (Name, Address and Occupation)

An amount shall be inserted by the Guarantor, representing the percentage of the Contract Price

specified in the Contract and denominated in Indian Rupees.

FORM OF LETTER OF APPLICATION

To,

Superintending Engineer, NH Circle, P.W.D., Raipur Zone

NH Campus, Pension Bada, Raipur (C.G.),

[Address of Employer]

DESCRIPTION OF WORKS:	BID FOR  “Short term maintenance to Raipur-Balodabazar-Sarangarh Road section of NH-130B  from Km 51.900 to Km 86.000  in the state of Chhattisgarh ”

Dear Sir,

Having examined the Bid Document, Instructions to Bidders, Qualification Information, Scope of

works, etc. for the subject work we hereby submit our bid for the subject work.

It is certified that the information furnished in this document is true and correct. The proposal is unconditional and unqualified. We undersigned accept that the Employer reserves the right to reject any or all applications without assigning any reason.

Thanking you,

Yours faithfully,

(Authorized Signatory)

## For and on behalf of M/s

## FORM OF LETTER OF ACCEPTANCE

No. ………………………….	Dated ………………..….

To

## M/s………………………….

Sub.: …………………………. Name of Work …………………………………

Sir,

Based on your bid submitted on	in compliance of bidding document of [the Employer] for execution of the works of	, it is hereby notified that your bid for a Contract Price of Rs…………… (Rupees in words…	) has been accepted for and on behalf of [the Employer]

You are hereby requested to furnish Performance Security plus additional security in the form detailed in Clause 32.2 of ITB for an amount equivalent to Rs…………… (Rupees in words…..…) within 10 days as per provisions of Clause 32.1 of ITB of the bid document and sign the contract agreement failing which the actions as stipulated in Clause-32.3 of ITB shall be taken.

Thanking you,

Yours faithfully,

(………………..)

Employer

FORM OF AGREEMENT

AGREEMENT

This agreement made the                 	day of                                                 	between the Superintending Engineer, NH Circle, P.W.D., Raipur Zone, NH Campus, Pension Bada, Raipur (C.G.),  on behalf of “Employer” (hereinafter called “the Employer” of the one part and   	                     (here in after called “the Contractor”) of the other part.

AND WHEREAS the Employer invited bids from eligible bidders for the execution of certain

works, viz………………………………………………

AND WHEREAS pursuant to the bid submitted by the Contractor, vide 	(here in after referred to as the “BID” or “ÖFFER”) for the execution of works, the Employer by his letter of acceptance dated 	accepted the offer submitted by the Contractor for the execution and completion of such works and remedying of any defects thereon, on terms and conditions in accordance with the documents listed in Para 2 below.

AND WHEREAS the Contractor by a deed of undertaking dated 	has agreed to abide by all the terms of the bid, including but not limited to the amount quoted for the execution of Contract, as stated in the bid, and also to comply with such terms and conditions as may be required from time to time.

AND WHEREAS the Contractor has agreed to undertake such works and has furnished a Performance Security pursuant to Clause 32 of ITB (Section-2).

NOW THIS AGREEMENT WITNESSETH as follows:

- In this agreement, words and expressions shall have the same meaning as are respectively assigned to them in the conditions of contract hereinafter referred to;

- The following documents shall be deemed to form and be read and construed as part

of this agreement viz.

  - Agreement;

  - Letter of Acceptance;

  - Contractor’s Bid;

  - Contract Data;

  - General Conditions of Contract;

  - Addendum to General Conditions of Contract;

  - Road Maintenance Standards and Specifications for Road Maintenance Works;

  - Drawings, if any;

  - Bill of Quantities; and

  - Any other document listed in the Contract Data.

- The foregoing documents shall be construed as complementary and mutually explanatory one with another. Should any ambiguity or discrepancy be noted, then the order of precedence of these documents shall be subject to the order as listed above and interpreted in the above order of priority.

- In consideration of the payments to be made by the Employer to the Contractor as hereinafter mentioned, the Contractor hereby covenants with the Employer to execute and complete the works and remedy any defects therein in conformity in all respects with the provisions of the contract.

- The Employer hereby covenants to pay the Contractor in consideration of the execution and completion of the works and remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the contract at the times and in the manner prescribed by the contract.

IN WITNESS WHEREOF the parties here to have caused this agreement to be executed the day and year above written. Signed, sealed and delivered by the said Employer through his Authorized Representative and the said Contractor through his Power of Attorney holder.

## Binding Signature of Employer 	Binding Signature of Contractor

For and on behalf of 	For and on behalf of M/s ----------------------

In the presence of	In the Presence of

- Name :	1. Name:

Address:	Address:

- Name :	2. Name:

Address:	Address:

# SECTION -5

GENERAL CONDITIONS OF CONTRACT (GCC) AND CONTRACT DATA

## SECTION 5

GENERAL CONDITIONS OF CONTRACT (GCC)

TABLE OF CLAUSES

| A. | General |  | 31. | Correction of Defects noticed during the Defects Liability Period |
| --- | --- | --- | --- | --- |
| 1. | Definitions |  | 32. | Uncorrected Defects |
| 2. | Interpretation |  | D. | Cost Control |
| 3. | Language and Law |  | 33. | Bill of Quantities |
| 4. | Engineer’s Decisions |  | 34. | Changes in the Quantities |
| 5. | Delegation |  | 35. | Variations |
| 6. | Communications |  | 36. | Payments for Variations |
| 7. | Subcontracting |  | 37. | Cash Flow Forecasts |
| 8. | Other Contractors |  | 38. | Payment Certificates |
| 9. | Personnel and Equipment |  | 39. | Payments |
| 10. | Employer’s and Contractor’s Risks |  | 40. | Compensation Events |
| 11. | Employer’s Risks |  | 41. | Taxes and Currencies for Payments |
| 12. | Contractor’s Risks |  | 42. | Security Deposit/Retention Money |
| 13. | Insurance |  | 43. | Liquidated Damages |
| 14. | Site Investigation Reports |  | 44. | Advance Payments |
| 15. | Queries about the Contract Data |  | 45. | Performance Security |
| 16. | Contractor to Construct the Works |  | 46. | Cost of Repairs |
| 17. | The Works to be completed by Intended Completion Date | the | E. | Finishing the Contract |
| 18. | Approval by the Engineer |  | 47. | Completion |
| 19. | Site Regulations and Safety |  | 48. | Taking Over |
| 20. | Discoveries |  | 49. | Final Account |
| 21. | Possession of the Site |  | 50. | Operation and Maintenance Manual |
| 22. | Access to the Site |  | 51. | Termination |
| 23. | Instructions |  | 52. | Payment upon Termination |
| 24. | Procedure for Dispute Resolution |  | 53. | Property |
| b. | Time Control |  | 54. | Release from Performance |
| 25. | Programme |  |  |  |
| 26. | Extension of the Intended Completion Date |  | F. | Other Conditions of Contract |
| 27. | Delays ordered by the\Engineer |  | 55. | Labour |
| 28. | Management Meetings |  | 56. | Compliance with Labour Regulations |
| C. | Quality Control |  | 57. | Drawings and Photographs of the Works |
| 29. | Identifying Defects |  | 58. | The Apprentices Act, 1961 |
| 30. | Tests |  |  |  |

A. GENERAL

- Definitions

  - Terms which are defined in the Contract Data but not defined in the Conditions of Contract keep their defined meanings. Capital initials are used to identify defined terms.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the Contractor’s Bid.

Certificate of Completion is the Certificate issued by the Engineer upon completion of works or

parts thereof as applicable in accordance with Clause 47.

Compensation Events are those defined in Clause 40.

Contract is the Contract between the Employer and the Contractor to maintain the road assets and to execute, complete, and maintain the Works. It consists of the documents listed in Clause 2.3.

Contract Data defines the documents and other information, which comprise the Contract.

Contractor is a person or corporate body whose Bid to carry out the Road Maintenance Works and Activities has been accepted by the Employer.

Contractor’s bid is the completed Bidding Document submitted by the Contractor to the Employer.

Contract Price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

Defect is any part of the Maintenance Works and Activities not completed in accordance with

the Contract Specifications.

Defects Liability Certificate is the certificate issued by the Engineer, after the Defects Liability

Period has ended and upon correction of Defects by the Contractor.

Defects Liability Period means the period so stipulated in the Contract Data, calculated from the Completion Date, during which the Contractor remains responsible for the rectification of any defect in the Works he has undertaken.

Employer is the party as defined in the Contract Data, who employs the Contractor to carry out the Works. The Employer may delegate any or all functions to a person or body nominated by him for specified functions.

Engineer is the person named in the Contract Data (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Engineer) who is responsible for supervising the execution of the Works and administering the Contract on behalf of the Employer.

Equipment is the Contractor’s machinery and vehicles brought temporarily to the Site to execute the Maintenance Works and Activities.

Intended Completion Date is the date, as given in contract data, on which it is intended that the Contractor shall complete the Works as per scope under the contract. The intended Completion Date may be revised only by the Engineer by issuing an Extension of Time after approval from the Employer.

Letter of Acceptance means the formal acceptance of the Bid by the Employer.

Materials are all supplies, including consumables, used by the Contractor for incorporation in the Maintenance Works and Activities.

Maximum Response Time means the maximum permissible time within which remedial action must be completed prior to a defect exceeding the permissible tolerance. Maximum Response Time commences from the time of earliest detection of the defect by (i) observation of the defect by the Contractor, or (ii) notification of the defect by the Engineer, or (iii) intimation of the defect by a road user.

Notice to Proceed means the notice issued by the Employer to the Contractor to proceed with the work after signing of the contract pursuant to Clause 32.1 of ITB.

Permissible Tolerance means the maximum permissible amount or quantity of a defect in road-asset condition that will not be exceeded at any time. If any defect exceeds the permissible tolerance, it shall be treated as “non-compliance” and the Contractor shall be paid in accordance with the relevant provisions in this contract.

Project Manager is a person appointed by the Contractor who is in charge of managing all activities of the Contractor under the Contract. He is also the Contractor’s Representative for the purpose of this Contract.

Road means the Road or package of roads in network or scattered for which the Maintenance Works and Activities are to be carried out under the Contract.

“Road Assets” include the following:

    - Main carriageway with shoulders (paved and/or earthen), medians, slip roads, service roads;

    - Road embankment including slopes, protection works, kerbs and chute drains;

    - Roadway in cutting including slopes protection works, drains;

    - Culverts, Bridges, Over/Underpasses, retaining walls, Guide bunds, Floor protection works;

    - Road signs, road markings, road delineators, guard rails, safety barriers, railings, fencings, parapets, kilometer stones, 200 m stones, road boundary stones;

    - All types of drains, trees, plantations and erosion control measures;

    - Road land;

    - Any other project facility or asset forming integral part of the road(s).

Road Maintenance Standards is the collective term for parameters which define the condition in which the road assets are required to be maintained and other requirements regarding safety and quality of works to be complied with by the Contractor.

## Road Maintenance Works and Activities to be carried out by Contractor shall include:

Maintenance of the road specified in the BOQ and executing other items of road maintenance works as ordered by the Engineer.

## Rectification Standard

The Contractor shall maintain the specific parts of the road aspects as specified in BOQ or as ordered by Engineer in charge and ensure road users safety and comfort. The maintenance activities shall be so planned that the defects are repaired well before they reach maximum condition as per the permissible tolerance

Site is the area defined as such in the Contract Data, where maintenance works are to be

executed.

Specifications means the Specifications of the Maintenance Works including the Road

Maintenance Standards as per the Contract.

Start Date is given in the Contract Data. It is the date when the Contractor shall commence execution of the Works.

Service Level means the defined condition in which the road assets are to be maintained by the

Contractor.

Sub-Contractor is a person or corporate body who has a Contract with the Contractor to carry out a work under the Contract, which includes part of the agreed scope of works at the Site.

Temporary Works are works designed, constructed, installed and removed by the Contractor that are needed for Works and Activities.

Time for Completion means the duration for completing the execution of maintenance works and passing the tests on completion of the Works or any Section or part thereof as stated in the Contract Data or as extended by the Engineer by issuing an Extension of Time after the approval from the Employer.

Variation is an instruction given by the Engineer in writing which varies the scope of Maintenance Works.

Work Order is an order issued by the Engineer to the Contractor for execution of certain works, specifying the time limits which may be in variance with the approved programme or in variation to the scope of work depending upon the site requirement.

## Interpretation

  - In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract Unless specifically defined. The Engineer will provide instructions clarifying queries about these Conditions of Contract.

  - If part completion is specified in the Contract Data, references in the Conditions of Contract to the Works, the Completion Date and the Intended Completion Date apply to any part of the Works (other than references to the Completion Date and Intended Completion Date for the whole of Works).

  - The following documents shall be deemed to form and be read and construed as part of the Contract. In case any ambiguity or discrepancy is noted, then the Contract shall be interpreted in the following order of priority:

    - Agreement;

    - Notice to Proceed with the Work;

    - Letter of Acceptance;

    - Contractor’s Bid;

    - Contract Data;

    - General Conditions of Contract;

    - Road Maintenance Standards and Specifications for Road Maintenance Works,

Part I and Part Il;

    - Priced Bill of Quantities; and

    - Any other documents listed in the Contract Data.

## Language and Law

  - The language of the Contract shall be in English and the law governing the Contract as given in Contract Data.

## Engineer’s Decisions

  - The Employer shall designate and notify to the Contractor in writing the name of the Engineer.

  - Except where otherwise specifically stated, the Engineer will decide contractual matters between the Employer and the Contractor in the role representing the Employer. The Engineer shall have no authority to relieve the Contractor of any of his obligations under the Contract.

## Delegation

  - The Engineer, duly informing the Employer, may delegate any of his duties and responsibilities to other people, after notifying the Contractor and may cancel any delegation under intimation to the Contractor.

## Communications

  - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered as per Indian Law.

## Subcontracting

  - The Contractor may subcontract any portion of work, up to a limit specified in Contract Data, with the approval of the Engineer but may not assign the Contract without the approval of the Employer in writing. Subcontracting shall neither alter the Contractor’s obligations, nor relieve the Contractor from any liability or obligation under the Contract.

  - The Contractor shall not be required to obtain any consent from the Employer for:

- the sub-contracting of any part of the Works for which the Sub-Contractor is named in the Contract;

- the provision for labour, or labour component;

- the purchase of Materials which are in accordance with the standards specified

in the Contract.

  - Beyond what has been stated in Clauses 7.1 and 7.2, if the Contractor proposes sub-contracting of any part of work during execution of the Works, because of some unforeseen circumstances to enable him to complete the Works as per terms of the Contract, the Employer will consider the following before according approval:

- The Contractor shall not sub-contract the whole of Works.

- The Contractor shall not sub-contract

- any part of the Work without prior consent of the Employer. Any such consent shall not relieve the Contractor from any liability or obligation under the Contract and he shall be fully responsible for the acts, defaults and neglects of any of his sub-Contractor, his agents or workmen as if they were the acts, defaults or neglects of the Contractor, his agents and workmen.

  - The Engineer should satisfy himself before recommending to the Employer whether

- the circumstances warrant such sub-contracting; and

- the sub-Contractor so proposed for the Work possess the experience, qualifications and equipment necessary for the job proposed to be entrusted to him in proportion to the quantum of Works to be sub-contracted.

## Other Contractors

  - The Contractor shall cooperate and share the Site with other Contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the Contract Data. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of Other Contractors and shall notify the Contractor of any such modification. The Contractor shall cooperate in such situations as well.

  - The Contractor should take up the works in convenient reaches as decided by the Engineer to ensure that there is least hindrance to the smooth flow of traffic including movement of vehicles and equipment of other Contractors till the completion of Works.

## Personnel and Equipment

  - The Contractor shall employ the technical personnel named in the Contract Data or other technical persons approved by the Engineer. The Engineer will approve any proposed replacement of technical personnel only if their relevant qualifications and abilities are substantially equal to or better than those of the personnel stated in the Contract Data. If the personnel stated in the Contract Data are not deployed on site by the Contractor within 15 days of issue of notice to proceed with the work, a penalty of 5000/- per day per person shall be levied for next 30 days, beyond which it shall be treated as a breach of Contract and action will be taken as per Clause 51.

  - The Contractor shall use the equipment identified in the bid along with competent

operators and adequate stock of spares for smooth operations.

  - If the Engineer asks the Contractor to remove a person who is a member of the Contractor’s staff or work force, stating the reasons, the Contractor shall ensure that the person leaves the Site within seven days and has no further connection with the Works under the Contract.

  - The Contractor shall establish, within his own organizational structure, a planning unit, staffed with suitably qualified personnel. The team will be headed by a Project Manager who will be assisted by his representatives, i.e. Site Manager and Manager, Planning. The task of this unit will be:

    - To plan, and to verify continuously the degree of compliance by the Contractor with the specified Road Maintenance Standards and report the same to the Engineer in the format acceptable to the Engineer.

    - To maintain and update the road condition inventory regularly.

    - To assist the Engineer in verification of the compliance.

  - The Contractor’s planning unit mentioned under Sub-clause 9.4 shall report the level of compliance with the required Service Levels in the standard formats acceptable to the Engineer.

## .	Employer’s and Contractor’s Risks

  - The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’s risks.

## Employer’s Risks

  - The Employer is responsible for the expected risks which are (a) in so far as they directly affect the execution of the Maintenance Works and Activities included in the Contract, the risks of war, hostilities, invasion, act of foreign enemies, rebellion, revolution, insurrection or military or usurped power, civil war, riot, commotion or disorder (unless restricted to the Contractor’s employees), natural calamities and contamination from any nuclear fuel or nuclear waste or radioactive toxic, explosive.

## Contractor’s Risks

  - All risks of loss of or damage to physical property and of personal injury and death, which arise during and in consequence of the performance of the Contract other than the excepted risks, referred to in Clause 11.1, are the risks of the Contractor.

## Insurance

  - The Contractor at his cost shall provide, in the joint names of the Employer and the Contractor, insurance cover from the Start Date to the completion of defect liability period, in that amounts and deductibles stated in the Contract Data for the following events which are due to the Contractor’s risks:

    - Loss of or damage to the Works and Materials

    - Loss of or damage to Equipment

    - Loss of or damage to property (except the Works Materials and Equipment) in connection with the Contract

    - Third Party Liability Insurance

    - Automobile Liability Insurance

    - Workers’ Compensation

    - Employer’s Liability

    - Other Insurances

  - Insurance policies and certificates for insurance shall be delivered by the Contractor to the Engineer for the Engineer’s approval before the Start Date. All such insurance shall provide for compensation to be payable in Indian Rupees to rectify the loss or damage incurred.

  - If the Contractor does not provide any of the policies and certificates required, the Employer may affect the insurance which the Contractor should have provided and recover the premiums the Employer had paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due from the Contractor.

  - Alterations to the terms of insurance shall not be made without the approval of the Engineer.

  - Both parties shall comply with any conditions of the insurance policies. The Contractor shall ensure that wherever applicable, its Sub-Contractor(s) shall take out and maintain in effect adequate insurance policies for their personnel and vehicles and for works executed by them under the Contract unless such Sub-Contractor(s) is/are covered by the policies taken out by the Contractor.

## Site Investigation Reports

  - The Contractor, in preparing the Bid, may rely at his own risks and liability on any Site Investigation Reports referred to in the Contract Data, supplemented by any other information available to him.

## Queries about the Contract Data

  - The authorized representative of the Employer as stated in the Contract data will

Clarify queries on the Contract Data.

## Contractor to Construct the Works

  - The Contractor’s obligations cover the carrying out of all Maintenance Works and Activities as defined in the Contract for keeping the roads in accordance with the Road Maintenance Standards.

The  Contractor shall construct, install and  maintain the Works  in accordance with the Specifications

and Drawings.

## The Works to be completed by the Intended Completion Date

  - The Contractor may commence execution of the Maintenance Works and Activities on the Start Date and shall carry out the Works in accordance with the Programme submitted by the Contractor, as updated with the approval of the Engineer, and complete them by the Intended Completion Date.

## Approval by the Engineer

  - The Contractor shall prepare/propose the Maintenance Manuals as per relevant applicable Standards and Specifications and existing policies/guidelines/practices and get the same approved from the Engineer/Employer.

  - The Contractor shall submit Specifications and Drawings showing the proposed Temporary Works to the Engineer, who is to approve them if they comply with Specifications and drawings.

  - The Contractor shall be responsible for design of Temporary Works.

  - The Engineer’s approval shall not alter the Contractor’s responsibility for design of the Temporary Works.

  - The Contractor shall obtain approval of third parties to the design of Temporary Works by Engineer.

  - All Drawings prepared by the Contractor for the execution of temporary or permanent Works, are subject to prior approval by the Engineer before their use.

## Site Regulations and Safety

  - The Contractor shall be responsible for the safety of all activities on the Site, including arrangements for smooth flow of traffic at his own cost as per guidelines of the IRC/Ministry of Road Transport & Highways. He shall provide proper barricading, diversion boards, etc. He shall be fully responsible for the safety of workers and staff at site and provide safety helmets, reflective jackets and other PPE to the workers, inspecting officers and supervisors.

## Discoveries

  - Anything of historical or other interest or of significant value unexpectedly discovered on the Site is the property of the Employer. The Contractor shall notify the Engineer of such discoveries and carry out the Engineer’s instructions for dealing with them.

## Possession of the Site

  - The Employer shall give possession of all parts of the Site to the Contractor on or before the start date of the Contract.

## Access to the Site

  - The Contractor shall allow access to the Site and to any place where work in connection with the Contract is being carried out, or is intended to be carried out to the Engineer and any person/persons/agency authorized by:

    - The Engineer

    - The Employer

## Instructions

  - The Contractor shall carry out all instructions of the Engineer pertaining to the maintenance works which comply with the applicable laws where the Site is located.

  - The Contractor shall permit the Engineer/Employer to inspect the Contractor’s contemporary records in respect of invoice of bitumen, cement, aggregates and steel, if so desired by the Engineer.

## Procedure for Dispute Resolution

  - Arbitration

The procedure for arbitration will be as follows:

- In case of Dispute or difference arising between the Employer and the Contractor relating to any matter arising out of or connected with this contract, such disputes  or differences shall be settled in accordance with the Arbitration and Conciliation Act, 1996 as amended vide Act of 2015. The Arbitral Tribunal shall consist of sole Arbitrator from the panel of three Arbitrators proposed by the Employer and choice of selecting one given to the Contractor. Contractor shall select one out of the three names of Arbitrators given to him within 30 days failing which the Employer shall nominate the Arbitrator out of the panel of three Arbitrators. In case the Contractor objects to the Arbitrator selected by the Employer, the Employer shall refer selection of Arbitrator to the Indian Roads Congress for nominating the Arbitrator for the dispute and both parties agree that the Arbitrator so selected by IRC shall decide the dispute. Indian Roads Congress shall try to appoint Arbitrator preferably from the state where the project is located or otherwise from adjoining States.

- Arbitration proceedings shall be held at Raipur, Chhattisgarh, India, and the language of the arbitration proceedings and that of all documents and communications between the parties shall be English.

- The decision of the Arbitrator shall be final and binding upon both parties. The cost and expenses of Arbitration proceedings will be paid as determined by the Arbitral Tribunal However, the expenses incurred by each party in connection with the preparation, presentation, etc. of its proceedings shall be borne by each party itself. The fees and expenses of the Arbitrator shall be shared equally by both the parties.

- Performance under the contract shall continue during the Arbitration proceedings and payments due to the Contractor by the Employer shall not be withheld, unless they are the subject matter of arbitration proceedings.

B. TIME CONTROL

- Programme

  - The Contractor shall submit to the Engineer for approval a programme within period specified in the contract data showing the general methods, arrangements, order, and timing for all the maintenance works and activities.

  - The Engineer may issue the work order in stages specifying the time limit for the same as and when required except the performance-based maintenance items.

  - An update of the Programme shall be a programme showing the actual progress achieved on each activity and the effect of progress achieved on the timing of the remaining Works, including any changes to the sequence of activities.

  - The Contractor shall submit to the Engineer for approval an updated Programme   at intervals. If the Contractor does not submit an updated Programme within this period, the Engineer may withhold the amount stated in the Contract Data from the next payment certificate and continue to withhold this amount until the next payment after the date on which the overdue Programme has been submitted.

  - The Engineer’s approval of the Programme shall not alter the Contractor’s obligations. The Contractor may revise the Programme and submit it to the Engineer again at any time. A revised Programme shall show the effect of Variations and Compensation Events.

## Extension of the Intended Completion Date

  - The Engineer shall extend the Intended Completion Date only after approval of the Employer if a Compensation Event occurs or a Variation is issued which makes it impossible for Completion to be achieved by the Intended Completion Date without the Contractor taking steps to accelerate the remaining Works, which would cause the Contractor to incur additional  cost.

  - The Engineer, within 14 days of receiving full justification from the Contractor for extension of Intended Completion Date, will refer to the Employer his recommendation. The Employer shall, in not more than 21 days from the date of receipt of Engineer’s recommendation, communicate to the Engineer the acceptance or otherwise. The Engineer shall convey the decision of the Employer to the Contractor.

## Delays Ordered by the Engineer

  - The Engineer may instruct the Contractor to delay the start or progress of any activity within the Works. Delay/delays totaling more than 30 days will require prior written approval of the Employer.

## Management Meetings

  - The Engineer may require the Contractor to attend a management meeting. The business of a management meeting shall be to review the plans and progress for the Maintenance Works.

28.2  	The Engineer shall record the business of management meetings and provide copies of the record to those attending the meeting. The responsibility of the parties for actions to be taken shall be decided by the Engineer either during the management meeting or after the management meeting and to be intimated in writing to all those who attended the meeting.

## QUALITY CONTROL

- Identifying Defects

  - The Engineer shall check the Contractor’s work and notify the Contractor of any Defects those are found. Such checking shall not affect the Contractor’s responsibilities. The Engineer may instruct the Contractor to uncover and test any work that the Engineer considers may have a Defect.

## Tests

  - The Contractor shall set up a field laboratory within period stated in contract data and

be solely responsible for:

- Carrying out the mandatory tests prescribed in Technical Specifications and

- For the correctness of test/procedures, whether preformed in his laboratory or elsewhere.

  - If the Engineer instructs the Contractor to carry out a test not specified in the Specifications to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the testing charges and for any number of samples. Otherwise, the Employer shall pay for the testing charges.

## Correction of Defects noticed during the Defects Liability Period

  - The works carried out shall be of very high standard, requiring no major repairs on the road for at least, during defects liability period, after the date of completion of works.

  - If any defects including shrinkage, cracks, other faults appear in the works within the period specified hereunder after issue of “Taking over” certificate, the Engineer shall give notice to the Contractor of any defects before the end of the Defects Liability Period. The Defects Liability Period shall be extended for as long as the defects remain to be corrected.

  - Every time notice of a defect is given, the Contractor shall correct the notified defect at his own cost within the length of time specified in the Engineer’s notice.

  - The defect liability period is not applicable for works of routine maintenance such as pot holes/ patch repairs/ruts repairs/ cleaning and clearing etc., under performance based BOQ item.

However, for other specific items of works (if any), got executed as ordered by Engineer (if any), the Defects Liability Period shall be 36 months, counted from the Date of Completion stated in the Certificate of Completion issued in pursuance of Clause 47.

  - If during the Defects Liability Period any defect is found in the design, engineering, materials and workmanship of the Works and Services executed by the Contractor, then the Contractor shall promptly, in consultation and agreement with the Engineer, appropriately remedy Such defects at its cost, or repair, replace or otherwise make good (as the Contractor shall, at its discretion, determine) such defects as well as any damage to the Road caused by such defects.

  - The Contractor’s obligations under this Clause 31 shall not apply to:

- any material that is supplied by the Employer, and normally consumed in maintenance, or have a normal life shorter than the Defects Liability Period stated herein;

- any design, Specification or other data, supplied or specified by or on behalf of the

Employer or any matter for which the Contractor has disclaimed responsibility herein;

  - The Employer shall offer the Contractor all reasonable opportunity to inspect the defect(s) Noticed, as well as provide all necessary access to the Facilities and the Site to enable him to perform his obligations under this Clause 31.

The Contractor may remove from the Site any Plant and Equipment or any part of the Facilities that are defective, if the nature of the defect, and/or any damage to the Facilities caused by the defect, is such that repairs cannot be expeditiously carried out at the Site.

## Uncorrected Defects

- If the Contractor fails to correct a Defect, to the satisfaction of the Engineer, within the time specified in the Engineer’s notice, the Engineer will assess the cost of having the Defect corrected. The Contractor will pay to the Employer this amount or the Engineer may deduct such amount from any sums due to the Contractor, on correction of the Defect together with 20 percent additional cost as the damages.

- In case of any non-compliance/ delayed compliance of maintenance standards, the damages / reduction in payment shall be applicable as provided under road maintenance Standards Part-I.

## COST CONTROL

- Bill of Quantities

  - The Bill of Quantities shall contain the description of items, units, rates and amount.

  - The Bill of Quantities is used to calculate the Contract Price. The Contractor is paid for the quantity of the work done at the rates given in the Bill of Quantities with accepted/awarded tender premium for each item for the work executed.

The accepted/awarded tender premium above/below the grand total of Project cost as per BOQ shall be applicable for individual item of work to determine payable amount to Contractor subject to contractual provisions.

## Changes in the Quantities

34.1       The final quantity of the work done may differ from the quantity given in the Bill of Quantities. The payment shall be made for the quantities executed. Provided that the items for which lump sum rates have been quoted shall not be measured and the payments for such items The final quantity of the work done may differ from the quantity given in the Bill of Quantities. The payment shall be made for the quantities executed. Provided that the items for which lump sum rates have been quoted shall not be measured and the payments for such items.

## Variations

  - The Engineer may order Variations, with the prior approval of the Employer, he considers necessary or advisable during the progress of the Works. Such Variations shall form part of the Contract and the Contractor shall execute the varied works. Oral orders of the Engineer for Variations, unless followed by written confirmation, shall not be taken into account.

## Payments for Variations

  - If rates for Variation items are specified in the Bill of Quantities, the Contractor shall

carry out such work at the same rate.

  - If the rates for Variation are not specified in the Bill of Quantities, the Engineer shall

derive the rate from similar items in the Bill of Quantities.

  - If the rate for Variation item cannot be determined in the manner specified in Clause 36.1 or 36.2, the Contractor shall, within 14 days of the issue of order of Variation work, inform the Engineer the rate which he proposes to claim, supported by analysis of the rates. The Engineer shall assess the quotation and determine the rate based on prevailing market rates within one month of the submission of the claim by the Contractor and approval from the Employer shall be taken. As far as possible, the rate analysis shall be based on the Standard Data Book and the current Schedule of Rates of the district public works division. The decision of the Employer on the rate so determined shall be final and binding on the Contractor.

## Cash Flow Forecasts

  - When the Programme is updated, the Contractor shall provide the Engineer with an

updated cash flow forecast.

## Payment Certificates

  - The Contractor shall submit to the Engineer monthly statements of the value of the work executed less the cumulative amount certified previously, supported with detailed measurement of the items of work executed.

  - The Engineer shall check the Contractor’s monthly statement within 14 days and certify the amount to be paid to the Contractor after taking into account any credit or debit for the month in question.

  - The value of BOQ items work executed shall be determined, based on measurements by the Engineer.

  - The value of work executed shall comprise the value of the quantities of the items in the Bill of Quantities completed.

  - The value of work executed shall also include the valuation of Variations and Compensation Events.

  - The Engineer/Employer may exclude any item certified in a previous certificate      or reduce the proportion of any item previously certified in any certificate in the light of latest information.

  - The final bill shall be submitted by the Contractor within one month of the actual date of completion of the work; otherwise the Engineer’s certificate of the measurement and of the total amount payable for work accordingly shall be final and payment made accordingly within a period of sixty days as far as possible.

## Payments

  - (a) Quantity Based 1 and 2:-

The quantities given in the bill of quantities or estimated quantities. The basis of payment will be actual quantities of items of work carries out and valued at the rates tendered in the BOQ along with accepted/awarded tender premium. The accepted/awarded tender premium above /below the grand total of the project cost shall be applicable for the individual items of work to determine payable amount to Contractor for work done subject to other contractual provisions. Any variation shall be dealt with as per contract provisions.

(b)	Performance Based:-

Payment for performance based activities shall be indexed on performance scale of 100 marks as given in Table below:

| Sl No | Brief Description | Weightage for performance rating | Remarks |
| --- | --- | --- | --- |
| 1 | Performance based maintenance and pavement repairs (100%) | Pot/patch repair - 50% | Length in which road is maintained without pot/patch rectifying the pot\patch within stipulated time during the month under consideration/Total length |
|  |  | Maintenance of embankment slopes/ shoulders, ensuring camber to shoulder-20% | Length in which road Shoulders/slopes maintained rectifying the shoulders/slopes within stipulated time during the month under consideration/Total length |
|  |  | Removal of rank vegetation/ plants/trees branches protruding on to carriageway of obstructing sight distance-15% | Length in which road maintain removing the rank vegetation within stipulated time during the month under consideration/Total length |
|  |  | Removal of stray and dead animals (Item no. 3.4) – 15% | Length in which road maintain removing the stray and dead animals within stipulated time during the month under consideration/Total length |

Note:-

- Performance assessment for performance based items of work, shall be done through   inspection by the Engineer-in-Charge at least two times during the month and overall rating can be done on the basis of average of assessments made during the inspection along with study of / videographic evidence. The Contractor shall be given 1 month time period initially from commencement for pot/patch repair of the pre-existing pot-holes/patches and repair of pavement subsequent to which the if any defect is noticed, the payment shall be subject to deductions.

- The Contractor shall submit video recording to the Engineer-in-Charge of condition of the Project Highway with special emphasis on performance based items.

- For performance based items of work, the Contractor shall be entitled for receiving payment proportionate to the average percentage of performance assessed for achievement between 80% to 100%.

- The Contractor shall not be entitled for payment for performance based maintenance if the average performance is rated less than 80%

- A percentage quoted by bidder shall be entered as a single percentage as Tender Premium % above/ tender discount % below on the estimated rates/amounts specified in the BOQ.

- When the unattended defects are corrected within a week of their communication to the contractor at the cost of the contractor and the amount along with specified damages of 20% are recovered from the contractor those defects would be considered as rectified while assessing the performance achievement.

- Road signs proposed to be installed under Quantity based maintenance in the stretch shall also come under performance based maintenance obligation after they are installed.

- Repeated failure in rectifying the defects / deficiencies even after intimating them to the contractor may lead to termination of contract for contractor default apart from reduction in relevant payments.

- Performance based maintenance can be reduced either in terms of length or in terms of months or both for taking up any development works or other exigencies as decided by the authority and in such cases the payments would be regulated on pro- rata basis in terms of length / period in months or both.

NOTE: Deleted.

** The  Performance based payments percentages are  assessed for the 12 months of work period. In case of any fore-closure of the work in view of declaration of Appointed Date for the Improvement works on the subject reach, the payments shall be reduced proportionately w.r.t the decrease in the Work period.

  - Payments shall be adjusted for deductions for advance payments, security deposit, other recoveries in terms of the Contract and taxes at source, as applicable under the law. The Employer shall pay the Contractor the amounts the Engineer had certified, within 28 days of the date of each certificate.

  - The authorized representative of the Employer shall make the payment certified by

the Engineer.

  - Items of the Works for which no rate or price has been entered in the Bill of Quantities, will not be paid for by the Employer and shall be deemed to be covered by other rates and prices in the Contract.

## Compensation Events

  - The following shall be Compensation Events unless they are caused by the Contractor:

- The Engineer orders a delay or delays exceeding a total of 30 days;

- The effects on the Contractor of any of the Employer’s Risks.

  - If a Compensation Event would prevent the Works being completed before the Intended Completion Date, the Intended Completion Date shall be extended. The Engineer shall decide whether and by how much the Intended Completion Date shall be extended after approval of the Employer.

  - The Contractor shall not be entitled to compensation to the extent that the Employer’s interests are adversely affected by the Contractor not having given early warning or not having cooperated with the Engineer/Employer.

The Contractor will not be entitled to compensation in case the fore-closure of contract in view of declaration of appointed date for the improvement works on the subject reach the payments shall be reduced proportionately w.r.t the decrease in the Work period.

## Taxes and Currencies for Payments

  - The rates quoted by the Contractor shall be deemed to be inclusive of the GST and other levies, duties, royalties, cess, toll, and other taxes of Central and State Governments, local bodies and authorities that the Contractor will have to pay for the performance of this Contract. The Employer will perform such duties in regard to the deduction of such taxes at source as per applicable law.

  - Basic Equipment to be made available in Maintenance/Patrol Vehicle :

Contractor shall deploy one or more Maintenance vehicles for timely and effective performance-based maintenance. The basic equipment to be made available in maintenance vehicle deployed on the performance-based maintenance under DPP shall include but not be limited to the following:

Heavy duty plate Compactor, small sized bitumen distributor cum sprayer with diesel based heating arrangement, emulsion container with emulsion, tools for cutting rank vegetation branches etc., like axes, manual/mechanical saw etc.. Container with different sizes of aggregate, tools required to cut the pothole/patches to regular shape.  Thermo-plastic paint and small paint marking machine, rubber traffic cones, signs, barricade material, flags, reflectors, battery operated lantern etc. Separate larger equipment to be deployed separately for carrying out large size patch work/re-surfacing in identified areas etc., as per the maintenance requirements are to be deployed apart from the small equipment specified above for maintenance work. Skilled manpower to operate the above maintenance tools and labor to assist the skilled manpower should always be available with the maintenance vehicle.

  - All payments shall be made in Indian Rupees.

## Security Deposit/Retention Money

  - The Employer shall retain security deposit of five percent of the amount from each payment due to the Contractor until Completion of the whole of the Works.

  - The security deposit/retention money and the performance security will be released to the Contractor when the Defects Liability Period if any is over, and the Engineer has certified that the Defects, if any, notified by the Engineer to the Contractor before the end of this period have been corrected. Also, the additional performance security will be released after the Project Completion.

  - If the Contractor so desires, then the Security Deposit/retention money can be released on submission of unconditional Bank Guarantee at the following two stages:-

- At a point after the progress of work in financial terms (gross value of work done) has

reached 50% of the contract amount

- After the retention money has been deducted to the full value (5% of the contract amount).

## Liquidated Damages

  - The Contractor shall pay liquidated damages to the Employer at the rate stated in the Contract Data for each day or part thereof that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s other liabilities.

Both the parties expressly agree that the liquidated damages payable by the Contractor are mutually agreed genuine pre-estimated loss and without requirement of any poof of actual damages likely to be suffered and incurred by the Employer and the Employer is entitled to receive the same and are not by way of penalty.

  - If the Intended Completion Date is extended after liquidated damages have been paid, the Engineer shall correct any overpayment of liquidated damages by the Contractor by adjusting in the next payment certificate. The contractor shall not be paid interest on the over payment of liquidated damages.

## Advance Payment-

  - The Employer will make an interest bearing advance payment to the Contractor up to 10% of Contract Price against provision by the Contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts equal to 110% of the advance payment. The guarantee shall remain effective until the advance payment has been repaid, but the amount of the guarantee shall be progressively reduced by the amounts repaid by the Contractor. The Contractor shall take the above advance before 2nd running bill and if the contractor delays seeking the advance, the same is not payable.

  - The Contractor is to use the advance payment only to pay for Equipment, plant and

Mobilization expenses required specifically for execution of the Works. The Contractor shall demonstrate that the advance payment has been used in this way by supplying copies of invoices or other documents to the Engineer.

  - The advance payment shall be repaid with interest @ SBI PLR applicable on the date of release of mobilization advance, by deducting from payments otherwise due to the Contractor. The mobilization advance will be recovered from 3rd running bill up to 8thrunning bill in six equal instalments and the interest will be recovered from 9th running   bill. In any case, the mobilization advance with interest must be recovered within ten months from the date of agreement. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, Compensation Events, or Liquidated Damages.

## Performance Security

  - Subject to further condition in Contract Data, the Performance Security equal to 3 percent of the Contract Price shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in the form given in the Contract Data and by a prescribed bank. The Performance Security shall be valid until a date 28 days after the expiry of Defects Liability Period or completion of the contract in case no defect liability period is specified. The validity shall account for additional 3 months’ time to account for BG verification, signing of contract and start date

## Cost of Repairs

  - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Liability Period shall be remedied/rectified by the Contractor at his cost if the loss or damage arises from the Contractor’s acts or omissions.

## FINISHING THE CONTRACT

- Completion

  - The Contractor shall request the Engineer to issue a certificate of Completion of the

Works, and the Engineer will do so upon deciding that the Works are completed.

## Taking Over

  - The Employer shall take over the Site and the Works within seven days of the

Engineer’s issuing a certificate of Completion.

## Final Account

  - The Contractor shall supply to the Engineer with a detailed account of the total amount that the Contractor considers payable under the Contract before the end of the Defects Liability Period. The Engineer shall issue a Defects Liability Certificate and certify any final payment that is due to the Contractor within 28 days of receiving the Contractor’s account if it is correct and complete. If it is not, the Engineer shall issue within 28 days a schedule that states the scope of the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Engineer shall decide on the amount payable to the Contractor and issue a payment certificate within 28 days of receiving the Contractor’s revised account.

## Operation and Maintenance Manual

  - If “as built” Drawings and/or operation and maintenance manuals are required relating to construction work carried out, the Contractor shall supply them within 28 days from the date of issue of certificate of completion.

  - If the Contractor does not supply the Drawings and/or manuals by the stipulated date or they do not receive the Engineer approval, the Engineer shall withhold the amount equal to Rs. 5 lakh from payments due to the Contractor.

## Termination

  - The Employer or the Contractor may terminate the Contract if the other party causes a fundamental breach of the Contract.

  - Fundamental breaches of Contract include, but shall not be limited to, the following:

- Fundamental Breaches by the Contractor

  - the Contractor stops work or grossly neglects Routine Maintenance Works  and Services for 28 days when no stoppage of work is shown on the current programme and the stoppage has not been authorized by the Engineer;

  - the Contractor is declared as bankrupt or goes into liquidation other than for approved reconstruction or amalgamation;

  - the Engineer/Employer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to remedy the defect and correct it within the period of time determined by the Engineer;

  - the Contractor does not maintain a Security Deposit as per clause;

  - the Contractor has delayed the completion of Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in Clause 43;

  - the aggregate liability of the Contractor to the Employer, exceeds the total amount specified in the Contract Data, provided that this limitation shall not apply to the cost of repairing or replacing defective works and equipment;

  - the Contractor fails to provide insurance cover as required under Clause 13;

  - if the Contractor, in the judgement of the Employer, has engaged in the corrupt or fraudulent practices as defined in Clause 34 of the Instructions to Bidders in competing for or in executing the Contract;

  - if the Contractor fails to set up a field laboratory with the prescribed equipment, within the period specified in the Contract Data;

  - if the Contractor does not deploy any of the personnel stated in Contract Data within 45 days of issue of notice to proceed or does not replace the personnel with a personnel with equivalent qualifications/experience  ;

  - The Contractor violates the provisions of Child Labour (Prohibition & Regulation) Act, 1986;

  - Any other fundamental breaches as specified in the contract data.

  - Without prejudice to any other right or remedies which the Employer may have under this contract upon occurrence of a Contractor’s fundamental breach of contract, the Employer shall be entitled to terminate this contract by issuing a Termination Notice to the Contractor provided that before issuing the Termination Notice, the Employer shall by a Notice inform the Contractor of its intention to issue such Termination Notice and grant 15 days to the Contractor to make a representation and may after the expiry of such 15 days, whether or not it is in receipt of such representation issue the Termination Notice.

  - Notwithstanding the above, the Employer may terminate the Contract for convenience.

  - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonably possible.

## Payment upon Termination

  - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer shall issue a certificate for the value of work done and Materials ordered less advance payments received up to the date of issue of the certificate and less the percentage to apply to the value of the work not completed, as indicated in the Contract Data. If the total amount due to the Employer exceeds any payment due to the Contractor, the difference shall be a debt payable to the Employer and Employer may recover the same from Performance Bank Guarantee.

  - If the Contract is terminated at the Employer’s convenience, the Engineer shall issue a certificate for the value of work done, and a pre-determined amount specified in the contract data to cover the reasonable cost of removal of Equipment and repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the Contract, and less taxes due to be deducted at source as per applicable law.

## Property

  - All Materials on Site, Plant, Equipment, Temporary Works and Works shall be deemed to be the property of the Employer for use for completing balance work if the Contract is terminated because of the Contractor’s default.

## Release from Performance

  - If the Contract is frustrated by the outbreak of war or by any other event entirely outside the control of the Employer or the Contractor, the Engineer shall certify that the Contract has been frustrated. The Contractor shall make the Site safe and stop work as quickly as possible after receiving this certificate and shall be paid for all work carried out before receiving it and for any work carried out afterwards to which a commitment was made.

## OTHER CONDITIONS OF CONTRACT

- Labour

  - The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport; and for compliance of various labour laws/regulations.

  - The Contractor shall, if required by the Engineer, deliver to the Engineer a return in detail, in such form and at such intervals as the Engineer may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on Site and such other information as the Engineer may require.

  - The Contractor’s personnel including equipment operators shall be appropriately qualified, skilled and experienced in their respective trades or occupations. The Engineer may require the Contractor to remove or cause to be removed any person employed on the site or the works, including the Contractor’s representative, if applicable, who

- Persists in any misconduct or lack of care;

- Carries out duties incompetently or negligently;

- Falls to conform with any provision of the contract;

- Persists in any conduct which is prejudicial to safety, health or protection of the environment.

If appropriate, the contractor shall then appoint or cause to be appointed a suitable replacement person

## Compliance with Labor Regulations

  - During continuance of the Contract, the Contractor and his sub-Contractors shall abide at all times by all existing labor enactments and rules made thereunder, regulations, notifications and bye laws of the State or Central Government or local authority and any other labour law (including rules), regulations, bye laws that may be passed or notification that may be issued under any labour law in future either by the State or the Central Government or the local authority. (Salient features of some of the major labour laws that are applicable to construction industry are given in Addendum to General Conditions of Contract.) The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authority on account of contravention of any of the provisions of any Act or rules made thereunder, regulations or notifications including amendments. If the Employer is caused to pay or reimburse, such amounts as may be necessary to cause or observe, or for non-observance of the provisions stipulated in the notifications/bye taws/Acts/Rules/regulations including amendments, if any, on the part of the Contractor, the Employer shall have the right to deduct any money due to the Contractor including his amount of performance security.  The Employer shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by the Employer.

In no case shall the employees of the Contractor and the Sub-Contractor be treated as the employees of the Employer at any point of time.

## Drawings and Photographs of the Works

  - The Contractor shall do photography/video photography of the site firstly before the start of work, secondly mid-way in the execution of different stages of work and lastly after the completion of each item of work. No separate payment will be made to the contractor for this.

  - The Contractor shall not disclose details of Drawings furnished to him and works on which he is engaged without the prior approval of the Engineer in writing. No photograph of the works or any part thereof or plant employed thereon, except those permitted under Clause 57.1, shall be taken or permitted by the Contractor to be taken by any of his employees or   any employees of his sub-Contractors without the prior approval of the Engineer in writing. No photographs/video photography shall be published or otherwise circulated without the approval of the Engineer in writing.

## The Apprentices Act, 1961

  - The Contractor shall duly comply with the provisions of the Apprentices Act, 1961 (Ill of 1961), the rules made there under and the orders that may be issued from time to time under the said Act and the said Rules and on his failure or neglect to do so, he shall be subject to all liabilities and penalties provided by the said Act and said Rules.

## CONTRACT DATA

Items marked “N/A” do not apply in this Contract.

1.1

- The Employer is

Superintending Engineer, NH Circle, P.W.D., Raipur Zone	[Cl.1.1 of ITB]

NH Campus, Pension Bada, Raipur (C.G.),

- The Engineer is:	[Clause 1.1 of GCC]

Designation: Executive Engineer NH Division No.-1, P.W.D. Raipur

Address:  NH Campus, Pension Bada, Raipur (C.G.),	[Cl.1.1]

- The Intended Completion Date for the whole of the Works is [12	months from Start Date except pavement repair for which it is 1 month]	[Cl.1.1, 17&26 of GCC]

- The Site is located at [Raipur-Balodabazar-Sarangarh Road section of NH-130B  from Km 51.000 to Km 86.000  in the state of Chhattisgarh]	[Sr no 1 of NIT]

- The	Start	Date	shall	be	within	15	days	after	the	date	of issue of the Notice to proceed						[Cl.1.1 of GCC]

- (a) The name and identification number of the Contract is

The Works consist of short term maintenance of Raipur-Balodabazar-Sarangarh Road section of NH-130B  from Km 51.900 to Km 86.000  								     [Cl. 1.1 of ITB]

- (a) The law which applies to the Contract is the law of Union of India. [CI.3.1 of GCC]

(b)The language of the Contract documents is English	[Cl.3.1 of GCC]

- The limit of subcontracting is NIL of initial contract price	[CI.7.1 of GCC]

- Schedule of other Contractor- NIL	[Cl.8.1 of GCC]

- The Technical Personnel are	[Cl. 9.1 of GCC]

| S. No. | Personnel | Qualification | Particular Experience (minimum requirement) | No. of Persons |
| --- | --- | --- | --- | --- |
| 1. | Project Manager | Graduate in Civil Engineering | 5 years as Project Manager on Highway, Bridge construction/ Maintenance works | 1 |
| 2. | Site Engineer-cum- Surveyor Engineer- cum- Material Engineer | Graduate in Civil Engineering | 4 years on Highway Construction/ Maintenance works | 1 |
| 3. | Incident cum Road Property Manager -cum-Route Operation Manager | Graduate from a recognized University | 3 years on Highway Property Management and Maintenance | 1 |
| 4 | Road Safety Auditor | Road Safety Audit Certificate from appropriate approved Govt. agency | 5 years experience |  |
|  |  | Graduate in Civil Engineering |  |  |
|  |  | Graduate in Civil Engineering |  | 3 days in every 3 months |

Roles and Responsibilities of Road Safety Auditor

Road Safety Auditor has to inspect the stretches entrusted for maintenance and identify any unsafe conditions giving their location details with chainages etc., and suggest temporary measures for immediate rectification.

He has to indicate whether the suggested immediate rectifications are covered in the BOQ item or are to be approved as variation. If so, the variation requirements are to be furnished to the Engineer in charge.

The Road Safety Auditor has to indicate the maintenance work in progress during his inspection in his inspection report and indicate whether appropriate traffic management measures including barricading, signs, markings, lanterns, reflectors etc., are in place as per the relevant IRC codes and good industry practice or not. The locations and type of maintenance work in progress and the traffic management measures adopted are to be furnished to the Engineer in charge with video graph and / or photographs in support thereof.

- Amount for insurance are:	[Cl.13.1 of GCC]

  - Rupees equivalent to Contract Price.

  - Rupees equivalent to 5% of Contract Price.

  - Rupees equivalent to 5% of Contract Price

  - Rupees 20 lakhs for multiple incidents.

The said insurance shall include all liabilities as per Clause 13.1 and shall be deductible as per premium rate.

- Site Investigation Report - NIL	[Cl 14.1 of GCC]

- The period for submission of the programme for approval of Engineer shall be 30 days from the issue of Letter of Commencement.	[{Cl.25.1 of GCC]

- Amount to be withheld for delays in submission of updated programme: 1% of value of work corresponding to the updated programme.	[Cl. 25.4 of GCC].

- The period for setting up a field laboratory with the prescribed equipment

relevant to items of work in BOQ is 30 days from the date of notice to start work

## [Cl. 30.1 of GCC].

- The Defect Liability Period will be 36   m o n t h s   f o r  periodic renewal and other  improvement works executed (if any) [Cl. 31 of GCC]

| a. Amount of liquidated damages for delay in completion of works | 0.1 percent of the remaining value of contract to be executed, rounded off to the nearest thousand, per day with the minimum of Rs. 10000/- per day |
| --- | --- |
| b. Maximum limit of liquidated damages for delay in completion of work. | 10 per cent of the Initial Contract Price rounded off to the nearest thousand [Clause.43 of GCC] |

- The standard form of Performance Security acceptable to the Employer shall be an

unconditional Bank Guarantee of the type as specified in the Bidding Documents.

## [Cl. 45.1 of GCC]

- The percentage to apply to the value of work not completed representing the Employer’s additional cost for completing the work shall be 20 percent. The Performance Security shall also be forfeited if the Contract is terminated because of a fundamental breach of Contract by the Contractor.	[Cl.52.1 of GCC]

- The reasonable cost of removal of equipment and repatriation of the Contractor’s personnel employed solely on the works in the event of termination of the contract at the Employer’s convenience or because of a fundamental breach of contract by the Employer is to be treated as 3 lakh.                                            [Cl. 52.2 of GCC]

# SECTION 6

ADDENDUM TO GENERAL CONDITIONS OF CONTRACT

## SECTION 6

ADDENDUM TO GENERAL CONDITIONS OF CONTRACT

SALIENT FEATURES OF SOME MAJOR LABOUR LAWS APPLICABLE TO ESTABLISHMENTS ENGAGED IN BUILDING AND OTHER CONSTRUCTION WORKS.

- Workmen Compensation Act, 1923: The Act provides for compensation in case of injury by accident arising out of and during the course of employment.

- Payment of Gratuity Act; 1972: Gratuity is payable to an employee under the Act on satisfaction of certain conditions if an employee has completed the prescribed minimum years (five years) of service or more or on death the rate of prescribed minimum days’ (15 days) wages for every completed year of service. The Act is applicable to all establishments employing the prescribed minimum number (10) or more employees.

- Employee’s P.F. and Miscellaneous Provision Act 1952: The Act provides for monthly contributions by the Employer plus workers at the prescribed rate (10 percent or 8.33 percent). The benefits payable under the Act are:

  - Pension or family pension on retirement or death as the case may be.

  - Deposit linked insurance on the death in harness of the worker.

  - Payment of P.F. accumulation on retirement/death etc.

- Maternity Benefit Act, 1961: The Act provides for leave and some other benefits to women employees in case of confinement or miscarriage etc.

- Contract Labour (Regulation & Abolition) Act, 1970: The Act provides for certain welfare measures to be provided by the Contractor to contract labour and in case the Contractor fails to provide, the same are required to be provided, by the Principal Employer by Law. The principal Employer is required to take Certificate of Registration and the Contractor is required to take license from the designated Officer. The Act is applicable to the establishments or Contractor of Principal Employer if they employ minimum prescribed (20 or more) numbers of contract labour.

- Minimum Wages Act, 1948: The Employer is to pay not less than the Minimum Wages fixed by appropriate Government as per provisions of the Act if the employment is a scheduled employment. Construction of buildings, roads, runways are scheduled employment.

- Payment of Wages Act, 1936: It lays down as to by what date the wages are to   be paid, when it will be paid and what deductions can be made from the wages of workers.

- Equal Remuneration Act, 1979: The Act provides for payment of equal wages for work of equal nature to male and female workers and for not making discrimination against female employees in the matters of transfers, training and promotions etc.

- Payment of bonus Act, 1965: The Act is applicable to all establishments employing minimum prescribed (say, 20 or more) number of workmen. The Act provides for payments of annual bonus within the prescribed range of percentage of wages       to employees drawing up to the prescribed amount of wages, calculated in theprescribed manner. The Act does not apply to certain establishments. The newly set- up establishments are exempted for five years in certain circumstances. States may have different number of employment size.

- Industrial Disputes Act, 1947: The Act lays down the machinery and procedure for resolution of industrial disputes, in what situations a strike or lock-out becomes illegal and what are the requirements for laying off or retrenching the employees or closing down the establishment.

- Industrial Employment (Standing Orders) Act, 1946: It is applicable to all establishments employing minimum prescribed number of persons (say, 100, or 50). The Act provides for laying down rules governing the conditions of employment by the Employer on matters provided in the Act and get these certified by the designated Authority.

- Trade unions Act, 1926: The Act lays down the procedure for registration of trade unions of workmen and employees. The Trade Unions registered under the Act have been given certain immunities from civil and criminal liabilities.

- Child Labour (Prohibition & Regulation) Act, 1986: The Act prohibits employment of children below 14 years of age in certain occupations and processes and provides for regulations of employment of children in all other occupations and processes. Employment of child labour is prohibited in building and construction industry.

- Inter-State Migrant  Workmen’s  (Regulation  of  Employment  &  Conditions  of Service) Act, 1979: The Act is applicable to an establishment which employs minimum prescribed number of labour (say, five or more) inter-state migrant workmen through an intermediary (who has recruited workmen in one state for employment  in an establishment situated in another state). The Inter-State migrant workmen, in an establishment to which this Act becomes applicable, are required to be provided certain facilities such as Housing, Medical-Aid, Travelling expenses from home up to the establishment and back etc.

- The building and Other Construction Workers (Regulation of Employment and Conditions of Service) Act, 1996 and the Cess Act of 1996: All the establishments who carry on any building or other construction work and employ the minimum prescribed (say, 10 or more) number of workers are covered under this Act. All such establishments are required to pay cess at the rate not exceeding 2 percent of the cost of construction as may be notified by the Government. As per current notification, one percent of the cost of construction is payable by the Employer of the establishment. The Employer of the establishment is required to provide safety measures at the building or construction work and other welfare measures, such as canteens, first-aid facilities, ambulance, housing accommodations for workers near to the work place etc. The Employer to whom the Act applies has to obtain a registration certificate from the Registering Officer appointed by the Government.

- Factories Act, 1948: The Act lays down the procedure for approval of plans before setting up a factory, health and safety provisions, welfare provisions, working hours, annual earned leave and rendering information regarding accidents or dangerous occurrences to designated authorities. It is applicable to premises employing the minimum prescribed number of persons (say, 10 persons or more) with aid of power or another minimum prescribed number of persons (say, 20 or more persons) without the aid of power engaged in manufacturing process.

# SECTION -7

ROAD MAINTENANCE STANDARDS AND SPECIFICATIONS FOR ROAD MAINTENANCE WORKS, PART-I AND PART-II

## SECTION-7

ROAD MAINTENANCE STANDARDS AND SPECIFICATIONS FOR ROAD MAINTENANCE WORKS, PART-I AND PART-II

PREAMBLE

The Road Maintenance Standards and Specifications shall be read in conjunction with all other documents constituting the Contract viz. Notice Inviting Tender, Instructions to Bidders; Conditions of Contract, Bill of Quantities and other related documents mentioned in the Bid Documents.

## General

The Standards and Specifications for the Road Maintenance Works and Activities as described

here in after shall comprise of the following:

PART-I	:	Road Maintenance Standards

PART-II	:	Specifications for Road Maintenance Works

Carbon foot prints shall be minimized during the execution of project. If approved by the Employer, the environment friendly machinery like Infrared Recycling Road Maintenance as approved by CRRI/ IRC/ MoRTH shall be got deployed.

## PART-I

ROAD MAINTENANCE STANDARDS

- Inspections

  - The Contractor shall carry out weekly Inspection of project road and submit report to the Engineer on the maintenance works carried out during the week and also identify other items of works with location requiring attention for maintenance.

  - Any maintenance which involves works of emergent nature and/or replacement shall be immediately reported to the Engineer for joint assessment and issue of the work order. Such repairs shall be carried out on authorization by the Engineer except in emergency situations where it needs to be attended to urgently for safety reasons. In such situations, temporary arrangements shall be made immediately and further directions sought from the Engineer.

  - The Engineer or his authorized representatives will monitor road condition and shall carry out at least fortnightly Inspection of the project road to verify that the Contractor is maintaining maintenance standards as per Contract and to make note of non-compliances of Performance based items of BOQ, other items of work and work orders issued for other works. Non-compliance/delayed compliance of maintenance work shall be dealt with as per provisions of GCC Clause 32.1 and maintenance standards herein below.

## 2      Maintenance Standards for performance based items

2.1 The following maintenance standards shall be achieved by the Contractor to be eligible for full payment:

| Item | Permissible Tolerance/Service Level | Measurement and Detection | Maximum Response Time | Rectification Standard |
| --- | --- | --- | --- | --- |
| Item no. 3.1 of Bill no 3 (repair of pot holes/edge cuts/ruts/ patches), | Not more than 5 isolated potholes/ edge cuts in a stretch of 1 km. Maximum size of pot hole/edge cut not more than 300 sq cm x 4 cm depth. | Visual inspection. Area of pot hole/ patches shall be measured by the area of rectangle enclosing the pothole. | Within two days | As per Clause 3004 of MoRTH Specifications |
|  | Max rutting – 2.5% in the sub-section. Rutting not to exceed 20 mm. | Rutting to be measured in isolated locations. |  |  |
|  | Patches not more than 5% of the surface area in a stretch of 1 km. |  |  |  |
| Item no. 3.2 of Bill no 3 (Maintenance of embankment slopes/shoulders) | Not more than 5 stretches of 10m each having gully erosion in embankment / cuts and edge drop in shoulders adjacent to paved area. | Visual inspection | Within 2 days | As per Clause No. clause 408 of Technical Specifications |
| Item no. 3.2 of Bill no 3 (Removal of rank vegetation) | Not more than 5 stretches of 10m each rank vegetation. | Visual inspection | Within 2 days |  |
| Item no. 3.4 of Bill no 3 Removal of animals | To reach the spot where stray animal is detected / informed (to Contractor’s representatives) to be occupying the main carriageway within 30 minutes. | Necessary arrangement to be made by Contractor regular patrolling w.r.t. removal of animals at least once in four hours for entire length of the highway. | Removal of dead animals/ birds and burying them at suitable location within two hours. Removal of stray animals to suitable place out of carriageway |  |

2.2 Deleted.

- The Contractor shall set up and maintain an Incident Management System (IMS) and supply regular incident statistics to the Employer.

Incident Management entails a set of coordinated activities initiated by the Contractor when an incident (an extraordinary event resulting in the reduction of road capacity or creates a hazard for users) occurs, in order to minimize the effects of the incident and restore normal capacity and safety levels to all affected road facilities as efficiently as possible.

The Contractor has to identify relevant agencies (e.g. rescue, fire, hazardous materials, traffic, police, ambulance, hospitals, alternative routes, cleanups) and their representatives and to liaise with these representatives on behalf of the Employer.

The Incident Management Centre on the project highway (minimum 500 sqm.) shall be continuously staffed on a 24 hours basis. The Contractor shall maintain records of the details of all incidents (e.g. collision, hazardous material, breakdown, etc. After occurrence of any major incident, resulting in multiple loss of life, significant periods of road closure or major route rehabilitation work, an incident debriefing report shall be produced and forwarded to the Employer within 24 hours of occurrence. The Incident Management Centre shall monitor the location of route of incident management vehicles/rescue operation vehicles through Vehicle Tracking System (VTS) on continuous basis.

The Contractor will keep a record of the removed accident/damaged vehicles by taking a dated photograph of the same and will submit the report on weekly basis to the Employer/Engineer.

The Contractor will remove dead animals/birds from the carriageway and bury them at a suitable location as directed by the Engineer/Employer within two hours of the incident and accident vehicles/Debris within 4 hours after police inspection. If the Contractor fails to remove the dead animals/birds and accident vehicles/debris from the carriageway within specified time of the incident, he will be levied a penalty of Rs.10,000/- per each such incident.

The Route Patrol Vehicle,and Crane shall be equipped (for 24 x7 period and for total duration of contract) with Vehicle Tracking System, equipment/medicines as mentioned in this Clause

## Route Patrols

The Contractor is required to provide 24 hours per day route patrols to assist the road users   of the highway, to provide information, feedback and perform functions in relation to incident management. To achieve this, the Patrol vehicles fitted with VTS should be fully equipped as well as the patrol persons should be adequately trained in traffic management, road safety and primary first aid. The purpose of these patrols is to:

- Provide the users of the highway with basic mechanical help for vehicles that breakdown on the road and also protect other users from such vehicles.

- Immediately identify traffic hazards of whatever nature, such as unauthorized parking, public transport vehicles, obstructing traffic during passenger loading and unloading, debris, stray animals and the like. The operator shall take the necessary measures to remove such obstructions.

- Provide emergency management at accident scenes until such time as the appropriate authorities arrive.

- Assist with the removal of damaged or mechanically impaired vehicles from the highway.

- Observe, record and report suspect aspects of the highway, hazards and incidental damage caused by vehicles, floods, storms or other random events, such that the highway maintenance records and database are continuously improved.

- Route Patrol in charge / Route Patrol assistant/ Driver with knowledge of repairs will be trained, tested and certified suitably with an I-card issued by the Employer. This should be ensured before commencement date within a week of proposing them.

- The routes entrusted should be marked with chainages at 100 m intervals and the same are to be maintained throughout the duration of the Contract.  These should be amenable to capturing in the regular route video in a readable form.

- Route Patrol Vehicle should carry out Date/Time latitude longitude logged videography of the route every week and furnish to Engineer-in-Charge for review and check on compliance with the requirements of the Contract.  A report on the same shall be submitted along with video recording.

## Patrol Vehicles/Rescue Vehicles

Vehicles should be fully covered having sufficient space for the required equipment storage, fitted with rotating light and hooter, and painted with approved unique colour pattern for quick recognition, with the Employer’s name and emblem painted prominently on sides, back and front, together with the control center and Helpline numbers. Vehicles should be in good condition and registration number not older than two years.

Each vehicle should also carry the following equipment.

- Fire extinguisher 1 no.

- Gas cutter with protective glass (2 Nos.)

- Liquid container 2 nos. Water container with fresh water 1 no Funnel

- Rubber Gloves, Leather Gloves (1 pair, each)

- Brooms on hard bristle, other soft-2 nos.

- Gum boot 4 pair, Rain coat 4 pairs, Blanket 1.

- Torch lights – 4nos. Spare Batteries, Flashing light 1 no.

- Hydraulic jack, towing chain, animal hook, rope

- Tool set (with standard set of spanners, pliers, hammer etc.) shovels.

- Battery charger, jumper cables

- Diamond cutter and chain saw (for cutting metal, reinforced concrete and wood) crow bar (16”)

- Digital Camera, measuring tape

- Paper pad, Forms, pen/pencils, folders.

- First aid kit, Rain Coat, water proof sheets, stretchers (two numbers)

- List of hospitals.

Each vehicle should also carry the following traffic management equipment, (used/worn out

items shall be replaced forthwith with new ones.)

- Signboards – “Accident ahead” – 3 nos. “Lane merging” – 3 nos “Direction Arrows” – 3 nos. “Speed Limit” (80/60/40)-3 nos.” keep left/right - 2 nos. (all signs 1200 mm size and of retro reflective type (high Intensity grade)

- Sign stand set (one for triangular and other for circular sign) 6 sets

- Flags, whistle, reflective hand signal.

- Traffic cones 500 mm size with solar bulb mounted on top-20 Nos.

- Barricades 4 Nos. reflective type 100 m, tape, stands, flags of 600 mm by 600 mm made of good read cloth secured to a staff at 1M length, Paddles of at least 600 mm wide and provided with rigid handle and marking SLOW, STOP.

- As a minimum, each patrol vehicle should carry sufficient communication equipment to render its staff capable of direct communication with the incident Management Control Center established.

## Manpower

The team which is to be deployed with each patrol vehicle, shall be given adequate training for their tasks, especially in first aid, vehicle maintenance and minor repairs. The Contractor must employ sufficient manpower to work in shifts for each patrol vehicle. Typical staffing shall be:

- Route Patrol in-Charge

- Route Patrol Assistance

- Driver with knowledge of vehicle repairs

Typical duties of the Route Patrol in-Charge are:-

- Patrol the corridor to ensure obstruction free flow as per shift standards

- To report to police and assist injured at accident scene and remove all obstructions from road when the vehicles are cleared.

- To provide first aid to injured, contact control room and ambulance service if needed, assist police.

- Report all incidents on radio control, to control room

- To ensure safety of traffic with minimal delay at accidents.

- To assist motorists on broken down vehicles and to ensure that they do not obstruct

free flow.

- Maintain relations with all emergency services, and local safety councils

- To report carriageway condition of drainage, ROW plantations, median plantation etc.

- Check on Encroachment irregularities taking place within ROW, and prevent

unauthorized entry into the corridor.

- Prevent theft of assets and report

- Attend to urgent maintenance for safety requirements.

All times, the Route Patrol In-Charge should have with him a list of telephone numbers and address of all concerned in providing the road users services.

On duty, all staff shall wear distinctive standard jackets having company LOGO, with night visibility. They are to deal with public and hence should be well trained and advised to be courteous and helpful.

Number of Patrol Vehicles shall be as given in BoQ (Bill No.3)

## Ambulance- NA

The vehicle shall be matador van/Swaraj Mazda/Tempo Travelers or equipment with approved colour pattern with the provision of two stretchers, fitted with rotating light for easy recognition with Road Authority name and emblem painted prominently on sides, back and front, together with control center help numbers. The ambulance is required to have the necessary medicines and equipment and also the paramedical staff. The vehicles fitted with VTS should be in good condition and registration number not older than two years. The vehicle shall run minimum 5 km daily (even for dry run), to be eligible for monthly payment.

  - General Ambulance:

Folding Doctor Seat with Belt with adequate height in relation to the stretcher, Antistatic, water proof ply board viny/flooring, Channel/locking system for rolling stretcher, High intensity blinkers, light bar/siren/beacon, Electronic siren with Public Addressing System, Internal lighting with three spot light embedded in ceiling, AC/DC connection and outlet points, wash basin with stainless steel Tank, SS Trash bin cabinet integrated with interiors, Head racks and cupboard, Attendant seat with seat belt to double as second stretcher for stable patients. Provision for communication system where the location of ambulance can be identified, Provision for fog light on sides, Cool/Warm boxes, Provision of Fire Extinguishers, Handled Spotlight, Inverter with facility re-charging from 220V AC and vehicle’s alternative. Oxygen delivery system comprising of cylinder trolley, pressure tubing with regulators, roof mounted Air –Conditioner with appropriate cooling capacity with additional blower for patient cabin, Extrication equipment and good suspension to cater for smooth transportation

  - Basic Life Support System

Automatic loading stretcher, scoop stretcher, folding stretcher, spine board full vacuum splint kit/foldable splints, C-Collars, Oxygen Cylinder with accessories mounted/with manifold and pressure indictors, Oxygen Cylinder (aluminum portable), BP Instruments (Wall mounted-Aneroid), Stethoscope, Automatic defibrillator, Resuscitations bag (ambu bag, laryngoscope, airways and mask of different size including pediatric), manual foot operated suction pump. I.V. Fluid and I.V. Sets, Tourniquet, First-Aid Box (Dressing material/Antiseptic lotion/ Analgesic etc.) Linen/Blanket, Laryngeal mask airway of all sizes.

The following paramedical staff are required with proper uniform and name of the person written on the uniform:

Trained Paramedical staff	1

Nursing staff with knowledge of first aid	1

Driver for ambulance	1

Number of Ambulance shall be provided as given in BoQ (Bill No.3)

## Tow Away Vehicle

The vehicle fitted with VTS shall be in good condition and registration number not older than   2 years. The vehicle shall be painted with approved colour pattern with road authority name and emblem painted sides, back and front. The Contractor must employ following manpower to work in shifts:

  - Driver with knowledge of vehicle repair

  - A helper

The vehicle shall run minimum 5 km daily (even for dry run), to be eligible for monthly payment. Number of Tow Away Vehicles shall be provided as given in BoQ (Bill No.3)

- In case of absence/deficiencies in respect of vehicles/manpower/equipment, as mentioned herein, found during inspection by Engineer/Authority Representative, a penalty of Rs.5000/- per item per incidence shall be levied.

## 3     Maintenance Standards for Other BOQ Items

## 3.1 Maintenance standards for cleaning, clearing and repairing roadside open/ unlined/ lined/ covered drains and  cross drainage works

## i) The work shall consist of cleaning, clearing, deepening and reshaping of roadside drains and making shallow lateral drains on shoulders to drain out the rain water/ surface water effectively from bituminous surface as well as from roadside berms.

## ii) Disposal of sediments, extraneous debris or vegetation growth, blocking flow.

## iii) Safety devices and signs shall be placed as per MoRTH Specifications for Road and Bridge Works (5th Revision) Clause No. 112.

## iv) The excavated material shall be disposed off as directed by Engineer-in-charge with all leads and lifts

## v) The drain slopes and sides shall be dressed up to original flow line and cross section

Performance based maintenance: Performance based maintenance shall include the following

Incident management and Pavement Repairs:-

Incident management and Pavement Repairs shall cover following items (Stretches less than 10m in length at one location to be dealt).

a. Repair of earthen shoulders/earthen side slopes of embankment

b. Carrying out PotPatch repairs with BC/BC + DBM/BC + DBM + WMM as the case may be

c. Repair of existing road signs

d. Cleaning of CD structures/ drains.

e. Removal of rank vegetation/plants/tree branches protruding on to carriageway or obstructing sight distance.

f. Engaging of mobile crane (tow away vehicle) for clearing of road during the accidents

g. Providing, running, and maintaining route patrol vehicle.

3.1 Basic Equipment to be made available in Maintenance/Patrol Vehicle:-

Contractor shall deploy Maintenance vehicle for timely and effective performance based maintenance. The basic equipment to be made available in maintenance vehicle deployed on the performance based maintenance shall include but not be limited to the following:

Heavy duty plate Compactor, small sized bitumen distributor cum sprayer with diesel based heating arrangement, emulsion container with emulsion, tools for cutting rank vegetation branches etc. like axes, manual/mechanical saw etc. Container with different sizes of aggregate, tools required to cut the pothole/patches to regular shape. Thermo-plastic paint and small paint marking machine, rubber traffic cones, signs, barricade material, flags, reflectors, battery operated lantern etc. Separate larger equipment to be deployed separately for carrying out large size patch work/re-surfacing in identified areas etc., as per the maintenance requirements are to be deployed apart from the small equipment specified above for maintenance work. Skilled manpower to operate the above maintenance tools and labor to assist the skilled manpower should always be available with the maintenance vehicle.

4.2 Maintenance Standards for routine maintenance of potholes and patches/fatty surface/rutting/cracks in the pavement:-

i) Potholes in bituminous pavement shall be cut to regular rectangular shape with plain base and rectified through granular base course and DBM of minimum 50mm thickness plus BC of 30mm thickness with primer tack coat etc., as per MORTH Specifications if the pothole depth is extended into granular layers of the pavement so that the surface of the repaired pothole/patch is flush with existing pavement after compaction and passage of traffic without any depression or raised surface with respect to the existing pavement.

ii) In case the depth of the pothole/patch is within bituminous layers of the pavement the same shall be cut to regular rectangular shape with plain base and shall be repaired with DBM and BC layers of appropriate thickness so that the surface of the repaired pothole/patch is flush with existing pavement after compaction and passage of traffic without any depression or raised surface with respect to the existing pavement.

iii) The fatty surface/rutting shall also be repaired after cutting off the excess material and bringing the surface flush with the existing pavement with layers of DBM/BC of suitable thickness with tack coat adequate compaction etc. as per MoRTH specifications.

iv) In case of defects in the concrete pavement surface the same shall be repaired with suitable epoxy concrete, filling of cracks etc., ensuring the repaired surface flush with the existing pavement as per MoRTH specifications and good industry practice.

v) Cracks in bituminous pavement shall be filled with fog seal/sand seal etc., as per MORTH specifications and good industry practice.

4.3 Maintenance Standards for repairing of earthen shoulders:-

i) The earthen shoulders shall be filled with subgrade quality earth and or cut suitably if the shoulders are raised above pavement level with camber of minimum 3% away from the carriageway to ensure adequate drainage.

ii) The level difference between carriageway and the earthen shoulder le threshold shall be removed through 1V 4H wedge or any other suitable method with proper watering/compaction at OMC.

4.4) Maintenance standards for cleaning, clearing and repairing roadside open/ unlined/lined/covered drains and cross drainage works:-

i) The work shall consist of cleaning, clearing, deepening and reshaping of roadside drains and making shallow lateral drains on shoulders to drain out the rain water/ surface water effectively from bituminous surface as well as from roadside berms.

ii) Disposal of sediments, extraneous debris or vegetation growth, blocking flow.

iii) Safety devices and signs shall be placed as per MoRTH Specifications for Road and Bridge Works (5th Revision) Clause No. 112.

iv) The excavated material shall be disposed off as directed by Engineer-in- charge with all leads and lifts.

v) The drain slopes and sides shall be dressed up to original flow line and cross section.

4.5 Maintenance standards for "Removal of rank vegetation/weeds from shoulders and embankment slopes.

i) The contractor shall keep the shoulders, embankment slopes up to right of way (RoW) on both sides complete in all respects.

ii) The work shall include breaking of clods, rough dressing and disposal of waste and vegetation outside RoW as per directions of the Engineer.

iii) The contractor shall maintain separate signed muster rolls of deployed labours & supervisors and log books of tractors. The muster rolls and log books shall be made available for inspection. Xerox copy of log books and muster rolls shall be submitted along with statement of work done by the contractor.

iv) If a contractor fails to keep the specified area without weeds, unwanted vegetation, debris (as per provision of BOQ), a penalty of Rs.500/km/incidence shall be imposed. The Engineer's decision in this context is binding on the Contractor.

4.6 Maintenance standards for routine maintenance of road signs and Delineators:-

i) The work shall consist of washing of signs, delineators, removal of posters etc. and repair to supporting structures with repainting.

ii) The road signs and delineators should be thoroughly washed using a detergent solution followed by a lean rinse and whole face of the sign shall be dried.

iii) Defects in supporting structures like bullet holes, surface marks or bent posts shall be repaired with appropriate tools.

iv) Damaged area shall be cleaned and loose/flaking paint shall be removed. Bullet holes shall be led with her and supporting that painted with first quality enamel paint in two or more coats.

## PART-II

SPECIFICATIONS FOR ROAD MAINTENANCE WORKS

- General

  - All materials, works and construction operations shall conform to the requirements laid down in the “Specifications for Road and Bridge Works” (5th Revision), Ministry of Road Transport and Highways, Published by Indian Roads Congress (IRC), New Delhi; IRC:82 “Code of Practice for Maintenance of Bituminous Surfaces on Highways” and IRC:SP:83 Guidelines for Maintenance, Repairs and Rehabilitation of Cement Concrete Pavements” wherever applicable. Where the Specification for a work is not given, sound engineering practice shall be adopted to the satisfaction of the Engineer.

“Specifications for Road and Bridge Works, Ministry of Road Transport and Highways” (5th Revision) is hereinafter referred to as MoRTH Specifications.

## Arrangement for Traffic during Construction

2.1  Contractor shall make all arrangements for safety during construction for the maintenance work in the light of Clause 112 of MoRTH specifications providing 2 cautionary Signs at a distance of 120 m, Channel for traffic clearly marked with pavement markings/painted drums with lanterns at night, Barricades, Signs, Markings, flags, Rubber traffic cones, lights and flagmen as approved by the Engineer to ensure safety. Drop off to be treated with 1V: 4H wedge or any other suitable method.

2.2 He shall provide, erect and maintain all such barricades, signs, markings, flags, lights as required or directed by the Engineer for safety of traffic passing through the section under repairs/improvement.

2.3 All maintenance works on the road shall be carried out in a manner which would cause least interference to the traffic. In stretches where resurfacing or riding quality improvement works are to be taken up, the Contractor during execution of work shall provide and maintain proper passage for traffic. Where it is not possible or safe to allow traffic on part width of the carriageway, a temporary diversion of proper Specifications shall be constructed by the Contractor at his cost. The Contractor shall take prior approval of the Engineer regarding traffic arrangements during construction.

2.4 All arrangements for traffic during construction shall be considered as incidental to the work and shall be Contractor’s responsibility. The Engineer shall determine the penalty to be imposed on the Contractor for deficiency in compliance to the requirement.

## Quality Control

  - Quality control on materials and workmanship is the primary responsibility of the Contractor. Quality control shall be exercised in accordance with the Quality Plan approved by the Engineer. The Engineer may, during and after construction test the quality of materials and work in order to verify conformance with the prescribed Specifications.

  - An attempt shall be made to attend to defects like potholes, undulations, rutting, bleeding, linear and alligator cracks and eroded edges etc. at an initial stage itself. Thermal bonded patches of regular rectangular shapes without bump or sump shall preferably be adopted.

## Specifications for Routine Maintenance

Before any work is started, signs, barriers, etc. shall be placed and necessary arrangements made for ensuring safety of traffic and workers in the work zone, as described in Clause 2 of this Section

Preparation of the surface prior to application of any treatment, shall be carried out in accordance

with the relevant Clauses of MoRTH Specifications.

After completion of the work, the site shall be left cleaned and tidy. No stockpiles of material shall be left on the road.

## Repair and Maintenance works related to Rigid Pavements

All repair and maintenance works related to Rigid Pavements shall be carried out following IRC:SP:83 (Guidelines for Maintenance, Repairs & Rehabilitation of Cement Concrete Pavements).

# SECTION 8

DRAWINGS AND SCHEDULE OF DRAWINGS

SECTION-9

FINANCIAL BID FORM AND BILL OF QUANTITIES

## SECTION-9

FINANCIAL BID FORM AND BILL OF QUANTITIES

FINANCIAL BID FORM

To

(Chief Engineer NH Zone, P.W.D., Raipur)

DESCRIPTION OF WORKS: BID FOR (Name of work)

Reference letter No. …………………

Dear Sir,

- Having examined the site of works and Bid Documents, comprising Instructions to Bidders, Scope of Works, Conditions of Contract, Technical Specifications, Bill of Quantities and schedules for the execution of the abovenamed works, we, the undersigned offer to execute and complete such works and remedy any defects therein in conformity with the said bid documents at tender premium as quoted in the Financial Bid.

- We undertake, if our Bid is accepted, to commence the work within fifteen (15) days of receipt of the order to commence, and to complete and deliver the sections and whole of the works comprised in the contract within the period stated in the bid hereto.

- If our Bid is accepted, we will furnish Performance Security (ies) in the form of a Bank Guarantee to be jointly and severally bound on us, in accordance with the Conditions of Contract.

- We agree to abide by this Bid for a period of One Hundred Twenty (120) days from the last date fixed for Bid Submission and it shall remain binding upon us and may be accepted at any time before the expiry of that period.

- We confirm our agreement to treat the Bid document and other records connected with the works as secret and confidential documents and shall not communicate information contained therein to any person other than the person authorized by the Employer or use such information in any manner prejudicial to the safety and integrity of the works.

- Unless and until an agreement is prepared and executed, this Bid, together with your written acceptance thereof, shall constitute a binding contract between us.

- We understand that you are not bound to accept the lowest or any bid you may receive.

Dated this 	day of 	20-----

Signature 	in the capacity of                             duly authorized**

To Sign Bid for and on behalf of

(in block capital letters)

Address:

Signature of Witness

Name of witness

Address of witness

## DESCRIPTION OF WORKS: FINANCIAL BID

| S. No. | Description | Amount |
| --- | --- | --- |
| 1 | Grand Total of BOQ | Rs. 17471132/- (Rs One Crore Seventy four Lakhs seventy one Thousand One Hundred thirty Two only) |
|  | I/We agree to execute the above works on the tender premium % above/below the Grand Total of the project cost as given above. | (In words) Percent Above/Below |

BILL OF QUANTITIES

1.	Preamble

- The Bill of Quantities (BOQ) shall be read in conjunction with the Instructions to Bidders, Conditions of Contract, Road Maintenance Standards and Specifications for Road Maintenance Works.

- The quantities given in the Bill of Quantities are estimated quantities. The basis of payment will be actual quantities of items of work carried out and valued at the rates tendered in the BOQ along with accepted/awarded tender premium. The accepted/ awarded tender premium above/below the grand total of the project cost shall be applicable for individual items of work to determine payable amount to Contractor for work done subject to other contractual provisions. Any variation shall be dealt with as per contract provisions.

- The rates and prices tendered in the BOQ shall include all equipment, tools, spares, labour, supervision, overheads, consumables, materials, erection, maintenance, testing of input material delivered, profit, taxes and duties together with general risks, liabilities and obligations set out and implied in the contract and other incidentals to comply with the requirements of Standards and Specifications.

- Payment for performance-based activities like treatment & repair of pot holes/ruts/patches in bituminous pavement & maintenance of concrete pavement (Item no. 3.1 & 3.2), maintenance of slopes/shoulder (Item no. 3.3), Removal of rank vegetation (Item no. 3.4) and Removal of animals (Item no. 3.5) shall be indexed on performance scale of 100 marks as given in Table below:

Payment for performance-based activities shall be indexed on performance scale of 100 marks as given in Table below:

| Sl No | Brief Description | Weightage for performance rating | Remarks |
| --- | --- | --- | --- |
| 1 | Performance based maintenance and pavement repairs (100%) | Maintenance of pavement Pot/patch / rut repair or repair of concrete pavement- 50% | Length in which road is maintained without pot/patch rectifying the pot\patch within stipulated time during the month under consideration/Total length |
|  |  | Maintenance of embankment slopes/ shoulders, ensuring camber to shoulder-20% | Length in which road Shoulders/slopes maintained rectifying the shoulders/slopes within stipulated time during the month under consideration/Total length |
|  |  | Removal of rank vegetation/ plants/trees branches protruding on to carriageway of obstructing sight distance-15% | Length in which road maintain removing the rank vegetation within stipulated time during the month under consideration/Total length |
|  |  | Removal of stray and dead animals (Item no. 3.4) – 15% | Length in which road maintain removing the stray and dead animals within stipulated time during the month under consideration/Total length |

Note:-

i) Performance assessment for performance based items of work, shall be done through inspection by the Engineer-in-Charge at least two times during the month and overall rating can be done on the basis of average of assessments made during the inspection along with study of / videographic evidence. The Contractor shall be given 1 month time period initially from commencement for pot/patch repair of the pre-existing pot-holes/patches and repair of pavement subsequent to which the if any defect is noticed, the payment shall be subject to deductions.

ii) The Contractor shall submit video recording to the Engineer-in-Charge of condition of the Project Highway with special emphasis on performance based items.

iii) For performance based items of work, the Contractor shall be entitled for receiving payment proportionate to the average percentage of performance assessed for achievement between 80% to 100%.

iv) The Contractor shall not be entitled for payment for performance based maintenance if the average performance is rated less than 80%

v) A percentage quoted by bidder shall be entered as a single percentage as Tender Premium % above/ tender discount % below on the estimated rates/amounts specified in the BOQ

vi) When the unattended defects are corrected within a week of their communication to the contractor at the cost of the contractor and the amount along with specified damages of 20% are recovered from the contractor those defects would be considered as rectified while assessing the performance achievement

vii) Road signs proposed to be installed under Quantity based maintenance in the stretch shall also come under performance based maintenance obligation after they are installed

viii) Repeated failure in rectifying the defects / deficiencies even after intimating them to the contractor may lead to termination of contract for contractor default apart from reduction in relevant payments.

ix)  Performance based maintenance can be reduced either in terms of length or in terms of months or both     for taking up any development works or other exigencies as decided by the authority and in such cases the payments would be regulated on pro- rata basis in terms of length / period in months or both.

NOTE: The performance assessment shall be carried out as per the MoRT&H Circular NO. RW/NH-33044/15/2021-S&R(P&B), dt: 16.4.2021.

** The  Performance based payments percentages are  assessed for the 12 months of work period. In case of any fore closure of the work inview of declaration of Appointed Date for the Improvement works on the subject reach, the payments shall be reduced proportionately w.r.t the decrease in the Work period.

## NOTE FOR EMPLOYER:

- The items of work given in the BOQ are indicative. Employer may include new items or delete items depending on the requirements of the work.

- The performance based items given in the BOQ are indicative and may be changed as per requirements.

- The rates of items as per applicable Schedule of Rates are required to be worked out and included in the BOQ and accordingly amount is to be calculated and included in the BOQ/Summary.

- Road maintenance standards given in Part-I for some items of work are indicative.

These may be amended / supplemented as per specific requirement of work.

## SUMMARY

| BILL NO. | DESCRIPTION | AMOUNT (Rs.) |
| --- | --- | --- |
| BILL NO. 1 | ROAD MAINTENANCE | 6524142.00 |
| BILL NO. 2 | ROAD PROPERTY MAINTENANCE | 5532078.00 |
| BILL NO. 3 | PERFORMANCE BASED MAINTENANCE AND PAVEMENT REPAIRS | 2749824.00 |
|  | TOTAL | 14806044.00 |
|  | ADD FOR GST 18% | 2665088.00 |
|  | GRAND TOTAL | 17471132.00 |

Bill-I :- ROAD MAINTENANCE

| S.No. | Particular of Items | Quantity | Rate | Unit | Amount |
| --- | --- | --- | --- | --- | --- |
| (1.1) 10.18 | The maintenance of earthen drains include erosion, repair, clearing, cleaning, reshaping, regrading, deepening of side drains as well as catch water drains etc. complete as directed by Engineer-In-Charge. (Frequency of cleaning in urban areas will be quarterly whereas in rural areas, it will be twice in a year i.e. before and after monsoon). | 15147.00 | 16.00 | RM | 242352.00 |
| (1.2) 10.19 | Road side RCC drain or earthen drain cleaning/ clearance through manual labours or with require machinery including removing / placing of drain cover and disposal of waste material upto suitable locations along with transportation charges etc. and as directed by Engineer-In-Charge (Frequency of cleaning in urban areas will be quarterly whereas in rural areas, it will be twice in a year i.e. before and after monsoon). | 3542.00 | 10.00 | RM | 35420.00 |
| (1.3) 10.25 | Dressing of side shoulder/Scrapping the road side shoulder by Mechanical means (By JCB/DOZER) including excavation of raised side shoulders upto 15cm depth including remooving/cutting bushes, grass and dressing shoulder to desired camber and disposing of excavated stuff up to road boundary etc complete. as directed by Engineer In Charge. | 51150.00 | 5.00 | Sqm | 255750.00 |
| (1.4) 4.18 | Construction of Shoulders (Construction of shoulders as per clause 408 with selected soil from borrow pits / borrow areas having CBR not less than 12 and shall have L.L. and P.I. not more than 25% and 6% respectively, inclusive of all leads and lifts, including clearing and scrapping of existing surface, providing required cross fall, compacting. watering rolling and royalty charges etc. complete. |  |  |  |  |
|  | With vibratory roller | 284.01 | 428.00 | Cum | 121555.00 |
| (1.5) 5.02 | Tack coat (Providing and applying tack coat withbitumen emulsion RS-1, grade confirming to IS:8887using emulsion pressure distributor on the prepared bituminous surface cleaned with mechanical broom) as per clause 503 & 112. |  |  |  |  |
| (i) | on Bituminous surfaces @ 0.25 kg per sqm | 28644.00 | 20.00 | Sqm | 572880.00 |
| (1.6) 10.26 | Bituminous Macadam (Providing and laying bituminous macadam as per clause 504 with mixed prepared in minimum 40-60 TPH capacity hot mix plant using crushed aggregates of specified grading premixed with bituminous binder VG-30 transported to site, laid over a previously prepared surface with paver finisher to the required grade, level and alignment and rolled to achieve the desired compaction) |  |  |  |  |
| A | With Mechanical paver finisher |  |  |  |  |
| (ii) | for Grading-II (19 mm nominal maximum size, bitumen content minimum 3.40%) | 238.70 | 6428.00 | Cum | 1534364.00 |
| (1.7) 10.27 | Close Graded Premix Surfacing/Mixed Seal Surfacing (Mechanical means using minimum 40-60 TPH capacity of HMP. Providing, laying and rolling of close-graded premix surfacing material of 20 mm thickness using bitumen to the required line, grade and level to serve as wearing course on a previously prepared base, including mixing in a suitable plant, laying and rolling with a Smooth wheeled roller 8-10 tonne capacity, and finishing to required level and grade, complete as per clause 508) |  |  |  |  |
| I. | With mechanical paver finisher |  |  |  |  |
| A | With bitumen |  |  |  |  |
| ii) | Type-B (13.2 mm to 0.09 mm size aggregates) | 23870.00 | 156.00 | Sqm | 3723720.00 |
| (1.8) Non SOR | Clearing slab/ box type culverts and pipe culverts including clearing, cleaning and reshaping of upstream and downstream faces of these culverts within right of way. The job includes disposal of excess material recovered from site including vegetation outside ROW with all leads and lifts complete in all respects as per direction of Engineer-In-Charge and as per Maintenance Standards Clause 3.1 (Frequency of cleaning will be one time in a year i.e. before start of monsoon). |  |  |  |  |
| (A) | Slab/ Box Type Culverts |  |  |  |  |
| (b) | Two Lane | 29.00 | 900.00 | Nos | 26100.00 |
| (B) | Pipe Culverts |  |  |  |  |
| (b) | Two Lane |  |  |  |  |
| (i) | Single Row | 12.00 | 1000.00 | Nos | 12000.00 |
|  |  | Total Amount of Bill-I :- |  |  | 6524141.00 |

BILL-II :- ROAD PROPERTY MAINTENANCE

| S. No. | Particular of Items | Quantity | Rate | Unit | Amount |
| --- | --- | --- | --- | --- | --- |
| (2.1) 8.04 | Retro- reflectorised Traffic signs (Providing and fixing of retro- reflectorised cautionary, mandatory and informatory sign as per IRC :67 made of retroreflective type sheeting and vide clause 801.3, 2mm thick aluminium sheeting, 3mm/4mm thick Aluminum composite material sheet depending on the size of the sign fixed over back support frame of min 40 x 40 x 5mm Angle mounted on a mild steel circular pipe 65 NB ,3.2 mm thicknness firmly fixed to the ground by means of properly designed foundation with M 15grade cement concrete 45 cm x 45 cm x 60 cm, 60 cm below ground level as per approved drawing and painting all components of the signs and supports as per clause 7.2 of IRC:67 ) |  |  |  |  |
|  | Made of Class-C Micro Prismatic Grade Sheeting of Type-XI (for National Highways and State Highways) |  |  |  |  |
| (ii) | 90 cm equilateral triangle | 16 | 6364 | Nos | 101824.00 |
| (xi) | 50 cm x 60 cm rectangular (single chevron with double plate in singe post) | 7 | 5785 | Nos | 40495.00 |
| (x) | 80 mm x 60 mm rectangular | 5 | 7837 | Nos | 39185.00 |
| (xv) | 90 cm high octagon | 4 | 10014 | Nos | 40056.00 |
| (vi) | 90 cm circular | 5 | 9616 | Nos | 48080.00 |
| (2.2) 8.08 | Painting on Concrete Surfaces One Coat on Old Concrete Surfaces (Painting one coat after filling the surface with synthetic enamel paint in all shades on old plastered concrete surfaces) | 13122.00 | 82 | Sqm | 1076004.00 |
| (2.3) 8.13 | Road Marking with Hot Applied Thermoplastic Compound with Reflectorising Glass Beads on Bituminous Surface (Providing and laying of hot applied thermoplastic compound 2.5 mm thick including reflectorising glass beads @ 250 gms per sqm area, thickness of 2.5 mm is exclusive of surface applied glass beads as per IRC:35 .The finished surface to be level, uniform and free from streaks and holes.) | 2129.00 | 713 | Sqm | 1517977.00 |
| (2.4) 8.14 | Kilo Meter Stone (Reinforced cement concrete M-15grade kilometer stone of standard design as per IRC:8, fixing in position including painting and printing etc) |  |  |  |  |
| (i) | 5th kilometer stone (precast) | 1 | 4325 | Nos | 4325.00 |
| (ii) | Ordinary Kilometer stone (Precast) | 5 | 2510 | Nos | 12550.00 |
| (iii) | Hectometer stone (Precast) | 55 | 740 | Nos | 40700.00 |
| (2.5) 8.46 | Providing Painting, figuring and numbering as per IRC specification complete for |  |  |  |  |
| (i) | 5th kilometer stone (precast) | 5 | 496 | Nos | 2480.00 |
| (ii) | Ordinary Kilometer stone (Precast) | 23 | 214 | Nos | 4922.00 |
| (iii) | Hectometer stone (Precast) | 81 | 30 | Nos | 2430.00 |
| (2.6) 8.09 | Painting on Steel Surfaces (Providing and applying two coats of ready mix paint of approved brand on steel surface after through cleaning of surface to give an even shade) | 15120 | 76 | Sqm | 1149120.00 |
| (2.7) 8.51 | Providing & Fixing Hazard Marker Type-2 Partial Retro Reflective Size 0.30 x 0.90M made of 16 gauge (1.6 mm) thick mild steel sheet Confirming to IS:2062 Painted with one cast of Zinc Chromate Stoving Primer and two coats of Black Stove Enamel (Oven Baked) paint with 10 cm bands of yellow Retro- Reflective Sheeting of Engineering Grade pasted a per IRC:79 including one MS angle Iron post of size 50x50x5 mm of 1.65 meter long duly painted with synthetic enameled paint block including bolts and fixing the same in M-15 concrete black of size 30x30x30cm, including transportation etc. Complete. | 30 | 1491 | Nos | 44730.00 |
| (2.8) 8.54 | Providing & Fixing tree studs in Square/ Round shape of 4” side/diameter made of 2 mm aluminum substrate (Confirming to IS:736 -Material Designation, 24345 or 1900) end reflective surface of High Intensity grade as specified in section 801.3 of MORT&H duly treated with HLVA and fixing the same with four Nos. high strength nails confirming to 1S:1367 on trees at site each. | 600 | 67 | Nos | 40200.00 |
| (2.9) 10.28 | Repair and mantanance of metal Beam crash barrier (MBCB) Providing and fixing GI high tensile button head 16 mm dia bolt length 40 mm nut GI washer grade 4.6 or and/ GI steel cold formed "C" shape channel spacer block length 300 mm of section 150x75x5 mm width 3 holes of 20 mm dia including transportation and welding or adhesive on end of bolt after fixing etc complete |  |  |  |  |
|  | A) Providing and fixing nut , bolt and washer (inclunding adhesive or welding) | 500 | 50 | Nos | 25000.00 |
|  | B) Providing and fixing of GI cold framed , C shape channel Spacer including all | 200 | 340 | Nos | 68000.00 |
|  | C) Replacement o damaged channel post with new channelmpost of ISMC series size 150x75x5 mm 1.80 m. Higt 1.10m. Ground of the road level firmly fixid to ground means of foundation with CC M15 Grade 300x300x1100 | 300 | 2755 | Nos | 826500.00 |
|  | D) Replacment of damaged w metal Beam with new W metal Beam crash barrier compressing o three mm thick corrugated sheet metal beam rail to be fixed on the vertical post | 500 | 895 | Rm | 447500.00 |
|  |  | Total Amount of Bill-II |  |  | 5532078.00 |

| S. No. | Particular of Items | Quantity | Rate | Unit | Amount |
| --- | --- | --- | --- | --- | --- |
| (3.1) Non SOR | Providing treatment and repair to pot holes/ruts of any depth/patch repair of all types of bitumen pavement including providing seal for filling cracks, WMM, bituminous surfacing, complete as per Technical Specification Clause 3004.2, and as per direction of Engineer by using paving grade bitumen/emulsion/cold ready mix material. The job includes removal of all failed material, trimming of completed excavation to provide firm vertical faces, cleaning of surface, painting of tack coat on the sides and base of excavation as per Clause no. 503, back filling the patch with bituminous material as per Clause no. 509. Compacting trimming and finishing the surface to form a smooth continuous surface all as per Clause no. 3004.2 of Technical Specifications. Carrying out cleaning, removing of dust/silt/thrash from carriageway |  |  |  |  |
|  | From KM 51.900 to km 86.000 = 34.100 Km | 34.100 | 2854.00 | Per km per month | 1167857.00 |
| (3.2) Non SOR | Maintenance of cuts and fills slopes/shoulders conforming to Technical Specifications Clause no. 3002. Fill material should be brought from borrow areas located outside ROW conforming to Technical Specification no. 305. Watered and well compacted with plate compactor or power rammer with all leads and lifts as directed by the Engineer |  |  |  |  |
|  | From KM 51.900 to km 86.000 = 34.100 Km | 34.100 | 612 | Per km per month | 250430.00 |
| (3.3) Non SOR | Removal of rank vegetation/ weeds and undesirable vegetation from shoulders, embankment slopes upto ROW (both sides) complete in all respects including breaking of clods, rough dressing, Surface cleaning with mechanical broomer (sides of median & divider) and disposal of waste material and vegetation at a place outside ROW as per direction of Engineer- ln-Charge. |  |  |  |  |
|  | From KM 51.900 to km 86.000 = 34.100 Km | 34.100 | 1166 | Per km per month | 477127.00 |
| (3.4) Non SOR | (a) Removal of dead animals/ birds and burying them at suitable location within two hours. (b) Removal of stray animals to suitable place out of carriageway | 34.100 | 2088 | Per km per month | 854410.00 |
|  |  | Total Amount of Bill-III |  |  | 2749824 |

Note: ln case of any error of Clause of MoRTH Specifications, the appropriate correct clause of the MoRTH Specifications shall prevail, as per the decision of Engineer-In-Charge/Employer.