MINISTRY OF ROAD TRANSPORT & HIGHWAYS

GOVERNMENT OF INDIA

EPC Schedules

FOR

Reconstruction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of bhopalpatnam-warangal-hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis

DECEMBER 2025

THE CHIEF ENGINEER, P.W.D., NH ZONE, RAIPUR, CHHATTISGARH

Schedule A

SCHEDULE - A

(See Clauses 2.1 and 8.1)

### SITE OF THE PROJECT

1	The Site

- Site of the Project Highway shall include the land, buildings, structures and road works as described in Annex-I of this Schedule-A.

- The dates of handing over the Right of Way to the Contractor are specified in Annex-II of this Schedule-A.

- An inventory of the Site including the land, buildings, structures, road works, trees and any other immovable property on, or attached to, the Site shall be prepared jointly by the Authority Representative and the Contractor, and such inventory shall form part of the memorandum referred ion Clause 8.2 (i) of this Agreement.

- The alignment plans of the Project Highway are specified in Annex-III. In the case of sections where no modification in the existing alignment of the Project Highway is contemplated, the alignment plan has not been provided. Alignment plans have only been given for sections where the existing alignment is proposed to be upgraded. The proposed profile of the Project Highway shall be followed by the contractor with minimum FRL as indicated in the alignment plan. The Contractor, however, improve/upgrade the road profile indicated in Annex-III based on site/design requirement.

- The status of the environment clearances obtained or awaited is given in Annex IV.

Project Alignment on Satellite Image.

Annex-I

(Schedule-A)

### SITE

1.	Site

The project road comprises of Reconstruction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of bhopalpatnam-warangal-hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis

2.	Land

The Site of the Project Highway comprises the land as described below:

| Sl. No | Existing Chainages |  | Length (km) | ROW (m) |
| --- | --- | --- | --- | --- |
|  | From (km) | To (km) |  |  |
| 1 | 5.900 | 7.575 | 1.675 | 30.00 |
| 2 | 32.275 | 33.400 | 1.125 | 30.00 |

3.	Carriageway

The details of existing carriageway are given below.

| S. no | Existing Chainage. From | Existing Chainage. To | C/W width (m) | Remarks |
| --- | --- | --- | --- | --- |
| 1 | 5.900 | 7.575 | 7.0 | PAVEMENT |
| 2 | 32.275 | 33.400 | 7.0 | PAVEMENT |

4.	Major Bridges

The Site includes the following Major Bridges:

| S. No. | Existing Chainage (Km) | Type of Structure |  |  | Span Arrangement (m) | Width (m) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Sub-structure | Super structure |  |  |
| Nil |  |  |  |  |  |  |

5.	Road over-bridges (ROB)/ Road under-bridges (RUB)

The Site includes the following ROB/RUB:

| S. No. | Existing Chainage (Km) | Type of Structure |  | Span Arrangement (m) | Width (m) |
| --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Super structure |  |  |
| Nil |  |  |  |  |  |

6.	Grade separators

The Site includes the following grade separators:

| S. No. | Existing Chainage (Km) | Type of Structure |  | Span Arrangement (m) | Width (m) |
| --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Super structure |  |  |
| Nil |  |  |  |  |  |  |

7.	Minor bridges

The Site includes the following minor bridges:

| S. No. | Existing Chainage (Km) | Type of Structure |  |  | No of spans with Span Length (m) | Width (m) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Sub structure | Super Structure |  |  |
| Nil |  |  |  |  |  |  |

8	Railway level crossings

The Site includes the following railway level crossings:

| S. No. | Location (km) | Remarks |
| --- | --- | --- |
| Nil |  |  |

9.	Underpasses (vehicular, non-vehicular)

The Site includes the following underpasses:

| S.No. | Existing Chainage (Km) | Type of structure | No. of span with Span Arrangement (m) | width (m) |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

10.	Culverts

The Site has the following culverts: 7.0 NO

| S. No. | Existing Chainage (km) | Type of Culvert | No. x span length /diameter (m) | Clear Width (m) | Overall Width (m) |
| --- | --- | --- | --- | --- | --- |
| 1 | 6.525 | SLAB CULVERT | 1 x 6.0 M. | 12.0 | 12.90- |
| 2 | 6.650 | SLAB CULVER | 1 x 2.0 M. | 10.80 | 12.00 |
| 3 | 6.775 | SLAB CULVER | 1 x 2.0 M. | 11.10 | 12.15 |
| 4 | 7.375 | SLAB CULVER | 1 x 2.0 M. | 11.10 | 12.10 |
| 5 | 32.375 | SLAB CULVER | 1 x 1.0 M. | 11.70 | 12.90 |
| 6 | 32.725 | SLAB CULVER | 1 x 4.0 M. | 11.10 | 12.90 |
| 7 | 32.850 | SLAB Culvet | 1 x 2.0 M. | 14.60 | 15.60 |

11.	Bus bays

The details of bus bays on the Site are as follows:

| S. No. | Chainage (km) | Length (m) | Left Hand Side | Right Hand Side |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

12.	Truck Lay byes

The details of truck lay byes are as follows:

| S.No. | Chainage (km) | Length (m) | Left Hand Side | Right Hand Side |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

13	Road side drains

The details of the road side drains are as follows:

| S. No. | Location |  | Type & Side |  |
| --- | --- | --- | --- | --- |
|  | From (Km.) | To (Km.) | Masonry / cc (Pucca) | Earthen (Kutcha) |
| Nil |  |  |  |  |

14.	Major junctions-The details of major junctions are as follows:

| S. No | Existing Chainage (km) | Direction | Type | Sides | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  | Nil |  |  |  |

15.	Minor junctions-The details of the minor junctions/Subways (all at grade) are as follows:

| S. No | Existing Chainage (km) | Direction | Type | Sides | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  | Nil |  |  | - |

16.	Bypasses-The details of the bypasses are as follows:

| S. No. | Name of bypass(town) | Chainage (km) | Design Length (Km) | Carriageway |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Width (m) | Type |
| Nil |  |  |  |  |  |

17.	Other structures

| Sl. No. | Chainage(km) | Type of Structure | No. of Spans with span length(m) | Width(m) |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

Annex-I

(Schedule-A)

- Electrical utilities

The site includes the following electrical utilities:

- Extra High-Tension Lines (EHT Lines) *

| S. NO | Chainage |  | Length (in Km) |  |  |  | Crossings |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From | To | 400KV | 220KV | 110KV | 66KV | 400KV | 220KV | 110KV | 66KV |
| NIL |  |  |  |  |  |  |  |  |  |  |

- High Tension/Low Tension Lines (HT/LT Lines) *

| S. NO | Section |  | Length (in Km) |  |  | Crossings (Nos.) |  |  | Transformers |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From | To | 33KV | 11KV | LT | 33KV | 11KV | LT | No | Capacity |
| 1 | NIL |  |  |  |  |  |  |  |  |  |

- Public Health utilities (Water/Sewage Pipe Lines) *The site includes the following Public Health utilities:

| S. No. | Chainage |  | Length (Km) |  |  |  | Crossings |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From | To | Water Supply line |  | Sewage line |  | Water Supply line |  | Sewage line |  |
|  |  |  | With Pumping | With Gravity flow | With Pumping | With Gravity flow | With Pumping | With Gravity flow | With Pumping | With Gravity flow |
| 1. | NIL |  |  |  |  |  |  |  |  |  |

- Other Water Supply utility

| S. No | Section | Village | Type of Utility | Quantity | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  | NIL |  |  |  |

- Any Other Line

Note:- This is illustrative and may change as per features of existing utilities.

Annex – II

(See Clauses 8.3 (i))

(Schedule-A)

### Dates for providing Right of Way of Construction Zone

| Design Chainage From(km) | Design Chainage To(km) | Length Distance(km) | Available Land Width (m) | Proposed Right of Way | Date of Providing ROW |
| --- | --- | --- | --- | --- | --- |
| 5.900 | 7.575 | 1.675 | 30.00 | 30.00 | On appointed Date |
| 32.275 | 33.400 | 1.125 | 30.00 | 30.00 |  |
| Total Length |  | 2.80 |  |  |  |

Annex - III

(Schedule-A)

### Alignment Plans

The Existing alignment of the Project Highway shall be modified in the following sections as per the alignment plan indicated below:

- Finished road level as per existing Road profile shall be followed by the contractor as minimum FRL. In any case, the finished road level of the project highway shall not be less than the existing Road Profile. The contractor shall, however, improve/upgrade the exiting Road profile as indicated in Annex-III based on site/design requirement.

- Typical Road marking & Signages are provided in Annex-III. The contractor shall prepare the detailed traffic signage plan based on site/design requirements as per IRC: 67-2022, IRC: 35-2015 and other relevant specifications/IRC codes/Manual in consultation with the Authority Engineer.

Annex - IV

(Schedule-A)

### Environment Clearances

The project highway does not require environment clearance.

The muck dumping sites shall be identified by the EPC contractor in consultation with the Authority Engineer &Forest department for dumping of muck, and necessary clearances/NOCs/permission shall be obtained by the Contractor in addition to the applicable permissions and clearances as stated in Schedule F.

Schedule B

SCHEDULE - B

(See Clause 2.1)

### DEVELOPMENT OF THE PROJECT HIGHWAY

1	Development of the Project Highway

Development of the Project Highway shall include design and construction of the 2-Lane Project Highway as described in this Schedule-B and in Schedule-C.

- Construction of two Lane with  Granular Shoulder

Up gradation alignment Construction shall include  two-Laning with Granular Shoulder of the Project Highway as described in Annex-I of this Schedule-B and in Schedule-C.

3	Specifications and Standards

The Project Highway shall be designed and constructed in conformity with the specifications and standards specified in Annex-I of Schedule-D.

Annex - I

(Schedule-B)

DESCRIPTION OF PROJECT

Construction of the two– Lane, the  road  of submerged length from km 5.90 to 7.575 and 32.275 to 33.4000 of Bhopalpatnam-Venktapuram-Warangal-Hyderabad Road ofd NH-163 in the State of Chhattisgarh through EPC Basis

1	Construction of Highway.

(i)	The Project Highway is Existing alignment shown in the alignment plans specified in Annexure III of Schedule-A. Geometric deficiencies, if any, in the existing horizontal and vertical profiles shall be corrected as per the prescribed standards for plain/rolling terrain to the extent possible within the available land available with the authority.

(ii)	Width of Carriageway

(a)	Two-Lanning shall be undertaken. The paved carriageway shall be in accordance with the typical cross sections given in Appendix B-I of Schedule–B. Additional widths for widening at horizontal curve shall be as per the Schedule D.

Provided that in the built-up areas the width of the carriageway shall be as specified in the following table:

| S. No. | Built-up Section | Design Chainage (km) |  | Width of carriageway (m) | TCS Type |
| --- | --- | --- | --- | --- | --- |
|  |  | From | To |  |  |
| 1 | Depla | 5.90 | 7.575 | 7.00 M | TCS-01 |
| 2 | Tarlaguda | 33.275 | 33.400 | 7.00 M | TCS-02 |

(b)	Except as otherwise provided in this Agreement, the width of the paved carriageway and cross-sectional features shall conform toparagraph1 (i) above.

(c)	All the cross-sectional elements are to be accommodated within the proposed ROW. If required, suitable retaining structures along with drainage system shall be provided as per site condition and this will not attract any change of scope.

2	Geometric Design and General Features

(i)	General

Geometric design and general features of the Project Highway shall be in accordance with Section 2 of the Manual.

(ii)	Design speed

The design speed shall be ruling speed of 100 km/hr and minimum speed of 80 km per hour.

- Improvement of the existing road geometrics

In the following sections, where improvement of the existing road geometrics to the prescribed standards is not possible, the existing road geometrics shall be improved to the extent possible within the given right of way and proper road signs and safety measures shall be provided:

| S. No. | Design Chainage |  | Type of Deficiency | Speed V (Km/hr) |
| --- | --- | --- | --- | --- |
|  | From | To |  |  |
| Nil |  |  |  |  |

(iv) 	Right of Way

The details of the proposed ROW are given in Annex-II of Schedule -A.

(v)	Type of shoulders

(a)	In built-up sections, 2.5m granular shoulder on either side as per TCS shall be provided in the following stretches:

| Sr. No. | Built-up stretch | Design Chainage (From) | Design Chainage (To) | Length (Km) | TCS | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Depla | 5.90 | 7.575 | 1.675 | TCS-01 | both side of carriage way width of 2.5 m . |
| 1 | Depla | 32.275 | 33.400 | 1.125 | TCS-02 | both side of carriage way width of 2.5 m |

(b)	In open country, granular shoulders shall be provided as per TCS Schedule (Appendix-BI) and the earthen shoulder shall be covered with granular material in full depth up to GSB layer as shown in typical cross section.

(c)	Design and specifications of granular shoulders and granular material shall conform to the requirements specified in 5.11 of the relevant manual.

(vi)   Lateral and vertical clearances at underpasses

(a) 	Lateral and vertical clearances at underpasses and provision of guardrails/crash barriers shall be as per paragraph 2.10 of the Manual.

(b) 	Lateral & Vertical clearance: The width of the opening and vertical clearances at underpasses shall be as follows:

| S. No. | Design Chainage(km) | Clear span/opening(m) | Overall Width (m) | Vertical Clearance (m) | Remarks |
| --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |

(vii)	Lateral and vertical clearances at overpasses

(a)	Lateral and vertical clearances at overpasses shall be as per paragraph 2.11 of the Manual.

(b)	Lateral &Vertical clearances at overpasses shall be as follows:

| S. No. | Design Chainage | Clear Span (m) | Overall Width (m) | Vertical Clearance (m) | Remarks |
| --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |

(viii)	Slip Roads/Service Roads

Slip roads shall be constructed at the locations and for the lengths indicated below:

| Sr. No. | Ch. From | Ch. To | Width (m) | Length (km) | Total Length (km) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |  |

(x)	Cattle and pedestrian under pass / over pass

Cattle and pedestrian underpass/ overpass shall be constructed as follows:

| Sl. No. | Location (km) | Type of crossing |
| --- | --- | --- |
| Nil |  |  |

(xi)Typical cross-sections of the Project Highway

The schedule of typical cross-sections is given in the table below. Drawings of typical cross-sections are given in Appendix B-I.

| S. No. | Design Chainage (From) | Design Chainage (To) | Length (Km) | Reference TCS | Type of construction |
| --- | --- | --- | --- | --- | --- |
| 1 | 5.900 | 7.575 | 1.675 | TCS-1 | As per TCS Drawing |
| 2 | 32.275 | 33.400 | 1.125 | TCS-1I |  |

3	Intersections and Grade Separators

All intersections and grade separators shall be as per section 3 of the Manual. Existing intersections which are deficient shall be improved to the prescribed standards.

Meticulously designed intersections shall be provided at the locations and of the types and features given in the table below:

(I)	At grade Intersections

All intersections as per the site requirement shall be designed and constructed in accordance with the manual. A list of intersections is given in the table below. Draft layout of major junctions is given in indicative Plan & Profile drawings for reference.

Major Junctions- Nos.

| S. No | Existing Chainage (km) | Direction | Type | Sides | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  | NIL |  |  |  |

Minor Junctions- Nos.

| S. No | Existing Chainage (km) | Direction | Type | Sides | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 |  | NIL |  |  |  | .200 | TCS-01 | 7.00m carriageway (either side) + 2.5m Hard shoulder (bth side of cairage way |

Cross Road Improvement-  Nos.

| Sl. No | Design Chainage | Category of crossroad | Type of Junction | Side | Road Leading to | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | NIL |  |  |  |  |  |

Note:	All other junctions, if any, identified during the execution of the work shall be developed as per the extent guidelines and shall not be treated as change in scope of work.

At locations of geometric improvement, the connectivity of built-ups area, along existing road, with the proposed highway shall be provided. All such locations shall be finalized as per site requirement in consultation with the Authority Engineer and it will not be treated as change in scope of work.

4	Road Embankment and Cut Section

(i) 	Reconstruction of new road embankment/cuttings shall conform to the Specifications and Standards given in Section 4 of the Manual and the specified cross-sectional details. Deficiencies in the plan and profile of the existing road shall be corrected.

(ii) 	Raising of the existing road

The existing road shall be raised as per design requirements in accordance with the manual in conformity to the minimum FRL.

Wherever required, toe wall/retaining wall/Breast Wall/other protection works along with drainage system shall be provided to contain the toe of the earthwork, so that all the features shown in the TCS are accommodated in the ROW provided.

| S. No. | Design Chainage (From) | Design Chainage (To) | Length (Km) | Reference TCS |
| --- | --- | --- | --- | --- |
| 1 | 5.90 | 7.575 | 1.675 | TCS-I |
| 2 | 32.275 | 33.400 | 1.125 | TCSII |

(iii) 	Cutting of the existing road

The existing road shall be cut upto the bottom of subgrade level in the following sections:

| S. No. | Design Chainage (From) | Design Chainage (To) | Length (Km) | Reference TCS |
| --- | --- | --- | --- | --- |
| 1 | 5.90 | 7.575 | 1.675 | As per required |
| 2 | 32.275 | 33.400 | 1.125 |  |

(iv) 	All surplus cutting soils shall be transported and be disposed of to the Spoil Banks in accordance with the Cl 3.1 of Schedule D. The locations of these spoil banks should be identified by the EPC contractor in consultation with the Authority Engineer and Competent Authority.

5	Pavement Design

- Pavement design shall be carried out in accordance with Section 5 of the Manual.

- Type of pavement

Flexible pavement shall be provided for the entire length of the project highway.

- Design requirements - as per paragraph 5.4, 5.9 and 5.11 of the manuals.

(a)	Design Period and strategy

Flexible pavement shall be designed for a minimum design period of 20 years. Stage construction shall not be permitted.                                                                         (b)	Design Traffic

Notwithstanding anything to the contrary contained in this Agreement or the Manual, the Contractor shall design the pavement for design traffic of minimum 30 MSA or as per actual traffic survey, whichever is higher. The entire road section proposed for development including paved shoulders shall be constructed after scarifying /dismantling the existing pavement and reconstructing with minimum crust given in table below.

For reconstruction

| S.No. | Description | Minimum Crust Composition of Flexible Pavement |
| --- | --- | --- |
| 1 | BC | 40 mm |
| 2 | DBM | 75 mm |
| 3 | WMM | 250 mm |
| 4 | GSB | 300 mm |
| 5 | Subgrade | 500 mm |

(iv)	Reconstruction of Stretches

The entire stretch of the existing road shall be reconstructed.

- Road Side Drainage

Drainage system including surface and subsurface drains for the Project Highway shall be provided as per Section 6 of the Manual. RCC Covered Drain will be shall be provided in the following stretches

| Sl. No | Design Chainages |  | Length (m) | Side | Total Length (m) | Drain Dimension (m) | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | From (Km.) | To (Km.) |  |  |  |  |  |
| 1 | NIL |  |  |  |  |  |  |

Note: Above length of the Footpath cum RCC Covered Drain is indicative and minimum specified. The actual length of the Footpath cum RCC Covered Drain shall be determined by the Contractor in accordance with the Manual requirements with approval from the Authority's Engineer. Any increase in the length specified in this Clause of Schedule B shall not constitute a Change of Scope.

7	Designs of Structures

(i)	General

(a)	All bridges, culvert sand other structures shall be designed and constructed in accordance with section 7 of the Manual and shall conform the cross-sectional features and other details specified therein.

(d)	All bridges shall be high level bridges.

(e) 	The structures shall be designed to carry utility services like electric cable, water pipeline, OFC etc. as per the requirement of site.

(f)	Cross-section of the new culverts and bridges at deck level shall conform to the typical cross-sections given in section 7 of the Manual.

(g)	IRC Class Special Vehicle loading shall be considered in the structural design of bridges/Flyover/VUP.

(ii)	Culverts

- Overall width of all culverts shall be equal to the roadway width of the approaches.

(b)	New / Reconstruction of culverts:

Culverts shall be provided at the following locations:

| Sr. No. | Design Chainage (km) | Proposed Type of Culvert | Proposed culvert =no x (length x width )(m) | Proposed Overall Width (m) | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | 6.525 | Box culvert | 1NO 6X6 | 24.00 | Reconstruction |
| 2 | 6.650 | Box culvert | 2NO 3X3 | 24.00 | Reconstruction |
| 3 | 6.775 | Box culvert | 2NO 3X3 | 24.00 | Reconstruction |
| 4 | 7.325 | Box culvert | 2NO 3X3 | 24.00 | Reconstruction |
| 5 | 32.375 | Box culvert | 1NO 3X3 | 12.00 | Reconstruction |
| 6 | 32.725 | Box culvert | 1NO 6X6 | 24.00 | Reconstruction |
| 7 | 32.850 | Box culvert | 2NO 3X3 | 24.00 | Reconstruction |

Note:

- The proposed locations are Minimum. Any change in number/length/span/height shall not be treated as change in scope of work.

- The culvert location planned as Table above shall be adjusted accordingly to the exact location of cross-water stream or existing culvert located based on the topographic survey performed by the Contractor for the final drawings of the Detailed Design.

- Cross road culvert to be provided at the location of Major Junction/ Minor Junctions for proper drainage facilities and utility purposes etc. as per manual and any change in number shall not be treated as change of scope.

(c)	Widening of existing culverts

All existing culverts which are not to be reconstructed shall be widened to the roadway width of the Project Highway as per the typical cross section given in section 7 of the Manual. Repairs and strengthening of existing structures where required shall be carried out.

| Sl. No. | Culvert location | Type, span height and width of existing culvert(m) | Repairs to be carried out |
| --- | --- | --- | --- |
| Nil |  |  |  |

(d)	Additional new culverts shall be constructed as per particulars given in the table below:

| Sl. No. | Design Chainage | Type | Span (m) | Minimum Vent Height (m) |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

(e)	Repairs/replacements of railing/parapets, flooring and protection works of the existing culverts shall be undertaken as follows:

| S. no. | Location | Type of repair required |
| --- | --- | --- |
| Nil |  |  |

(f)	Floor protection works shall be as specified in the relevant IRC Codes and Specifications.

(iii)	Bridges

(a)	Existing bridges to be re-constructed/widened

- The existing bridges at the following locations shall be re-constructed:

| Sl. No. | Bridge location (Ch) | Existing Span Arrangement (m) | Existing Width (m) | Proposed Span Arrangement (m) | Proposed Width (m) | Remarks |
| --- | --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |  |

- The following narrow bridges shall be widened:

| Sl. No. | Design Chainage | Existing Chainage | Span Arrangement | Existing width (m) | Proposed Total Width (m) | Cross-section at deck level for widening |
| --- | --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |  |

(b)	New bridges

Major Bridges: -

| S.No | Design Chainage | Name of Nallah /River | Span arrangement (m) | Total Width of Structure (m) |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

Viaducts: -

| Sl. No | Design Chainage | Name of Nallah/River | Span arrangement (m) | Total Width of Structure (m) |
| --- | --- | --- | --- | --- |
| Nil |  |  |  |  |

Minor Bridges: -

| Sl. No. | Design Chainage (km) | Type of Structure | Proposed Span Arrangement (m) | Proposed width (m) | Remarks |
| --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |

Note: Proposed span arrangement is Minimum and any increase in length/span/height shall not be treated as change in scope of work.

IRC Class Special Vehicle loading shall be considered in the structural design of bridges/Flyover/VUP.

(c)	The railings of existing bridges shall be replaced by crash barriers at the following locations:

| Sl.No. | Location at Chainage | Remarks |
| --- | --- | --- |
| NIL |  |  |

(d)	Repairs/replacements of railing/parapets of the existing bridges shall be undertaken as follows:

The existing bridges and structures to be repaired/ strengthened, the nature and extent of repairs /strengthening required are given below;

The following bridges shall be retained with repairs:

| S. No. | Existing Chainage | Design Chainage | Existing Span Arrangement (m) | Existing Width (m) | Remarks |
| --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |

(e)	Drainage system for bridge decks

An effective drainage system for bridge decks shall be provided as specified in the Manual.

(iv) Rail-road bridges

(a)	Design, construction and detailing of ROB shall be as specified in section 7 of the Manual.

(b)	Road over-bridges

Road over-bridges (road over rail) shall be provided at the following locations:

| Sl. No. | Design Chainage (km) | Route | Span arrangement (m) | Total Length (m) | Width (m) |
| --- | --- | --- | --- | --- | --- |
| Nil |  |  |  |  |  |

(c)	Road under-bridges

Road under-bridges (road under railway line) shall be provided at the following level crossings, as per GAD drawings attached:

| Sl.No. | Location of Level crossing (Ch) | Number and length of span(m) |
| --- | --- | --- |
| NIL |  |  |

(v)	Grade separated structures

The grade separated structures shall be provided at the locations and of the type and length specified in paragraphs 2 (vi), 2 (vii) and 2 (ix) of this Annex-I.

(vi)	Repairs and strengthening of bridges and structures

The existing bridges and structures to be repaired/strengthened, and the nature and extent of repairs /strengthening required are given below:

Bridges

| Sl.No. | Location | Nature and extent of repairs to be carried out |
| --- | --- | --- |
| Nil |  |  |

ROB / RUB

| Sl.No. | Location of ROB/RUB(Ch) | Nature and extent of repairs /strengthening to be carried out |
| --- | --- | --- |
| NIL |  |  |

Overpasses/Underpasses and other structures

| Sl.No. | Location of Structure (Ch) | Nature and extent of repairs/strengthening to be carried out |
| --- | --- | --- |
| NIL |  |  |

(v)	Slope Protection Structures

Structures for Slope protection and Retaining/ Breast Walls shall be designed and constructed as stipulated in Schedule-D.

Structures to be constructed for slope protection shown in the following Table:

- Toe wall

| From | From (Ch.) | To (Ch.) | TOTAL |  |
| --- | --- | --- | --- | --- |
| From | 5.9 | 7.575 | 1655M | BOTH SIDE OF ROAD |
| From | 32.275 | 33.400 | 1109M | BOTH SIDE OF ROAD |

- STONE& BOULDER PITCHING

| From | From (Ch.) | To (Ch.) | TOTAL |  |
| --- | --- | --- | --- | --- |
| From | 5.9 | 7.575 | 1655M | BOTH SIDE OF ROAD |
| From | 32.275 | 33.400 | 1109M | BOTH SIDE OF ROAD |

(ix)	Disposal of Debris: - As per Manual.

Note;- "Minimum 25%of total concrete volume other than the foundations & sub-structures of Bridges/ Viaduct/RoB for new construction, reconstruction and widening shall be mandatorily factory manufactured pre-cast concrete elements, if such factory is there within 100 km distance from any point on the project. Any relaxation to the use of factory manufactured pre-cast concrete elements may be granted by Authority only if the contractor/ concessionaire is able to demonstrate that the manufacturer(s) is not able to provide such products matching to the works programme of the contractor or the prices of such products demanded by the manufacturer for onsite delivery is more than the prices derived for corresponding cast-insitu item at the SoR rates prevailing on 28th day before the Bid Due Date."

8.	Traffic Control Devices and Road Safety Works

(i)	Traffic control devices and road safety devices and road furniture shall be provided in accordance with Section 9 of the Manual.

(a)	Traffic/ Road Signs:

Traffic signs viz roadside signs, overhead signs, kerb mounted signs etc. along the entire Project highway shall be provided in accordance with section 9 of the manual.

(b)	Pavement Marking:

Pavement markings shall cover road marking for the entire Project Highway as per manual.

(c)	Safety Barrier:

Concrete Safety/Median Barriershall be installed all along the project highway on either side of median as per section mentioned in IRC:119-2015 in a minimum length as below. Painting of concrete Crash barrier with synthetic enamel paint in Yellow and Black Strips shall also be done.

| From (km) | To (km) | Length in m (LHS) | From (km) | To (km) | Length in m (RHS) |
| --- | --- | --- | --- | --- | --- |
| NIL |  |  |  |  |  |

Note: The above proposed length is Minimum. Concrete safety barriers along the Project highway shall be provided as per schedule D and any increase in length shall not be treated as change in scope of work. Deduction will be carried out for length not provided due to median cuts/opening.

(ii)	Specifications of the reflecting sheeting

Retro reflective sheeting should be of high intensity grade with encapsulated lens or with micro prismatic retro reflective element in accordance with ASTM Standard D 4956-04 in accordance with Clause 9.2.3 of the Manual.

9.	Road side Furniture

Roadside furniture shall be provided in accordance with the provisions of the Manual. The minimum provisions are as follows:-

| S. No. | Particulars | Location | Minimum Quantities |
| --- | --- | --- | --- |
| 1 | Road Markings | Centre line markings, edge line markings, junction markings, pedestrian crossing markings, Rumble Strips (in Thermoplastic Paint) etc. | 981.59 Sqm |
| 2 | delineator | As per required | 280 no |
| 3 | Cautionary, mandatory and informatory sign | a. 90 cm Equilateral triangle | 3.0 Nos |
|  |  | b.60cm Equilateral triangle | 4.0Nos |
|  |  | c. 60 cm circular | 4.0 Nos |
|  |  | d. 80 cm x 60 cm Rectangular | 6.0 Nos |
|  |  | e. 60 cm x 60 cm square | 6.0 Nos |

- Road studs - Road studs shall be provided for the entire Project highway at median openings, bridges, VUP/Interchange/Flyover structures, approaches of bridges, VUP/Interchange/ Flyover, at curves on shoulder edge line, junctions, slip roads on both sides of edge lines etc. in accordance with the manual.

- LED traffic beacons - Shall be provided on entire project highway in accordance with the manual.

c)	Delineators: Delineators for the entire Project Highway at the locations as suggested in relevant IRC Manual recommended in Schedule D.

d)	Concrete Crash Barrier, Metal Beam Crash Barrier, Separators (MS Railings) – as per manual.

e)	Traffic Safety Devices wherever required.

10.	COMPULSORY AFFORESTATION--NIL

- est control etc.

11.	HAZARDOUS LOCATIONS

The safety measures shall be provided at all hazardous/sinking/land slide locations as per the manual in consultation with the Authority’s Engineer.

| S. No. | Particulars | Location | Minimum Quantities |
| --- | --- | --- | --- |
| 1 | Crash barrier | 5.9 to 7.575 & 32.275 to 33.40 | 5427.60 R/m |

12.	SPECIAL REQUIREMENTS FOR HILL ROADS- NIL

13.	UTILITY DUCT

NIL

14.	CHANGE OF SCOPE

The length of Structures, bridges, culverts, underpasses, flyovers etc. specified hereinabove shall be treated as an approximate assessment. The actual lengths as required based on detailed investigations shall be determined by the Contractor in accordance with the Specifications and Standards. Any variations in the lengths specified in this Schedule-B shall not constitute a Change of Scope, save and except any variations in the length arising out of a Change of Scope expressly undertaken in accordance with the provisions of Article 13.

Appendix B-I

# (Schedule B-1)

    - The shifting of utilities and felling of trees shall be carried out by the Contractor. The details of utilities are as follows:

| Sr. No | Type of Utility | Unit | Quantity | Remark |
| --- | --- | --- | --- | --- |
| A | Electrical Utilities |  | nil |  |
| A1 | Electrical Poles | Nos. |  |  |
| A2 | Electrical cables | Meters |  |  |
| A3 | Transformers | Nos. |  |  |
| B | Water/Sewage pipeline |  |  |  |
| B1 | Sewage | Meters |  |  |
| B2 | Water supply | Meters |  |  |
| B3 | Handpump/Tubewells/Borewells | Nos. |  |  |

Sheet-II (Annexure-I to Schedule-B1)

Utility Shifting

Shifting of obstructing existing utilities indicated in Schedule A to an appropriate location in accordance with the standards and specifications of concerned Utility Owning Department is part of the scope of work of the Contractor/Concessionaire*. The bidders may visit the site and assess the quantum of shifting of utilities for the projects before submission of their bid. Copy of utility relocation plan is enclosed. The specifications of concerned Utility Owning Department shall be applicable and followed.

Notes:

- The type/ spacing/ size/ specifications of poles/ towers/ lines/ cables to be used in shifting work shall be as per the guidelines of utility owning department and it is to be agreed solely between the Contractor/Concessionaire“ and the utility owning department. No change of scope shall be admissible and no cost shall be paid for using different type/ spacing/ size/ specifications in shifted work in comparison to those in the existing work or for making any overhead crossings to underground as per requirement of utility owning department and/or construction of project highway. The Contractor/Concessionaire” shall carry out joint inspection with utility owning department and get the estimates from the utility owning department. The assistance of the Authority is limited to giving forwarding letter on the proposal of Contractor/Concessionaire* to utility owning department whenever asked by the Contractor/Concessionaire“. The decision/ approval of utility owning department shall be binding on the Contractor/Concessionaire“.

- The supervision charges at the rates/ charges applicable of the utility owning department shall be paid directly by the Authority for the Utility Owning department as and when Contractor/Concessionaire” furnishes demand of Utility Owning Department along with a copy of estimated cost given by the later.

- The dismantled material/scrap of existing Utility to be shifted/ dismantled shall belong to the Contractor/ Concessionaire* who would be free to dispose-off the dismantled material as deemed fit by them unless the Contractor/Concessionaire“ is required to deposit the dismantled material to utility owning department as per the norm and practice and in that case the amount of credit for dismantled material may be availed by the Contractor/Concessionaire” as per estimate agreed between them.

- The utilities shall be handed over after shifting work is completed to Utility Owning Department to their entire satisfaction. The maintenance liability shall rest with the Utility Owning Department after handing over process is complete as far as utility shifting works are concerned.

Note -II 	Copy of utility shifting plans enclosed as Annexure-II to Schedule B1.

*Strike out which is not applicable.

Schedule-C

SCHEDULE – C

(See Clause 2.1)

Project Facilities

1	Project Facilities

The Contractor shall construct the Project Facilities in accordance with the provisions of this agreement. The Project Facilities shall include:

(a)	Toll plazas;

(b)	Roadside furniture;

(c)	Pedestrian facilities;

(d)	LandScaping and Tree Plantation;

(e)	Truck lay-byes;

(f)	Way-side amenities;

(g)	Bus-bays and Passenger shelters;

(h)	Others;

2	Description of Project Facilities

(a)	Toll Plazas

Toll Plaza shall be provided as per as stipulated in section 10 of the Manual. Canopy of Toll Plaza should be designed to withstand load of solar panels in addition to other design loads. Location of toll plaza is as per the following details.

| Sl. No. | Toll Plaza ID | Design Chainage | Side | Min Number of Lanes |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

- Roadside furniture; As per clause 9 of Annex-I Schedule B

(c)	Pedestrian facilities;

Pedestrian Crossings: Provide pedestrian crossing facilities on locations as recommended in Schedule D.

(d)	Land Scaping and Tree Plantation; -   nil

(e)	Truck lay-byes

Truck Lay bye shall be provided at the following locations in accordance with section 12.5 of the manual at 2 locations.

| Sl.No. | Design Chainage (km) | Side | Nearest Village/Remark |
| --- | --- | --- | --- |
| NIL |  |  |  |

(f)	Way-side Amenities

As stipulated in section 12.10 of the manual, Way-side Amenities shall be provided at the following locations:

| S. No. | Design Chainage | Side |
| --- | --- | --- |
| NIL |  |  |

(g)	Bus bays with Bus- shelters

Bus Shelter shall be provided along the project highway. Tentative locations for Bus shelters are indicated below; however, the same shall be finalized as per suitability of location and site requirement in consultation with the Authority’s Engineer/ Authority. As stipulated in section 12.6 of the Manual, Bus- shelters shall be provided at below indicative locations.

| S. No. | Design Chainage | Side |
| --- | --- | --- |
| NIL |  |  |

(h)	Others

1. 	Highway Patrol unit – Nil

2.	Highway LED Lighting: Nil

3.	Emergency Medical Services: Nil

4.	Cranes services: Nil

5.	Communication System: Nil

6.	Advance Traffic Management System (ATMS): Nil

7.	Operation and Maintenance Centre: Nil

Schedule-D

SCHEDULE - D

(See Clause 2.1)

SPECIFICATIONSANDSTANDARDS

1	Construction

The Contractor shall comply with the Specifications and Standards set forth in Annex-I of this Schedule-D for construction of the Project Highway.

2	Design Standards

The Project Highway including Project Facilities shall conform to design requirements set out in the following documents:

- Manual of Specifications and Standards for Two Laning of Highways (Second Revision) (IRC:112  SP: 73-2018), referred to herein as the Manual.

- MoRTH Specifications for Road and Bridge Works (5th Revision) 1st July2022

- All relevant IRC codes and Manual with upto date amendments.

- IRC: SP112-2017,Manual for the quality control in road and bridges and culverts.

- IRC:SP 13-2022, Guidelines for the design of amall bridges and  culverts.

- IS 15883(PART 1,2,3,4,5,6,8&9,Construction  project managrment-Guidelines

Annex - I

(Schedule-D)Specifications and Standards for Construction                                                   1	Specifications and Standards

All Materials, works and construction operations shall conform to the Guidelines for the Manual of Specifications and Standards for two Laning of Highways (Second Revision) (IRC: SP: 73-2018), referred to as the Manual and Indian Road Congress (IRC) Codes and Standards and MORTH Specifications for Road and Bridge Works.

Where the aforesaid Manuals, guidelines, codes, standards and specifications are silent on any aspect, Good Industry Practice shall be adapted to the satisfaction of the Authority’s Engineer.

2	Deviations from the Specifications and Standards

2.1	The terms “Concessionaire”, “Independent Engineer” and “Concession Agreement” used in the Manual shall be deemed to be substituted by the terms “Contractor”, “Authority’s Engineer” and “Agreement” respectively.

2.2	Notwithstanding anything to the contrary contained in the aforesaid Manual, the following Specifications and Standards shall apply to the Project Highway, and for purposes of this Agreement, the aforesaid Manual shall be deemed to be amended to the extent set forth below;

1)	"Design, fabrication/ casting and launching/installation of factory manufactured. pre-cast concrete elements will be done as per relevant IRC/BIS standards/guidelines/codes duly considering expected handling/lifting stresses. Any international guidelines such as ASHTO, FHWA (Accelerated Bridge Construction. Guidelines), Japan ft Euro codes, may be followed in case of any gaps in IRC/BIS standards/ guidelines/ codes. The pre-cast factory shall have minimum facility of fully automatic RMC plant, arrangement for steam curing, mechanical handling of concrete and pre-cast components, bar bending machines, stacking yard, in-house design team and NABL accredited quality control laboratory, RO plant for water purification, etc. The precast factory shall be certified by Quality Council of India if it is so mandated by MoRTH."

2)	TCS of Highway

| Sl. No. | Item | Clause Referred in Manual | Provision as per Manual | Modified Provision |
| --- | --- | --- | --- | --- |
| 1 | Typical Cross Section | IRC SP 73 2018 clause- 2.17 | Fig: -2.4 | As per Schedule B Typical Cross Sections TCS-01$II shows 7.00m carriageway + 2.5m Granular shoulder on either side of the carriageway. |

3)	Implementation of MoRTH issued Policy Circulars

| Sr. No. | Policy Circular no. | Dated | Subject |
| --- | --- | --- | --- |
| 1 | Efile No. RW/NH- 33044/55/2021-S&R (P&B)pt./Hill Slope Monitoring (Computer No.219394) | 28th November 2024 | Expert Committee Report on Cost Effective Long-term Remedial Measures for Landslide Prone Areas in Hilly Regions. |
| 2 | Efile No. RW/NH- 33044/27/2024/S&R(P&B) (Computer No. 243038) | 23rd September 2024 | Policy Guidelines on use of Inert Material in construction of National Highways. |
| 3 | Efile No. RW/NH- 34066/09/2017/S&R(B) (Computer No. 185417) | 12th February 2021 | Reinforcing Steel Bars (Clause 1000.9.3.1 of Ministry's Specifications for Road and Bridge Works). |
| 4 | Efile No. RW/NH- 34066/09/2017/S&R(B) (Computer No. 185417) | 22nd January 2021 | Use of Stainless Steel Reinforcing Steel Bars in Bridges on National Highways and other centrally sponsored projects to be constructed in marine Environment Susceptible to Severe Corrosion. |
| 5 | EFile No.RW/NH- 34049/01 /2020-SaR (P&B)pt (Computer No.-207229) | 20th September 2024 | Use of New/ Alternative Material and Technology in Construction and Maintenance of National Highways Projects and adoption of Value Engineering Practices therein. |
| 6 | Efile No. RW/NH- 35083/02/2024-S&R (Computer No. 238879) | 26th November 2024 | Use of Waste Plastic in Bituminous Concrete Wearing Course Mix in National Highways Construction Et Maintenance Works. |
| 7 | EFile No.RW/NH- 35072/05/2018-SER (P&B) (Computer No.165688) | 19th April, 2024 | Recommended Bitumen Type & Grade for Different Climate & Traffic Loading for National Highway and Expressway Works in India. |
| 8 | EFile No.RW/NH- 35072/05/2018-S&R (P&B) (El 65688) | 23rd August,2023 | Use of Bitumen: Demand-Supply, Type & Grade, Specifications, Source of Procurement and Quality in Construction of National Highways Projects. |
| 9 | EFile No.RW/NH- 36098/25/2022-S&R (P&B)/ pt. | 16 March, 2023 | Safety in Road Construction Zones in National Highway Projects - effective and adequate measures to be taken. |
| 10 | EFile No: RW/NH- 33044/10/2021- S&R(P&B)(171909) | 15th March,2023 | Reuse of materials reclaimed from existing pavement layers. |
| 11 | Efile No. RW/NH- 36098/17/2022/SER(B) | 2nd January, 2023 | Provisions of crash barriers in existing bridges. |
| 12 | EFile No.RW/NH- 33049/01/2020-SER (B) Pt. | 22nd February,2022 | Use of Ultra High Performance Fiber Reinforced Concrete (UHPFRC) in Design a Construction of Structures/ Bridges of National Highways. |
| 13 | Efile No. RW/NH- 33044/04/2022- SER(PEB) | 15th February, 2022 | Use of dynamite on hills/mountains for the construction of roads. |
| 14 | Efile No.RW/NH-34066/01/2020-QCZ | 1stOcttober,2020 | Guidelines & Standard operating procedure for quality control/assurance in construction of National Highways & other centrally sponsored projects |

Schedule – E

(See Clause 2.1 and 14.2)

MAINTENANCE REQUIREMENTS

1.	Maintenance Requirements

  - The Contractor shall, at all-time maintain the Project Highway in accordance with the provisions of this Agreement, Applicable Laws and Applicable Permits.

  - The Contractor shall repair or rectify any Defect or deficiency set forth in Paragraph 2 of this Schedule-E within the time limit specified therein and any failure in this behalf shall constitute non-fulfillment of the Maintenance obligations by the Contractor.  Upon occurrence of any breach hereunder, the Authority shall be entitled to effect reduction in monthly lump sum payment as set forth in Clause 14.6 of this Agreement, without prejudice to the rights of the Authority under this Agreement, including Termination thereof.

  - All Materials, works and construction operations shall conform to the “SPECIFICATIONS FOR ROAD AND BRIDGE WORKS (FIFTH REVISION, April 2013)”, including latest corrections slips, issued by   the Ministry of Surface Transport & Highways, Government of India and published by the Indian Roads Congress.

Where the specifications for a work are not given, Good Industry Practice shall be adopted to the satisfaction of the Authority’s Engineer.

2.	Repair/rectification of Defects and deficiencies

The obligations of the Contractor in respect of Maintenance Requirements shall include repair and rectification of the Defects and deficiencies specified in Annex-I of this Schedule-E within the time limit set forth therein.

3.	Other Defects and deficiencies

In respect of any Defect or deficiency not specified in Annex-I of this Schedule-E, the Authority’s Engineer may, in conformity with Good Industry Practice, specify the permissible limit of deviation or deterioration with reference to the Specifications and Standards, and any deviation or deterioration beyond the permissible limit shall be repaired or rectified by the Contractor within the time limit specified by the Authority’s Engineer.

4.	Extension of time limit

Notwithstanding anything to the contrary specified in this Schedule-E, if the nature and extent of any Defect or deficiency justifies more time for its repair or rectification than the time specified herein, the Contractor shall be entitled to additional time in conformity with Good Industry Practice.  Such additional time shall be determined by the Authority’s Engineer and conveyed to the Contractor and the Authority with reasons thereof;

5.	Emergency repairs/restoration

Notwithstanding anything to the contrary contained in this Schedule-E, if any Defect, deficiency or deterioration in the Project Highway poses a hazard to safety or risk of damage to property, the Contractor shall promptly take all reasonable measures for eliminating or minimizing such danger.

6.	Daily inspection by the Contractor

The Contractor shall, through its engineer, undertake a daily visual inspection of the Project Highway and maintain a record thereof in a register to be kept in such form and manner as the Authority’s Engineer may specify.  Such record shall be kept in safe custody of the Contractor and shall be open to inspection by the Authority and the Authority’s Engineer at any time during office hours.

7.	Pre-monsoon inspection / post-monsoon inspection

The Contractor shall carry out a detailed pre-monsoon inspection of all bridges, culverts and drainage system before [1st June] every year in accordance with the guidelines contained in IRC: SP:35.  Report of this inspection together with details of proposed maintenance works as required on the basis of this inspection shall be sent to the Authority’s Engineer before the [10th June] every year.  The Contractor shall complete the required repairs before the onset of the monsoon and send to the Authority’s Engineer a compliance report.  Post monsoon inspection shall be done by the [30th September] and the inspection report together with details of any damages observed and proposed action to remedy the same shall be sent to the Authority’s Engineer.

8.	Repairs on account of natural calamities

All damages occurring to the Project Highway on account of torrential rains, floods, earthquake or other natural disasters shall be undertaken by the Contractor at its own cost and/or out of the proceeds of insurance.

Annex – I

(Schedule-E)

Repair/rectification of Defects and deficiencies

The Contractor shall repair and rectify the defects and deficiencies specified in this Annex-I of Schedule-E within the time limit set forth in the table below.

Table -1: Maintenance Criteria for Pavements:

| Asset Type |  | Performance Parameter | Level of Service (LOS) |  |  | Frequency of Inspection | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Desirable | Acceptable |  |  |  |  |  |  |
| Flexible Pavement (Pavement of MCW, Service Road, approaches |  | Potholes | Nil | < 0.1 % of area and subject to limit of 10 mm in depth |  | Daily | Length Measurement Unit like Scale, Tape, odometer etc. | IRC 82: 2015 and Distress Identification Manual for Long Term Pavement Performance Program, FHWA 2003 (http://www.tfhrc.com/pavement/lttp/ reports/03031/) | 24-48 hours | MORT&H Specification 3004.2 |
| S of Grade structure, approaches of connecting roads, slip roads, lay byes etc. as applicable) |  | Cracking | Nil | < 5 % subject to limit of 0.5 sqm for any 50m length |  | Daily |  |  | 7-15days | MORT&H Specification 3004.3 |
|  |  | Rutting | Nil | < 5 mm |  | Daily | Straight Edge |  | 15-30days | MORT&H Specification 3004.2 |
|  |  | Corrugations and Shoving | Nil | < 0.1 % of area |  | Daily | Length Measurement Unit like |  | 2-7days | IRC:82-2015 |
| Asset Type | Performance Parameter |  | Level of Service (LOS) |  | Frequency of Inspection |  | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
|  |  |  | Desirable | Acceptable |  |  |  |  |  |  |
| S of Grade structure, approaches of connecting roads, slip roads, lay byes etc. as applicable) | Bleeding |  | Nil | < 1 % area | Daily |  | Scale, Tape odometer etc. |  | 3-7days | MORT&H Specification 3004.4 |
|  | Ravelling / Stripping |  | Nil | < 1 % area | Daily |  |  |  | 7-15days | IRC:82-2015 read with IRC SP 81 |
|  | Edge Deformation / Breaking |  | Nil | < 1m for any 100m section and width < 0.1m at any location, restricted to 30cm from the edge | Daily |  |  |  | 7-15days | IRC:82-2015 |

| Asset Type | Performance Parameter |  | Level of Service (LOS) |  | Frequency of Inspection |  | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Desirable | Acceptable |  |  |  |  |  |  |
|  | Roughness |  | 2000 mm/km | 2400 mm/km | Bi-Annually |  | Class I Profilometer SCRIM (Sideway force Coefficient Routine Investigation Machine or equipment) | Class I Profilometer: ASTM E950 (98): 2004 – Standard Test Method for measuring Longitudinal Profile of Travelled Surfaces with Accelerometer Established Inertial Profiling Reference ASTM E1656-94:2000- Standard Guide for Classification of Automatic Pavement Condition Survey Equipment | 180days | IRC:82-2015 |
|  | Skid Number |  | 60SN | 50SN | Bi-Annually |  |  |  | 180 days | BS: 7941-1: 2006 |
|  | Pavement Condition Index |  | 3 | 2.1 | Bi-Annually |  |  |  | 180 days | IRC:82-2015 |
|  | Other Pavement Distresses |  |  |  | Bi-Annually |  |  |  | 2-7 days | IRC:82-2015 |
|  | Deflection /Remaining Life |  |  |  | Annually |  | Falling W eight Deflector meter | IRC 115:2014 | 180 days | IRC:115-2014 |
| Rigid Pavement (Pavement of MCW, Service Road, Grade structure, | Roughness BI |  | 2200mm/km | 2400mm/km | Bi-Annually |  | Class I Profilometer | ASTME950(98) :2004 and ASTM E1656- 94:2000 | 180 days | IRC:SP:83-2008 |
| Asset Type | Performance Parameter |  | Level of Service (LOS) |  | Frequency of Inspection |  | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
|  |  |  | Desirable | Acceptable |  |  |  |  |  |  |
| Approaches of connecting roads, slip roads, lay byes etc. as applicable) | Skid |  | Skid Resistance no. at different speed of vehicles |  | Bi-Annually |  | SCRIM (Sideway- force | IRC:SP:83-2008 | 180 days | IRC:SP:83-2008 |
|  |  |  | Minimum SN | Traffic Speed (Km/h) |  |  | Coefficient Routine Investigation Machine or equivalent) |  |  |  |
|  |  |  | 36 | 50 |  |  |  |  |  |  |
|  |  |  | 33 | 65 |  |  |  |  |  |  |
|  |  |  | 32 | 80 |  |  |  |  |  |  |
|  |  |  | 31 | 95 |  |  |  |  |  |  |
|  |  |  | 31 | 110 |  |  |  |  |  |  |
| Embankment / Slopes | Edge drop at shoulders |  | Nil | 40mm | Daily |  | Length Measurement Unit like Scale, Tape, odometer etc. | IRC | 7-15 days | MORT&H Specification 408.4 |
|  | Slope of camber/c ross fall |  | Nil | <20% variation in prescribed slope camber / cross fall | Daily |  |  |  | 7-15 days | MORT&H Specification 408.4 |
|  | Embankment Slopes |  | Nil | <15% variation in prescribe | Daily |  |  |  | 7-15 days | MORT&H Specification 408.4 |
| Asset Type |  | Performance Parameter | Level of Service (LOS) |  |  | Frequency of Inspection | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
|  |  |  | Desirable | Acceptable |  |  |  |  |  |  |
|  |  |  |  | Side slope |  |  |  |  |  |  |
|  |  | Embankment Protection | Nil | Nil |  | Daily | NA |  | 7-15days | MORT&H Specification |
|  |  | Rain Cuts/ Gullies in slope | Nil | Nil |  | Daily Specially During Rainy Season | NA |  | 7-15days | MORT&H Specification |

In addition to the above performance criterion, the contractor shall strictly maintain the rigid pavements as per requirements in the following table

Table -2: Maintenance Criteria for Rigid Pavements:

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 |  | For the case d > D/2 |
| CRACKING |  |  |  |  |  |  |  |
| 1 | Single Discrete Cracks Not intersecting with any joint | w= width of crack L= length of crack d= depth of crack D= depth of slab | 0 | Nil, not discernible |  | No Action | Not applicable |
|  |  |  | 1 | w<0.2mm.hair cracks |  |  |  |
|  |  |  | 2 | w= 0.2 -0.5 mm, discernible from slow-moving car |  | Seal without delay | Seal, and stitch if L >1m. Within 7 days |
|  |  |  | 3 | w= 0.5 -1.5 mm, discernible from fast-moving car |  |  |  |
|  |  |  | 4 | w= 1.5-3.0 mm |  | Seal, and stitch if L > 1m. Within 7 days | Staple or Dowel Bar Retrofit, FDR for affected portion. Within 15 days |
|  |  |  | 5 | w > 3 mm |  |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 2 | Single Transverse (or Diagonal) Crack intersecting with one or more joints | w= width of crack L= length of crack d= depth of crack D= depth of slab | 0 | Nil, not discernible | No Action |  |
|  |  |  | 1 | w<0.2mm.hair cracks | Route and seal with epoxy Within 7 days | Staple or Dowel Bar Retrofit. Within 15 days |
|  |  |  | 2 | w= 0.2 -0.5 mm, discernible from slow-moving car |  |  |
|  |  |  | 3 | w= 0.5 - 3.0 mm, discernible from fast-moving car | Route and seal and stitch, if L >1m. Within 7 days |  |
|  |  |  | 4 | w= 3.0 - 6.0 mm | Dowel Bar Retrofit. Within 15 days | Full Depth Repair Dismantle and reconstruct affected. Portion with norms and specifications – See Para 5.5 &9.2 Within 15 days |
|  |  |  | 5 | w > 6 mm, usually associated with spalling, and/or slab rocking under traffic | Not Applicable, as it may be full depth |  |
| 3 | Single Longitudinal Crack intersecting with one or more joints | w= width of crack L= length of crack d= depth of crack D= depth of slab | 0 | Nil, Not discernible | No, Action |  |
|  |  |  | 1 | w= 0.5 mm, discernible from slow-moving vehicle | Seal with epoxy, if L > 1m. Within 7 days | Staple or Dowel Bar Retrofit. Within 15 days |
|  |  |  | 2 | w= 0.5 - 3.0 mm, discernible from fast vehicle | Route seal and stitch, if L > 1m. Within 15 days | - |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  | 3 | w= 3.0 - 6.0 mm | Staple, if L> 1m. Within 15 days | Partial Depth Repair with stapling. Within15 days |
|  |  |  | 4 | w= 6.0 - 12.0 mm, usually associated with spalling | Not Applicable, as it may be full depth |  |
|  |  |  | 5 | w > 12 mm, usually associated with spalling, and/or slab rocking under traffic |  | Full depth Repair Dismantle and reconstruct affected portion as per norms and specifications See Para 5.6.4 Within 15 days |
| 4 | Multiple Crack intersecting with one or more joints | w= width of crack | 0 | Nil, Not discernible | No, Action | - |
|  |  |  | 1 | w < 0.2 mm, hair cracks | Seal and stitch if L > 1m. Within 15 days |  |
|  |  |  | 2 | w= 0.2 - 0.5 mm, discernible from slow vehicle |  |  |
|  |  |  | 3 | w= 0.5 - 3.0 mm, discernible from fast vehicle | Full depth repair within 15 days | Dismantle, Reinstate subbase, Reconstruct whole slab as per specifications within 30 days |
|  |  |  | 4 | w= 3.0 - 6.0 mm panel broken into 2 or 3 pieces |  |  |
|  |  |  | 5 | w > 6 mm and /or panel broken into more than 4 pieces |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 5 | Corner Break | w= width of crack L= length of crack | 0 | Nil, not discernible | No Action | - |
|  |  |  | 1 | w < 0.5mm, only 1 corner broken | Seal with low viscosity epoxy to secure broken parts Within 7 days | Seal with epoxy seal with epoxy Within 7 days |
|  |  |  | 2 | w < 1.5mm, L< 0.6m, only one corner broken |  |  |
|  |  |  | 3 | w < 1.5mm, L < 0.6m, two corners broken | Partial Depth (Refer Figure 8.3 of IRC:83-2008) Within 15 days | Full depth repair |
|  |  |  | 4 | w > 1.5mm, L > 0.6m or three corners broken |  |  |
|  |  |  | 5 | Three or four corners broken |  | Reinstate sub-base and reconstruct the slab as per norms and specifications Within 30 days |
| 6 | Punch-out (Applicable to Continuous Reinforced Concrete Pavement (CRCP) only) | w= width of crack L= length (m/m2) | 0 | Nil, Not discernible |  | No, Action |
|  |  |  | 1 | w < 0.5 mm, L< 3m / m2 | Not Applicable, as it may be full depth | Seal with low viscosity epoxy to secure broken parts. |
|  |  |  | 2 | either w > 0.5 mm or L < 3m /m2 |  |  |
|  |  |  | 3 | w > 1.5mm and L < 3m /m2 |  |  |
|  |  |  | 4 | w > 3mm, L < 3m /m2and deformation |  | Full depth repair Cutout and replace damaged area taking care not to damage reinforcement. Within 30 days |
|  |  |  | 5 | w > 3mm, L < 3m /m2and deformation |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Surface Defects |  |  |  |  |  |  |
| 7 | Raveling or Honeycomb type surface | r= area damaged surface / total surface of slab (%) h = maximum depth of damage | 0 | Nil, not discernible | Short Term | Long Term |
|  |  |  |  |  | No action. | Not Applicable |
|  |  |  | 1 | r < 2 % | Local repair of area damaged and liable to be damaged. Within 15 days |  |
|  |  |  | 2 | r = 2 - 10 % |  |  |
|  |  |  | 3 | r = 10 - 25 % | Bonded Inlay, 2 or 3 slabs if affecting. Within 30 days |  |
|  |  |  | 4 | r = 25 - 50 % |  |  |
|  |  |  | 5 | r > 50% and h > 25mm | Reconstruct slabs, 4 or more slabs if affecting. Within 30 days |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Surface Defects |  |  |  |  |  |  |
| 8 | Scaling | r= damaged surface / total surface of slab (%) h = maximum depth of damage | 0 | Nil, not discernible | Short Term | Long Term |
|  |  |  |  |  | No action. | Not Applicable |
|  |  |  | 1 | r < 2 % | Local repair of area damaged and liable to be damaged. Within 7 days |  |
|  |  |  | 2 | r = 2 - 10 % |  |  |
|  |  |  | 3 | r = 10 - 20 % | Bonded Inlay Within 15 days |  |
|  |  |  | 4 | r = 20 - 30 % |  |  |
|  |  |  | 5 | r > 30% and h > 25mm | Reconstruct slabs Within 30 days |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 9 | Polished Surface /Glazing | t = texture depth, sand patch test | 0 |  | No action. | Not Applicable |
|  |  |  | 1 | t >1 mm |  |  |
|  |  |  | 2 | t = 1 - 0.6 mm | Monitor rate of deterioration Diamond Grinding if affecting 50% or more slabs in a continuous stretch of minimum 5 km. Within 30 days |  |
|  |  |  | 3 | t = 0.6 - 0.3 mm |  |  |
|  |  |  | 4 | t = 0.3 - 0.1 mm |  |  |
|  |  |  | 5 | t <0.1 mm |  |  |
| 10 | Pop out (Small Hole), Pothole Refer Para 8.4 | n = number/m2 d = diameter h = maximum depth | 0 | d < 50 mm; h < 25 mm ; n < 1 per 5 m2 | No action |  |
|  |  |  | 1 | d = 50 – 100 mm; h < 50 mm; n < 1 per 5 m2 | Partial depth repair 65 mm deep. Within 15 days | Not Applicable |
|  |  |  | 2 | d = 50 – 100 mm; h > 50 mm; n < 1 per 5 m2 |  |  |
|  |  |  | 3 | d = 100 – 300 mm; h <100 mm; n < 1 per 5 m2 | Partial depth repair 110 mm i.e. 10mm more that the depth of the hole. Within 30 days |  |
|  |  |  | 4 | d = 10 – 300 mm; h >100 mm; n < 1 per 5 m2 |  |  |
|  |  |  | 5 | d > 300 mm; h > 100 mm ; n > 1 per 5 m2 | Full depth repair. Within 30 days |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Joints Defects |  |  |  |  |  |  |
| 11 | Joint Seal Defects | loss or damage L = Length as % total joint length | 0 | Difficult to discern | Short Term | Long Term |
|  |  |  |  |  | No action | Not Applicable |
|  |  |  | 1 | Discernible, L < 25% but of little immediate consequence with regard to ingress of water or trapping incompressible material. | Clean joint, inspect later. |  |
|  |  |  | 3 | Notable. L > 25%insufficient protection against ingress of water and trapping incompressible material. | Clean and reapply sealant in selected locations. Within 7 days |  |
|  |  |  | 5 | Severe; w > 3 mm negligible protection against ingress of water and trapping incompressible material. | Clean, widen and reseal the joint. Within 7 days |  |
| 12 | Spalling of Joints | w = width on either side of the joint L = length of spalled portion ( as % joint length) | 0 | Nil, not discernible | No action. | Not Applicable |
|  |  |  | 1 | w < 10 mm | Apply low viscosity epoxy resin / mortar in cracked portion. Within 7 days |  |
|  |  |  | 2 | w = 10 - 20 mm, L < 25% |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating |  | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Joints Defects |  |  |  |  |  |  |  |
|  |  |  | 3 | w = 20 – 40 mm, L > 25% | Partial Depth Repair. Within 15 days |  | Not Applicable |
|  |  |  | 4 | w = 40 – 80 mm, L > 25% | 30 – 50 mm deep, h = w + 20 % of w, within 30 days |  |  |
|  |  |  | 5 | w > 80 mm, and L > 25% | 50 – 100 mm deep repair. H = w + 20% of w. Within 30 days |  |  |
| 13 | Faulting (or Stepping) in Cracks or Joints | f = difference of level | 0 | no discernible, < 1 mm | No action. |  | No action |
|  |  |  | 1 | f < 3 mm |  |  |  |
|  |  |  | 2 | f = 3 – 6 mm | Determine cause and observe, take action for diamond grinding |  | Replace the slab as appropriate. Within 30 days |
|  |  |  | 3 | f = 6 – 12 mm | Diamond Grinding |  |  |
|  |  |  | 4 | f = 12 – 18 mm | Raise sunken slab |  | Replace the slab as appropriate. Within 30 days |
|  |  |  | 5 | f > 18 mm | Strengthen sub grade and sub – base by grouting and raising sunken slab |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Joints Defects |  |  |  |  |  |  |
| 14 | Blowup or Buckling | h = vertical displacement from normal profile | 0 | Nil, not discernible | Short Term | Long Term |
|  |  |  |  |  | No action |  |
|  |  |  | 1 | h < 6 mm |  |  |
|  |  |  | 2 | h = 6 – 12 mm | Install Signs to Warn Traffic Within 7 days |  |
|  |  |  | 3 | h = 12 – 25 mm |  |  |
|  |  |  | 4 | h > 25 mm | Full Depth Repair. Within 30 days |  |
|  |  |  | 5 | shattered slab, ie 4 or more pieces | Replace broken slabs. Within 30 days |  |
| 15 | Depression | h = negative vertical displacement from normal profile L = length | 0 | No discernible, h < 5 mm | No action. | Not applicable |
|  |  |  | 1 | h = 5 – 15 mm |  |  |
|  |  |  | 2 | h = 15 -30 mm, Nos < 20% joints | Install Signs to Warn Traffic Within 7 days |  |
|  |  |  | 3 | h = 30 – 50 mm |  |  |
|  |  |  | 4 | h > 50 mm or > 20 % joints | Strengthen sub grade. Reinstate pavement at normal level if L < 20 m. Within 30 days |  |
|  |  |  | 5 | h > 100 mm |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Joints Defects |  |  |  |  |  |  |
|  |  |  |  |  | Short Term | Long Term |
| 16 | Heave | h = positive vertical displacement from normal profile. L = length | 0 | No discernible, h < 5 mm | No action |  |
|  |  |  | 1 | h = 5 – 15 mm | Follow up | scrabble |
|  |  |  | 2 | h = 15 – 30 mm, Nos < 20% joints | Install Signs to Warn Traffic Within 7 days |  |
|  |  |  | 3 | h = 30 – 50 mm |  |  |
|  |  |  | 4 | h > 50 mm or > 20% joints | Stabilize sub grade. Reinstate pavement at normal level if length < 20 m. Within 30 days |  |
|  |  |  | 5 | h > 100 mm |  |  |
|  |  |  | 5 | f > 18 mm | Strengthen sub grade and sub – base by grouting and raising sunken slab |  |
| 17 | Bump | h = vertical displacement from normal profile. | 0 | h < 4 mm | No action |  |
|  |  |  | 1 | h = 4 – 7 mm | Grind, in case of new construction Within 7 days | Construction Limit for new Construction |
|  |  |  | 3 | h = 7 – 15 mm | Grind, in case of on going maintenance Within 15 days | Replace in case of new construction. Within 30 days. |
|  |  |  | 5 | h > 15 mm | Full Depth Repair. Within 30 days | Full Depth Repair. Within 30 days |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Joints Defects |  |  |  |  |  |  |
|  |  |  |  |  | Short Term | Long Term |
| 18 | Lane to Shoulder Drop-off | f = difference of level | 0 | Nil, Not discernible, < 3 mm | No action |  |
|  |  |  | 1 | f = 3 – 10 mm | Spot repair of shoulder Within 7 days |  |
|  |  |  | 2 | f = 10 – 25 mm |  |  |
|  |  |  | 3 | f = 25 – 50 mm | Fill up shoulder Within 7 days | For any 100 m stretch Reconstruct shoulder, if affecting 25% or more of stretch. Within 30 days |
|  |  |  | 4 | f = 50 – 75 mm |  |  |
|  |  |  | 5 | f > 75 mm |  |  |
| Drainage |  |  |  |  |  |  |
| 19 | Pumping | quantity of fines and water expelled through open joints and cracks Nos | 0 | no discernible | No Action |  |
|  |  |  | 1 to 2 | slight/ occasional Nos < 10% | Repair cracks and joints without delay. | Inspect and repair sub-drainage at distressed sections and upstream. |
|  |  |  | 3 to 4 | Appreciable/ Frequent 10- 25% | Lift or jack slab within 30 days |  |
|  |  | Nos/100m stretch | 5 | abundant, crack development > 25% | Repair distressed pavement sections. Strengthen sub grade and sub base. Replace slab. Within 30 days |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 20 | Ponding | Ponding on slabs due to blockage of drains | 0-2 | no discernible problem | No Action |  |
|  |  |  | 3 to 4 | Blockage observed in drains, but water flowing | Clean drains etc within 7days follow up | Action required to stop water damaging foundation within 30 days |
|  |  |  | 5 | Ponding, accumulation of water observed | -do- |  |

Table-3: Maintenance Criteria for Safety Related Item sands Other Furniture Items:

| Asset Type | Performance Parameter | Level of Service (LOS) |  |  | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Highway | Availability of Safe Sight Distance | AsperIRCSP: 84-2014,a minimum of safe stopping sight distance shall be available throughout. |  |  | Monthly | Manual Measurement s with Odometer along with video/ image backup | Removal of obstruction within24 hours, in case of sight line affected by temporary objects such a streets, temporary encroachments. In case of permanent structure or design deficiency: Removal of obstruction/improvement of deficiency at the earliest Speed Restriction boards and suitable traffic calming measures such as transverse bar marking, blinkers, etc. shall be applied during the period of rectification. |  | IRC:SP 84-2014 |
|  |  | Design Speed, kmph | Desirable Minimum Sight Distance(m) | Safe Stoppin g Sight Distance (m) |  |  |  |  |  |
|  |  | 100 | 360 | 180 |  |  |  |  |  |
|  |  | 80 | 260 | 130 |  |  |  |  |  |
| Pavement t Marking | Wear | <70% of marking remaining |  |  | Bi- Annually | Visual Assessment as per Annexure-F of IRC:35-2015 | Re -painting | Cat-1 Defect – within 24 hours Cat-2 Defect - within 2months | IRC:35- 2015 |

| Asset Type | Performance Parameter | Level of Service (LOS) |  |  | Frequency of Measurement | Testing Method |  | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Day time Visibility | During expected life Service Time Cement Road- 130mcd/m2/lux Bituminous Road - 100mcd/m2/lux |  |  | Monthly | As per Annexure-D of IRC:35-2015 |  | Re -painting | Cat-1 Defect – within 24 hours Cat-2 Defect – within 2months | IRC:35- 2015 |
|  | Night Time Visibility | Initial and Minimum Performance for Dry Retro electivity during nighttime: |  |  | Bi-Annually | As per Annexure-E of IRC:35-2015 |  | Re -painting | Cat-1 Defect – within 24 hours Cat-2 Defect – within 2months | IRC:35-2015 |
|  |  | Design Speed | (RL) Retro Reflectivity (mcd/m2/lux) |  |  |  |  |  |  |  |
|  |  |  | Initial (7 days) | Minimum Threshold level (TL) &warranty period required up to 2 years |  |  |  |  |  |  |
|  |  | Up to 65 | 200 | 80 |  |  |  |  |  |  |
|  |  | 65 -100 | 250 | 120 |  |  |  |  |  |  |
|  |  | Above 100 | 350 | 150 |  |  |  |  |  |  |
|  |  | Initial and Minimum Performance fortnight Visibility under wet condition (Retroreflectivity): |  |  |  |  |  |  |  |  |
| Asset Type | Performance Parameter | Level of Service (LOS) |  |  | Frequency of Measurement | Testing Method | Recommended Remedial measures |  | Time limit for Rectification | Specification sand Standards |
|  |  | Initial7 days Retro reflectivity: 100 mcd/m2/lux Minimum Threshold Level:50 mcd/m2/lux |  |  |  |  |  |  |  |  |
|  | Skid Resistance | Initial and Minimum performance for Skid Resistance: Initial (7days):55BPN Min. Threshold: 44BPN *Note: shall be considered under urban/city traffic condition encompassing the locations like pedestrian crossings, bus bay, bus stop, cycle track intersection delineation, transverse bar markings etc |  |  | Bi-Annually | As per Annexure-G of IRC:35-2015 |  |  | Within 24 hours | IRC:35-2015 |
| Road Signs | Shape and Position | Shape and Position as per IRC:67- 2012. Signboard should be clearly visible for the design speed of the section. |  |  | Daily | Visual with video/image backup | Improvement of shape, in case if shape is damaged. Relocation as per requirement |  | 48hours incase of Mandatory Signs, Cautionary and Informatory Signs(Single and Dual post signs) 15 Days in case of Gantry/Cantilever r Sign boards | IRC:67-2012 |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Retro reflectivity | As per specification in IRC:67-2012 | Bi-Annually | Testing of each signboard using Retro Reflectivity Measuring Device. In accordance with ASTMD 4956-09. | Change of signboard | 48hours incase of Mandatory Signs, Cautionary and Informatory Signs(Single and Dual post signs) 1Monthincase of Gantry/Cantilever er Sign boards | IRC:67-2012 |
| Kerb | Kerb Height | AsperIRC86:1983dependingupon type of Kerb | Bi-Annually m | Use of distance R easuringtape H | Raising Kerb eight | Within 1 Month | RC 86:1983 |
|  | Kerb Painting | Functionality: Functioning of Kerb painting as intended | Daily | Visual with video/image K backup | Kerb Repainting | Within 7-days | RC 35:2015 |
| Other Road Furniture | Reflective Pavement Markers(Road Studs) | Numbers and Functionality as per specifications in IRC: SP:84-2014 and IRC:35-2015,unless specified in Schedule-B. | Daily | Counting | New Installation | Within 2 months | IRC:SP:84- 2014,IRC:35- 2015 |
|  | Pedestrian Guardrail | Functionality: Functioning of guardrails intended | Daily | Visual with video/image backup | Rectification | Within 15 days | IRC:SP:84- 2014 |
|  | Traffic Safety Barriers | Functionality: Functioning of Safety Barriers as intended | Daily | Visual with video/image backup | Rectification | Within 7 days | IRC:SP:84- 2014, IRC:119- 2015 |
| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
|  | End Treatment of | Functionality: Functioning of End Treatment as intended | Daily | Visual with video/image | Rectification | Within 7 days | IRC:SP:84- 2014, |
|  | Traffic Safety Barriers |  |  | backup |  |  | IRC:119- 2015 |
|  | Attenuators | Functionality: Functioning of Attenuators as intended | Daily | Visual with video/image backup | Rectification | Within 7 days | IRC:SP-2014, IRC:119- 2015 |
|  | Guard Posts and Delineators | Functionality: Functioning of Guard Posts and Delineators as intended | Daily | Visual with video/image backup | Rectification | Within 15 days | IRC: 79 - 1981 |
|  | Overhead Sign Structure | Overhead sign structure shall be structurally adequate | Daily | Visual with video/image backup | Rectification | Within 15 days | IRC:67-2012 |
|  | Traffic Blinkers | Functionality: Functioning of Traffic Blinkers as intended | Daily | Visual with video/image backup | Rectification | Within 7 days | IRC:SP:84- 2014 |
| Highway Lighting System | Highway Lights | Illumination: Minimum40Luxilluminationonthe road surface | Daily | The illumination level shall be measured with luxmeter | Improvement in Lighting System | 24 hours | IRC:SP:84- 2014 |
|  |  | No major failure in the lighting system | Daily | - | Rectification of failure | 24 hours | IRC:SP:84- 2014 |
|  |  | No minor failure in the lighting system | Monthly | - | Rectification of failure | 8 hours | IRC:SP:84- 2014 |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Toll Plaza Canopy Lights | Minimum 40 Lux illumination on the road surface | Daily | The illumination level shall be measured with luxmeter | Improvement in Lighting System | 24 hours | IRC:SP:84- 2014 |
|  |  | No major/minor failure in the lighting system | Daily | - | Rectification failure | 8 hours | IRC:SP:84- 2014 |
| Trees and Plantation n including median plantation n | Obstruction in minimum head-room of 5.5 m above carriageway or obstruction in visibility of road signs | No obstruction due to trees | Monthly | Visual with video/image backup | Removal of trees | Immediate | IRC:SP:84- 2014 |
|  | Deterioration in health of trees and bushes | Health of plantation shall be as per requirement of specifications & instructions issued by Authority from time to time | Daily | Visual with video/image backup | Timely watering and treatment. Or Replacement of Trees and Bushes. | Within 90 days | IRC:SP:84- 2014 |
|  | Vegetation affecting sight line and road structures | Sight line shall be free from obstruction by vegetation | Daily | Visual with video/image backup | Removal of Trees | Immediate | IRC:SP84- 2014 |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Rest Areas | Cleaning of toilets | - | Daily | - | - | Every 4 hours |  |
|  | Defects in electrical, water and sanitary installations | - | Daily | - | Rectification | 24 hours |  |
| Other Project Facilities and Approach roads | Damage or deterioration in Approach Roads, pedestrian facilities, truck lay- bys, bus-bays, bus- shelters, cattle crossings, Traffic Aid Posts, Medical Aid Posts and other works |  | Daily | - | Rectification | 15days | IRC:SP 84-2014 |

Table 4: Maintenance Criteria for Structures and Culverts:

|  | Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Pipe/Box/ slab culverts | Free waterway/ unobstructed d flow section | 85%of culvert normal flow area to available. | 2timesin a year (before and after rainy season) | Inspection by Bridge Engineer as per IRC SP: 35-1990 and recording of depth of silting and area of vegetation. | Cleaning silt up soils and debris in culvert barrel after rainy season, removal of bushes and vegetation, U/s of barrel, under barrel and D/s of barrel before rainy season. | 15 days before onset of monsoon and within 30daysafter End of rainy season. | IRC 5-2015, IRC SP:40-1993 and IRC SP:13- 2004 |
|  |  | Leak-proof expansion joints if any | No leakage through expansion joints | Bi-Annually | Physical inspection of expansion joints as per IRC SP: 35-1990 if any, for leakage strain son walls at joints. | Fixing with sealant suitably | 30 days or before onset of rains whichever comes earlier | IRC SP:40- 1993andIRC SP:69-2011 |
|  |  | Structurally sound | Spalling of concrete not more than 0.25 sqm | Bi-Annually | Detailed inspection of all components of culvert as per IRC SP:35-1990 and recording the defects | Repairs to spalling, cracking, delaminating, rusting shall be followed as per IRC:SP:40-1993 | 15 days | IRC SP:40- 1993and MORTH Specifications clause 2800 |
|  |  |  | Delimitation of concrete not more than 0.25 sq.m. |  |  |  |  |  |
|  |  |  | Cracks wider than 0.3 mm not more than 1maggregate length |  |  |  |  |  |
| Asset Type |  | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
|  |  | Protection work in good condition | Damaged of rough stone apron or bank revetment not more than 3 sqm, damage to solid apron (concrete apron) not more than 1 sqm | 2 times in a year (before and after rainy season) | Condition survey as per IRC SP:35-1990 | Repairs to damaged aprons and pitching | 30 days after defect observation or 2 weeks before onset of rainy season whichever is earlier | IRC: SP 40-1993 and IRC: SP: 13-2004. |
| Bridges including ROBS Flyover etc. as applicable |  | Riding quality or user comfort | No pothole in wearing coat on bridge deck | Daily | Visual inspections per IRCSP:35-1990 | Repairs to BC or wearing coat | 15 days | MORTH Specification 2811 |
| Bridge –Super Structure |  | Bumps | No bump at expansion joint | Daily | Visual inspections per IRCSP:35-1990 | Repairs to BC or either side of expansion joints, profile correction course on approach slab in case of settlement to approach embankment | 15 days | MORTH Specification 3004.2 & 2811 |
|  |  | User safety (condition of crash barrier and guard rail) | No damaged or missing stretch of crash barrier or pedestrian hand railing | Daily | Visual inspections and detailed condition survey as per IRC SP:35-1990 | Repairs and replacement of safety barriers as the case may be | 3 days | IRC: 5-1998 IRC:SP: 84-2004. And IRC SP: 40- 1993 |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Rusted reinforcement | Not more than 0.25 sq.m. | Bi- Annually | Detailed condition survey as per IRC SP: 35-1990 Using Mobile Bridge Inspection Unit | All the corroded reinforcement shall need to be thoroughly cleaned from rusting and applied with anti- corrosive coating before carrying out the repair to affected concrete portion with epoxy mortar / concrete. | 15 days | IRC:SP: 40-1993. And MORTH Specification 1600. |
|  | Spalling of concrete | Not more than 0.50 sq.m. |  |  |  |  |  |
|  | Delamination | Not more than 0.50 sq.m. |  |  |  |  |  |
|  | Cracks wider than 0.30 mm | Not more than 1m total length. | Bi- Annually | Detailed condition survey as per IRC SP: 35-1990 Using Mobile Bridge Inspection Unit | Grouting with epoxy mortar, investigation causes for cracks development and carry out necessary rehabilitation. | 48 hours | IRC:SP: 40-1993. And MORTH Specification 2800. |
|  | Rain seepage through deck slab | Leakage- nil | Quarterly | Detailed condition survey as per IRC SP: 35-1990 Using Mobile Bridge Inspection Unit | Grouting with slab at leakage areas, waterproofing, repairs to drainage spouts. | 1months | MORTH Specification 2600 & 2700. |
|  | Deflection due to permanent loads and live loads | Within design limits. | Once in every 10 years for spans more than 40 m | Load test method | Carry out major rehabilitation works on bridge to retain original design loads capacity. | 6months | IRC:SP: 51-1999. |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Vibrations in bridge deck due to moving trucks | Frequency of vibrations shall not be more than 5 Hz. | Once in every 5 years for spans more than 30m and every 10 years for spans between 15 to 30m. | Laser displacement sensors or laser vibro-meters | Strengthening of super structure | 4 months | AASHTOLRFD Specification |
|  | Leakage in Expansion Joints | No damage to elastomeric sealant compound in strip expansion joint, no leakage of rain water through expansion joint in case of buried and asphalt plug and copper strip joint. | Bi- Annually | Detailed condition survey as per IRC SP: 35-1990 Using Mobile Bridge Inspection Unit | Replace of seal in expansion joint | 15 days | MORTH Specification 2600 and IRC SP: 40-1993. |
|  | Debris and dust in strip seal expansion joint | No dust or debris in expansion joint gap. | Monthly | Detailed condition survey as per IRC SP: 35-1990 Using Mobile Bridge Inspection Unit | Cleaning of expansion joint gaps thoroughly | 3 days | MORTH Specification 2600 and IRC SP: 40-1993. |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Drainage spouts | No down take pipe missing/broken below soffit of the deck slab. No silt, debris, clogging of drainage spout collection chamber. | Monthly | Detailed condition survey as per IRC SP: 35-1990 Using Mobile Bridge Inspection Unit | Cleaning of drainage spouts thoroughly. Replacement of missing/broken down take pipes with a minimum pipe extension of 500mm below soffit of slab. Providing sealant around the drainage spout if any leakages observed. | 3 days | MORTH Specification 2700 |
| Bridge sub structure | Cracks/spalling of concrete /rusted steel | No cracks spalling of concrete and rusted steel | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | All the corroded reinforcement shall need to be thoroughly cleaned from rusting and applied with anti-corrosive coating before carrying out repairs to substructure by grouting/guniting and micro concreting depending on type of defect noticed. | 30 days | IRC: SP: 40-1993. And MORTH Specification 2800. |
|  | Bearings | Delaminating of bearing reinforcement not more than 5%, cracking or tearing of rubber not more | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | In case of failure of even one bearing on any pier/ abutment, all the bearings on that pier/ abutment shall be replaced, in order to get uniform load transfer on to bearings. | 3 months | MORTH Specification 2810 and IRC SP: 40-199. |
| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measurement | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification sand Standards |
|  |  | Than 2 locations per side, no rupture of reinforcement or rubber. |  |  |  |  |  |
| Bridge Foundations | Scouring around foundations | Scouring shall not be lower than maximum scour level form the bridge | Bi-Annually | Condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit. In case of doubt, use Underwater camera for inspection of deep wells in major Rivers. | Suitable protection works around pier/ abutment | 1 months | IRC: SP: 40-1993. IRC: 83-2014 MORTH Specification 2500. |
|  | Protection works in good condition | Damaged of rough stone apron or bank revetment not more than 3 sq.m. damage to apron (concrete apron) not more than 1 sq.m. | 2 times in a year (before and after rainy season) | Condition survey as per IRC SP: 35-1990 | Repairs to damaged aprons and pitching. | 30 days after defect observation or 2 weeks before onset of rainy season whichever is earlier | MORTH Specification 2810 and IRC SP: 40-199. |

Note: Any Structure during the entire contract period which is found that does not complies with all requirements of this Table will be prepared, rehabilitated or even reconstructed under the scope of the contractor.

Table 5: Maintenance Criteria for Hill Roads

In addition to above, for hill roads the following provisions for maintenance is also to done.

| Hill Roads |  |  |
| --- | --- | --- |
| (i) | Damage to Retaining wall /Breast wall | 7 (Seven) days |
| (ii) | Landslides requiring clearance | 12 (Twelve) hours |
| (iii) | Snow requiring clearance | 24 (Twenty Four) hours |

Note: For all tables 1 to 5 above, latest BIS & IRC standard (even those not indicated herewith) along with MoRTH specifications shall be binding for all maintenance activities.

A.	Flexible Pavement

|  | Nature of Defect or deficiency | Time limit for repair/ rectification |
| --- | --- | --- |
| (b) Granular earth shoulders, sides lopes, drains and culvert |  |  |
| (i) | Variation by more than 1 % in the prescribed slope of camber/cross fall (shall not be less than the camber on the main carriageway) | 7 (Seven) days |
| (ii) | Edge drop at shoulders exceeding 40 mm | 7 (Seven) days |
| (iii) | Variation by more than 15% in the prescribed side (embankment) slopes | 30 (Thirty) days |
| (iv) | Rain cuts/gullies in slope | 7 (Seven) days |
| (v) | Damage to or silting of culverts and side drains | 7 (Seven) days |
| (vi) | Desalting of drains in urban/semi-urban areas | 24 (Twenty Four) days |
| (vii) | Railing, parapets, crash barriers | 7(seven) days (Restore immediately if causing safety hazard) |
| (c) Road side furniture including road sign and pavement marking |  |  |
| (i) | Damage to shape or position, poor visibility or loss of retro-reflectivity | 48 (forty eight) hours |
| (ii) | Painting of km stone, railing, parapets, crash barriers | As and when required /Once every year |
| (iii) | Damaged/missing signs road requiring replacement | 7 (Seven) days |
| (iv) | Damaged to road mark ups | 7 (Seven) days |
| (d) Road lighting |  |  |
| (i) | Any major failure of the system | 24 (Twenty Four) days |
| (ii) | Faults and minor failures | 8 (eight) hours |
| (e) Trees and plantation |  |  |

|  | Nature of Defect or deficiency | Time limit for repair/ rectification |
| --- | --- | --- |
| (i) | Obstruction in a minimum head- room of 5 m above carriageway or obstruction in visibility of road signs | 24 (Twenty Four) days |
| (ii) | Removal of fallen trees from carriageway | 4 (Four) hours |
| (iii) | Deterioration in health of trees and bushes | Timely watering and treatment |
| (iv) | Trees and bushes requiring replacement | 30 (thirty) days |
| (v) | Removal of vegetation affecting sight line and road structures | 15 (fifteen) days |
| (f) Rest area |  |  |
| (i) | Cleaning of toilets | Every 4 (four) hours |
| (ii) | Defects in electrical, water and sanitary installations | 24 (Twenty Four) days |
| (g) [Toll Plaza] |  |  |
| (h) | Other Project Facilities and Approach roads |  |
| (i) | Damage in approach roads, pedestrian facilities, truck lay- byes, bus-bays, bus-shelters, cattle crossing,[Traffic Aid Posts, Medical Aid Posts], and service roads | 15 (fifteen) days |
| (ii) | Damaged vehicles or debris on the road | 4 (four) hours |
| (iii) | Malfunctioning of the mobile crane | 4 (four) hours |
| Bridges |  |  |
| (a) Superstructure |  |  |
| (i) | Any damage, cracks, spalling/ scaling Temporary measures Permanent measures | Within 48 (forty eight) hours Within 15 (fifteen) days or as specified by the Authority’s Engineer |
| (b) Foundations |  |  |

|  | Nature of Defect or deficiency | Time limit for repair/ rectification |
| --- | --- | --- |
| (i) | Scouring and / or cavitations | 15 (fifteen) days |
| (c) Pipers, abutment, return walls and wing walls |  |  |
| (i) | Cracks and damages including settlement and tilting, spalling, scaling | 30 (thirty) days |
| (d) Bearings (metallic) of bridges |  |  |
| (i) | Deformation, damages, tilting or shifting of bearings | 15 (fifteen) days Greasing of metallic bearings once in a year |
| (e) Joints |  |  |
| (i) | Malfunctioning of joints | 15 (fifteen) days |
| (f) Other items |  |  |
| (i) | Deforming of pads in elastomeric bearings | 7 (seven) days |
| (ii) | Gathering of dirt in bearings and joints; or clogging of spouts, weep holes and vent - holes | 3 (three) days |
| (iii) | Damage or deterioration in kerbs, parapets, handrails and crash barriers | 3 (three) days (immediately within 24 hours if posing danger to safety) |
| (iv) | Rain-cuts or erosion of banks of the side slopes of approaches | 7 (seven) days |
| (v) | Damaged to wearing coat | 15 (fifteen) days |
| (vi) | Damage or deterioration in approach slabs, pitching apron, toes, floor or guide bunds | 30 (thirty) days |
| (vii) | Growth of vegetation affecting the structure or obstructing the waterway | 15 (fifteen) days |
| (g) Hill Roads |  |  |
| (i) | Damage to retaining wall/breast wall | 7 (seven) days |
| (ii) | Landslides requiring clearance | 12 (twelve) hours |

|  | Nature of Defect or deficiency | Time limit for repair/ rectification |
| --- | --- | --- |
| (iii) | Snow requiring clearance | 24 (twenty four) hours |

[Note:	Where necessary, the Authority may modify the time limit for repair/rectification, or add to the nature of Defect or deficiency before issuing the bidding document, with the approval of the competent authority.]

Schedule-F

(See Clause 3.1.5(a))

APPLICABLE PERMITS

1.	Applicable Permits

The Contractor shall obtain, as required under the Applicable Laws, the following Applicable Permits:

- Permission of the State Government for extraction of boulders from quarry;

- Permission of Village Panchayat and Pollution Control Board for installation of crushers;

- License for use of explosives;

- Permission of the State Government for drawing water from river/reservoir;

- License from inspector of factories or other competent Authority for setting up batching plant;

- Clearance of Pollution Control Board for setting up batching plant;

- Clearance of Village Panchayats and Pollution Control Board for setting up asphalt plant;

- Permission of Village Panchayats and State Government for borrow earth; and

- Any other permits, clearances or approvals required under Applicable Laws.

1.2	Applicable permits, as required, relating to environmental protection and conservation shall have been produced by the Authority in accordance with the provisions of this Agreement

Schedule-G

(See Clause 7.1.1, 7.5.3 and 19.2)

FORM OF BANK GUARANTEE

Annex-I

(See Clause 7.1.1)

PERFORMANCE SECURITY

The Chief Engineer,

NH Zone, PWD,

Pension Bada, Raipur, Chhattisgarh

WHEREAS:

(A)___________________ [name and address of contractor] (hereinafter called “the Contractor”) and [The Chief Engineer NH, PWD, Raipur], (“the Authority”) have entered into an agreement (the “Agreement”) for “Reconstruction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of bhopalpatnam-warangal-hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis”, subject to and in accordance with the provisions of the Agreement.

- The Agreement requires the Contractor to furnish a Performance Security for due and faithful performance of its obligations, under and in accordance with the Agreement, during the Construction Period and Defects Liability Period (as defined in the Agreement) in a sum of Rs. …. Crore (Rupees …. Crore) (the “Guarantee Amount”).

- We, ……………. through our branch at …………………………. (the “Bank”) have agreed to furnish this bank guarantee (hereinafter called the “Guarantee”) by way of Performance Security.

NOW, THEREFORE, the Bank hereby, unconditionally and irrevocably, guarantees and affirms as follows:

- The Bank hereby unconditionally and irrevocably guarantees the due and faithful performance of the Contractor’s obligations during Construction Period and Defects Liability Period under and in accordance with the Agreement, and agrees and undertakes to pay to the Authority, upon its mere first written demand, and without any demur, reservation, recourse, contest or protest, and without any reference to the Contractor, such sum or sums up to an aggregate sum of the guarantee amount as the Authority shall claim, without the Authority being required to prove or to show grounds or reasons for its demand and/or for the sum specified therein.

- A letter from the Authority, under the hand of an officer not below the rank of General Manager in the NHPWD that the Contractor has committed default in the due and faithful performance of all or any of its obligations under and in accordance with the Agreement shall be conclusive, final and binding on the Bank.  The Bank further agrees that the Authority shall be the sole judge as to whether the Contractor is in default in due and faithful performance of its obligations during and under the Agreement and its decision that the Contractor is in default shall be final, and binding on the Bank, notwithstanding any difference between the Authority and the Contractor, or any dispute between them pending before any court, tribunal, arbitrators or any other Authority or body, or by the discharge of the Contractor for any reason whatsoever.

- In order to give effect to this Guarantee, the Authority shall be entitled to act as if the Bank were the principal debtor and any change in the constitution of the Contractor and/or the Bank, whether by their absorption with any other body or corporation or otherwise, shall not in any way or manner affect the liability or obligation of the Bank under this Guarantee.

- It shall not be necessary, and the Bank hereby waives any necessity, for the Authority to proceed against the Contractor before presenting to the Bank its demand under this Guarantee.

- The Authority shall have the liberty, without affecting in any manner the liability of the Bank under this Guarantee, to vary at any time, the terms and conditions of the Agreement or to extend the time or period for the compliance with, fulfillment and/or performance of all or any of the obligations of the Contractor contained in the Agreement or to postpone for any time, and from time to time, any of the rights and powers exercisable by the Authority against the Contractor, and either to enforce or forbear from enforcing any of the terms and conditions contained in the Agreement and/or the securities available to the Authority, and the Bank shall not be released from its liability and obligation under these presents by any exercise by the Authority of the liberty with reference to the matters aforesaid or by reason of time being given to the Contractor or any other forbearance, indulgence, act or omission on the part of the Authority or of any other matter or thing whatsoever which under any law relating to sureties and guarantors would but for this provision have the effect of releasing the Bank from its liability and obligation under this Guarantee and the Bank hereby waives all of its rights under any such law.

- This Guarantee is in addition to and not in substitution of any other guarantee or security now or which may hereafter be held by the Authority in respect of or relating to the Agreement or for the fulfillment, compliance and/or performance of all or any of the obligations of the Contractor under the Agreement.

- Notwithstanding anything contained hereinbefore, the liability of the Bank under this Guarantee is restricted to the Guarantee amount and this Guarantee will remain in force for the period specified in paragraph 8 below and unless a demand or claim in writing is made by the Authority on the Bank under this Guarantee all rights of the Authority under this Guarantee shall be forfeited and the Bank shall be relieved from its liabilities hereunder.

- The Guarantee shall cease to be in force and effect on ****$. Unless a demand or claim under this Guarantee is made in writing before expiry of the Guarantee, the Bank shall be discharged from its liabilities hereunder.

- The Bank undertakes not to revoke this Guarantee during its currency, except with the previous express consent of the Authority in writing, and declares and warrants that it has the power to issue this Guarantee and the undersigned has full powers to do so on behalf of the Bank.

- Any notice by way of request, demand or otherwise hereunder may be sent by post addressed to the Bank at its above referred branch, which shall be deemed to have been duly authorized to receive such notice and to effect payment thereof forthwith, and if sent by post it shall be deemed to have been given at the time when it ought to have been delivered in due course of post and in proving such notice, when given by post, it shall be sufficient to prove that the envelope containing the notice was posted and a certificate signed by an officer of the Authority that the envelope was so posted shall be conclusive.

- This Guarantee shall come into force with immediate effect and shall remain in force and effect for up to the date specified in Para 8 above or until it is released earlier by the Authority pursuant to the provisions of the Agreement.

- This guarantee shall also be operable at our……………… Branch at New Delhi, from whom, confirmation regarding the issue of this guarantee or extension/ renewal thereof shall be made available on demand. In the contingency of this guarantee being invoked and payment there under claimed, the said branch shall accept such invocation letter and make payment of amounts so demanded under the said invocation.

- This Guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication no. 758, except that the supporting statement under Article 15 (a) is hereby excluded.

Signed and sealed this ………. day of ………. 20……. at ………

SIGNED, SEALED AND DELIVERED

For and on behalf of the Bank by:

(Signature)

(Name)

(Designation)

(Code Number)

(Address)

NOTES:

(i)	The bank guarantee should contain the name, designation and code number of the officer(s) signing the guarantee.

(ii)	The address, telephone number and other details of the head office of the Bank as well as of issuing branch should be mentioned on the covering letter of issuing branch.

Annex-II

(Schedule-G)

(See Clause 7.5.3)

Form for Guarantee for Withdrawal of Retention Money

The Chief Engineer,

NH Zone, PWD,

Pension Bada, Raipur, Chhattisgarh

WHEREAS:

__________________ [name and address of contractor] (hereinafter called “the Contractor”) and [The Chief Engineer NH, PWD, Raipur], (“the Authority”) have entered into an agreement (the “Agreement”) for “coConstruction of the two– Lane, the  road  of submerged length from km 5.90 to 7.575 and 32.275 to 33.4000 of Bhopalpatnam-Venktapuram-Warangal-Hyderabad Road ofd NH-163 in the State of Chhattisgarh through EPC Basis

- subject to and in accordance with the provisions of the Agreement.

- In accordance with the Clause 7.5.3 of the Agreement, the Contractor may withdraw the retention money (hereinafter called “Retention Money”) after furnishing to the Authority a bank guarantee for an amount equal to the proposed withdrawal.

- We, ……………. through our branch at …………………………. (the “Bank”) have agreed to furnish this bank guarantee (hereinafter called the “Guarantee”) for the amount of Rs. …………Cr. (Rs.………. in words) (the “Guarantee Amount”).

NOW, THEREFORE, the Bank hereby, unconditionally and irrevocably, guarantees and affirms as follows:

- The Bank hereby unconditionally and irrevocably undertakes to pay to the Authority, upon its mere first written demand, and without any demur, reservation, recourse, contest or protest, and without any reference to the Contractor, such sum or sums up to an aggregate sum of the Guarantee Amount as the Authority shall claim, without the Authority being required to prove or to show grounds or reasons for its demand and/or for the sum specified therein.

- A letter from the Authority, under the hand of an officer not below the rank of General Manager in the NHPWD that the Contractor has committed default in the due and faithful performance of all or any of its obligations under and in accordance with the Agreement shall be conclusive, final and binding on the Bank.  The Bank further agrees that the Authority shall be the sole judge as to whether the Contractor is in default in due and faithful performance of its obligations during and under the Agreement and its decision that the Contractor is in default shall be final, and binding on the Bank, notwithstanding any difference between the Authority and the Contractor, or any dispute between them pending before any court, tribunal, arbitrators or any other Authority or body, or by the discharge of the Contractor for any reason whatsoever.

- In order to give effect to this Guarantee, the Authority shall be entitled to act as if the Bank were the principal debtor and any change in the constitution of the Contractor and/or the Bank, whether by their absorption with any other body or corporation or otherwise, shall not in any way or manner affect the liability or obligation of the Bank under this Guarantee.

- It shall not be necessary, and the Bank hereby waives any necessity, for the Authority to proceed against the Contractor before presenting to the Bank its demand under this Guarantee.

- The Authority shall have the liberty, without affecting in any manner the liability of the Bank under this Guarantee, to vary at any time, the terms and conditions of the Retention Money and any of the rights and powers exercisable by the Authority against the Contractor, and either to enforce or forbear from enforcing any of the terms and conditions contained in the Agreement and/or the securities available to the Authority, and the Bank shall not be released from its liability and obligation under these presents by any exercise by the Authority of the liberty with reference to the matters aforesaid or by reason of time being given to the Contractor or any other forbearance, indulgence, act or omission on the part of the Authority or of any other matter or thing whatsoever which under any law relating to sureties and guarantors would but for this provision have the effect of releasing the Bank from its liability and obligation under this Guarantee and the Bank hereby waives all of its rights under any such law.

- This Guarantee is in addition to and not in substitution of any other guarantee or security now or which may hereafter be held by the Authority in respect of or relating to the Retention Money.

- Notwithstanding anything contained hereinbefore, the liability of the Bank under this Guarantee is restricted to the Guarantee amount and this Guarantee will remain in force for the period specified in paragraph 8 below and unless a demand or claim in writing is made by the Authority on the Bank under this Guarantee all rights of the Authority under this Guarantee shall be forfeited and the Bank shall be relieved from its liabilities hereunder.

- The Guarantee shall cease to be in force and effect 90 (ninety) days after the date of the Completion Certificate specified in Clause 12.4 of the Agreement.

- The Bank undertakes not to revoke this Guarantee during its currency, except with the previous express consent of the Authority in writing, and declares and warrants that it has the power to issue this Guarantee and the undersigned has full powers to do so on behalf of the Bank.

- Any notice by way of request, demand or otherwise hereunder may be sent by post addressed to the Bank at its above referred branch, which shall be deemed to have been duly authorized to receive such notice and to effect payment thereof forthwith, and if sent by post it shall be deemed to have been given at the time when it ought to have been delivered in due course of post and in proving such notice, when given by post, it shall be sufficient to prove that the envelope containing the notice was posted and a certificate signed by an officer of the Authority that the envelope was so posted shall be conclusive.

- This Guarantee shall come into force with immediate effect and shall remain in force and effect for up to the date specified in para 8 above or until it is released earlier by the Authority pursuant to the provisions of the Agreement.

- This guarantee shall also be operable at our……………… Branch at New Delhi, from whom, confirmation regarding the issue of this guarantee or extension/ renewal thereof shall be made available on demand. In the contingency of this guarantee being invoked and payment there under claimed, the said branch shall accept such invocation letter and make payment of amounts so demanded under the said invocation.

Signed and sealed this ………... day of ………. 20……... at ………

SIGNED, SEALED AND DELIVERED

For and on behalf of the Bank by:

(Signature)

(Name)

(Designation)

(Code Number)

(Address)

NOTES:

(i)	The bank guarantee should contain the name, designation and code number of the officer(s) signing the guarantee.

(ii)	The address, telephone number and other details of the head office of the Bank as well as of issuing branch should be mentioned on the covering letter of issuing branch.

Annex-III

(Schedule-G)

(See Clause 19.2)

Form for Guarantee for Advance Payment

The Chief Engineer,

NH Zone, PWD,

Pension Bada, Raipur, Chhattisgarh

WHEREAS:

(A_)              __________________ [name and address of contractor] (hereinafter called “the Contractor”) and [The Chief Engineer NH, PWD, Raipur], (“the Authority”) have entered into an agreement (the “Agreement”) for Reconstruction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of Bhopalpatnam-warangal-hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis

subject to and in accordance with the provisions of the Agreement.

- In accordance with the Clause 19.2 of the Agreement, the Authority shall make to the Contractor an interest bearing (@ Bank Rate) advance payment  (hereinafter called “Advance Payment”) equal to 10% (ten per cent) of the contract price;  and that the Advance Payment shall be made in two installments subject to the Contractor furnishing an irrevocable and unconditional guarantee by a scheduled bank for an amount equivalent to 110% (one hundred and ten percent) of such installment to remain effective till the complete and full repayment of the installment of the Advance Payment as security for compliance with its obligations in accordance with the Agreement. The amount of {first/second} installment of the Advance Payment is Rs. ------ cr. (Rupees ------ crore) and the amount of this Guarantee is Rs. ------- cr. (Rupees ------ crore) (the “Guarantee Amount”) $.

- We, ……………...through our branch at …………………………. (the “Bank”) have agreed to furnish this bank guarantee (hereinafter called the “Guarantee”) for the Guarantee Amount.

NOW, THEREFORE, the Bank hereby, unconditionally and irrevocably, guarantees and affirms as follows:

- The Bank hereby unconditionally and irrevocably guarantees the due and faithful repayment on time of the aforesaid installment of the Advance Payment under and in accordance with the Agreement, and agrees and undertakes to pay to the Authority, upon its mere first written demand, and without any demur, reservation, recourse, contest or protest, and without any reference to the Contractor, such sum or sums up to an aggregate sum of the guarantee amount as the Authority shall claim, without the Authority being required to prove or to show grounds or reasons for its demand and/or for the sum specified therein.

- A letter from the Authority, under the hand of an officer not below the rank of General Manager in the NHPWD, that the Contractor has committed default in the due and faithful performance of all or any of its obligations for the repayment of the installment of the Advance Payment under and in accordance with the Agreement shall be conclusive, final and binding on the Bank.  The Bank further agrees that the Authority shall be the sole judge as to whether the Contractor is in default in due and faithful performance of its obligations during and under the Agreement and its decision that the Contractor is in default shall be final, and binding on the Bank, notwithstanding any difference between the Authority and the Contractor, or any dispute between them pending before any court, tribunal, arbitrators or any other Authority or body, or by the discharge of the Contractor for any reason whatsoever

- In order to give effect to this Guarantee, the Authority shall be entitled to act as if the Bank were the principal debtor and any change in the constitution of the Contractor and/or the Bank, whether by their absorption with any other body or corporation or otherwise, shall not in any way or manner affect the liability or obligation of the Bank under this Guarantee.

- It shall not be necessary, and the Bank hereby waives any necessity, for the Authority to proceed against the Contractor before presenting to the Bank its demand under this Guarantee.

- The Authority shall have the liberty, without affecting in any manner the liability of the Bank under this Guarantee, to vary at any time, the terms and conditions of the Advance Payment or to extend the time or period of its repayment or to postpone for any time, and from time to time, any of the rights and powers exercisable by the Authority against the Contractor, and either to enforce or forbear from enforcing any of the terms and conditions contained in the Agreement and/or the securities available to the Authority, and the Bank shall not be released from its liability and obligation under these presents by any exercise by the Authority of the liberty with reference to the matters aforesaid or by reason of time being given to the Contractor or any other forbearance, indulgence, act or omission on the part of the Authority or of any other matter or thing whatsoever which under any law relating to sureties and guarantors would but for this provision have the effect of releasing the Bank from its liability and obligation under this Guarantee and the Bank hereby waives all of its rights under any such law.

- This Guarantee is in addition to and not in substitution of any other guarantee or security now or which may hereafter be held by the Authority in respect of or relating to the Advance Payment.

- Notwithstanding anything contained hereinbefore, the liability of the Bank under this Guarantee is restricted to the Guarantee amount and this Guarantee will remain in force for the period specified in paragraph 8 below and unless a demand or claim in writing is made by the Authority on the Bank under this Guarantee all rights of the Authority under this Guarantee shall be forfeited and the Bank shall be relieved from its liabilities hereunder.

- The guarantee shall cease to be in force and effect on ****.$ Unless a demand or claim under this Guarantee is made in writing on or before the aforesaid date, the Bank shall be discharged from its liabilities hereunder.

- The Bank undertakes not to revoke this Guarantee during its currency, except with the previous express consent of the Authority in writing, and declares and warrants that it has the power to issue this Guarantee and the undersigned has full powers to do so on behalf of the Bank.

- Any notice by way of request, demand or otherwise hereunder may be sent by post addressed to the Bank at its above referred branch, which shall be deemed to have been duly authorized to receive such notice and to effect payment thereof forthwith, and if sent by post it shall be deemed to have been given at the time when it ought to have been delivered in due course of post and in proving such notice, when given by post, it shall be sufficient to prove that the envelope containing the notice was posted and a certificate signed by an officer of the Authority that the envelope was so posted shall be conclusive.

- This Guarantee shall come into force with immediate effect and shall remain in force and effect for up to the date specified in Para 8 above or until it is released earlier by the Authority pursuant to the provisions of the Agreement.

- This guarantee shall also be operable at our……………… Branch at New Delhi, from whom, confirmation regarding the issue of this guarantee or extension/ renewal thereof shall be made available on demand. In the contingency of this guarantee being invoked and payment there under claimed, the said branch shall accept such invocation letter and make payment of amounts so demanded under the said invocation.

- This Guarantee is subject to the Uniform Rules for Demand Guarantees (URDG) 2010 Revision, ICC Publication no. 758, except that the supporting statement under Article 15 (a) is hereby excluded.

Signed and sealed this ………... day of ………. 20……... at ………

SIGNED, SEALED AND DELIVERED

For and on behalf of the Bank by:

(Signature)

(Name)

(Designation)

(Code Number)

(Address)

Schedule-H

(See Clauses10.1 (iv) and 19.3)

#### 1	Contract Price Weight ages

#### 1.1	The tender cost including GST is 32.48 Cr,

#### 1.2	Proportions of the Contract Price for different stages of Construction of the Project Highway shall be as specified below:

| S. No. | Item | Weightage in percentage to the Contract Price | Stage for Payment | Percentage weightage |
| --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 |
| 1 | Road works including culverts, widening and repair of culverts. | 69.365 % | A - Widening and strengthening of existing road |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Subbase course (GSB) | 0.00% |
|  |  |  | (3) Subbase (CTSB) | 0.00% |
|  |  |  | (4) Non-bituminous base course (WMM) | 0.00% |
|  |  |  | (5) Bituminous base | 0.00% |
|  |  |  | (6) wearing coat | 0.00% |
|  |  |  | (7) widening and repair of culverts | 0.00% |
|  |  |  | B.1 - Reconstruction realignment/ bypass (Flexible pavement) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 28.189 % |
|  |  |  | (3) Subbase course (GSB) | 8.593 % |
|  |  |  | (4) Non-bituminous base course (WMM) | 5.486 % |
|  |  |  | (4) Bituminous base (DBM) | 8.195 % |
|  |  |  | - Wearing coat (BC)+Granular Shoulder | 5.184 % |
|  |  |  | B.2 - Reconstruction realignment / bypass (Rigid Pavement) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Subbase course (GSB) | 0.00% |
|  |  |  | (3) Dry lean concrete (DLC) | 0.00% |
|  |  |  | (4) Pavement quality concrete (PQC) course | 0.00% |
|  |  |  | C.1 - Reconstruction/ New Service Road (flexible Pavement) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Subbase course (GSB) | 0.00% |
|  |  |  | (3) Non-bituminous base course (WMM) | 0.00% |
|  |  |  | (4) Bituminous base | 0.00% |
|  |  |  | (5) wearing coat | 0.00% |
|  |  |  | C.2 - Reconstruction/ New Service road (Rigid Pavement) |  |
|  |  |  | (1) Earthwork up to top of the subgrade | 0.00% |
|  |  |  | (2) Subbase course (GSB) | 0.00% |
|  |  |  | (3) Dry lean concrete (DLC) | 0.00% |
|  |  |  | (4) Pavement quality concrete (PQC) course | 0.00% |
|  |  |  | D. - Reconstruction/ New culverts on existing road, realignment, bypasses | 44.353 % |
| 2 | Minor Bridges/ Underpasses/ Overpasses | 0.00% | A.1 - Widening and repairs of Minor Bridges |  |
|  |  |  | (1) Foundation: On completion of the foundation work of abutments and piers | 0.00% |
|  |  |  | (2) Sub-structure: On completion of abutments and piers with abutment/ pier cap. | 0.00% |
|  |  |  | (3) Super-structure: On completion of the super- structure in all respects including wearing coat, bearings, expansion joints, handrails, crash barriers, road signs and markings, tests on completion etc. complete in all respect. | 0.00% |
|  |  |  | (4) Approaches: On completion of approaches including wing walls/ return walls, Retaining walls, stone pitching, protection works for floor, embankment slope, etc. complete in all respect and fit for use. | 0.00% |
|  |  |  | A.2 - New of Minor Bridges |  |
|  |  |  | (1) Foundation: On completion of the foundation work of abutments and piers | 0.00% |
|  |  |  | (2) Sub–structure: On completion of abutments and piers with abutment/ pier cap. | 0.00% |
|  |  |  | (3) Super-structure: On completion of the super-structure upto deck slab including bearings. | 0.00% |
|  |  |  | (4) Miscellaneous Works: On completion of wearing coat, expansion joint, crash barrier, railings, protection works and any remaining work associated to bridge including tests on bridge. | 0.00% |
|  |  |  | (5) Approaches: On completion of approaches including wing walls/ return walls, Retaining walls, stone pitching, protection works for floor, embankment slope etc. complete in all respect and fit for use. | 0.00% |
|  |  |  | (6) Guide Bunds and River Training Works: On completion of Guide Bunds and river Training Works complete in all respects | 0.00% |
|  |  |  | B.1 - Widening and repairs of Underpasses/Overpasses |  |
|  |  |  | Underpasses/ Overpasses | 0.00% |
|  |  |  | B.2 - New Underpasses/Overpasses |  |
|  |  |  | (1) Foundation: On completion of the foundation work of abutments and piers | 0.00% |
|  |  |  | (2) Sub–structure: On completion of abutments and piers with abutment/ pier cap. | 0.00% |
|  |  |  | (3) Super-structure: On completion of the super-structure upto deck slab including bearing. | 0.00% |
|  |  |  | (4) Miscellaneous Works: On completion of wearing coat, expansion joint, crash barrier, railings and any remaining work associated to bridge including tests on bridge | 0.00% |
|  |  |  | (5) Approaches: On completion of approaches including Wing walls/ Return walls, Retaining walls/ Reinforced Earth walls, stone pitching, protection works complete in all respect and fit for use. | 0.00% |
| 3 | Major Bridge works and ROB/RUB/elevated sections/flyovers including viaducts, if any | 0.00% | A.1 - Widening and repairs of existing major bridges |  |
|  |  |  | (1) Foundation: | 0.00% |
|  |  |  | (i) Pile Foundation |  |
|  |  |  | (ii) Open Foundation |  |
|  |  |  | (2) Sub-structure: | 0.00% |
|  |  |  | (3) Super-structure: (including bearings.) | 0.00% |
|  |  |  | (4) Wearing Coat including expansion joints | 0.00% |
|  |  |  | (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Guide bunds, river training works etc. | 0.00% |
|  |  |  | (8) Approaches (including retaining walls, stone pitching, protection works). | 0.00% |
|  |  |  | A.2 - New major bridges |  |
|  |  |  | (1) Foundation: | 0.00% |
|  |  |  | (i) Well Foundation |  |
|  |  |  | (ii) Pile Foundation |  |
|  |  |  | (iii) Open Foundation |  |
|  |  |  | (2) Sub-structure: | 0.00% |
|  |  |  | (3) Super-structure: (including bearings.) | 0.00% |
|  |  |  | (4) Wearing Coat including expansion joints | 0.00% |
|  |  |  | (5) Miscellaneous Items like hand rails, crash barrier, road markings etc. | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Guide bunds, river training works etc. | 0.00% |
|  |  |  | (8) Approaches (including retaining walls, stone pitching, protection works). | 0.00% |
|  |  |  | B.1 - Widening and repairs of (a) ROB and (b) RUB |  |
|  |  |  | (1) Foundation | 0.00% |
|  |  |  | (i) Pile Foundation |  |
|  |  |  | (ii) Open Foundation |  |
|  |  |  | (2) Sub structure | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) Wearing coat: (a) in case of ROB - wearing coat including expansion joints complete in all respects as specified and (b) in case of RUB - rigid pavement under RUB including drainage facility complete in all respect as specified. | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches (including retaining walls, stone pitching, protection works). | 0.00% |
|  |  |  | B.2 - New ROB / RUB |  |
|  |  |  | (1) Foundation | 0.00% |
|  |  |  | (i) Well Foundation |  |
|  |  |  | (ii) Pile Foundation |  |
|  |  |  | (iii) Open Foundation |  |
|  |  |  | (2) Sub structure | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) Wearing coat: (a) in case of ROB - wearing coat including expansion joints complete in all respects as specified and (b) in case of RUB - rigid pavement under RUB including drainage facility complete in all respect as specified. | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% |
|  |  |  | C.1 - Widening and repairs of Elevated section/Flyover/Grade Separators |  |
|  |  |  | (1) Foundation | 0.00% |
|  |  |  | (i) Pile Foundation |  |
|  |  |  | (ii) Open Foundation |  |
|  |  |  | (2) Sub structure | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) wearing coat including expansion joint | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% |
|  |  |  | C.2 - New Elevated section/Flyover/Grade Separators |  |
|  |  |  | (1) Foundation: | 0.00% |
|  |  |  | (i) Well Foundation |  |
|  |  |  | (ii) Pile Foundation |  |
|  |  |  | (iii) Open Foundation |  |
|  |  |  | (2) Sub-structure: | 0.00% |
|  |  |  | (3) Superstructure (including bearing) | 0.00% |
|  |  |  | (4) Wearing coat including expansion joint | 0.00% |
|  |  |  | (5) Miscellaneous items (like hand rails, crash barriers, road markings etc.) | 0.00% |
|  |  |  | (6) Wing walls/return walls | 0.00% |
|  |  |  | (7) Approaches(including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% |
| 4 | Other works | 30.635 % | (i) Excavation upto bottom of subgrade of existing Pavement and transportation of mucks | % |
|  |  |  | (ii) Site clearance, Tree cutting/uprooting and Dismantling of existing structures | 0.748 % |
|  |  |  | (iii) Road signs, markings, km stones safety Devices, boundary pillars, RPM, Place Identification signs, Painting of Crash Barrier etc. | 1.633 % |
|  |  |  | (iv) Utility Ducts | 0.00% |
|  |  |  | (v) Junction improvement works | 0.00% |
|  |  |  | (vi) Road side RCC drains/Toe wall | 32.332% |
|  |  |  | (vii) Safety and traffic management during construction | 0.00% |
|  |  |  | (viii) Concrete Safety Barrie/Crash barrier/stone $ boulder pitching | 65.287% |
|  |  |  | (ix) Plantation of shrubs in road median | 0.00% |
| 5 | Utility shifting | % | Pipeline Utility Shifting | 0.00% |
|  |  |  | Electrical Utility Shifting | 0.00% |
| Total |  | 100.00% |  |  |

#### 1.3	Procedure of estimating the value of work done.

#### 1.3.1	Road works

Procedure for estimating the value of road work done shall be as follows:

Table1.3.1

| Stage of Payment | Percentage -weight age | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| A - Widening and strengthening of existing road |  |  |
| (1) Earthwork up to top of the sub- grade | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in a length of not less than 10 (ten) percent of the total length or 500m whichever is less |
| (2) Sub-base Course (GSB) | 0.00% |  |
| (3) Subbase (CTSB) | 0.00% |  |
| (4) Non bituminous Base course | 0.00% |  |
| (5) Bituminous Base course | 0.00% |  |
| (6) Wearing Coat | 0.00% |  |
| (7) widening and repair of culverts | 0.00% | Cost of completed culverts shall be determined pro rata basis with respect to the total no. of culverts. The payment shall be made on the completion of atleast one culvert. 75% of the cost will be payable on completion of box/ abutments and slab/ pipe and head wall. Remaining 25% will become payable on completion of protection works including return/ wing walls and any other work associated with culverts. |
| B.1 - Reconstruction realignment/bypass (Flexible pavement) |  | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 500 m length, whichever is less. |
| (1) Earthwork up to top of the sub- grade | 28.189 % |  |
| (2) Sub-base Course | 8.593 % |  |
| (3) Non bituminous Base course | 5.486% |  |
| (4) Bituminous Base course | 8.195 % |  |
| (5) Wearing Coat+Grannular shoulder | 5.184% |  |
| B.2 - Reconstruction/ realignment/bypass (Rigid Pavement) |  | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 500 m length, whichever is less. |
| (1) Earthwork up to top of the sub- grade | 0.00% |  |
| (2) Sub-base Course | 0.00% |  |
| (3) Dry lean concrete (DLC) | 0.00% |  |
| (4) Pavement quality concrete (PQC) course | 0.00% |  |
| C.1 - Reconstruction/ New Service Road (flexible Pavement) |  | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 500 m length, whichever is less. |
| (1) Earthwork up to Sub grade top | 0.00% |  |
| (2) Sub base course (GSB) | 0.00% |  |
| (3) Non-bituminous base course (WMM) | 0.00% |  |
| (4) Bituminous base | 0.00% |  |
| (5) wearing coat | 0.00% |  |
| C.2 - Reconstruction/ New Service Road (Rigid Pavement) |  | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 500 m length, whichever is less. |
| (1) Earthwork up to Sub grade top | 0.00% |  |
| (2) Sub base course (GSB) | 0.00% |  |
| (3) Dry lean concrete (DLC) | 0.00% |  |
| (4) Pavement quality concrete (PQC) course | 0.00% |  |
| D. - Reconstruction & New Culverts on existing road, realignments, bypasses | 44.353 % | Cost of each culvert shall be determined on pro rata basis with respect to the total number of culverts. Payment shall be made on the completion of atleast one culvert. 75% of the cost will be payable on completion of box/ abutments and slab/ pipe and head wall. Remaining 25% will become payable on completion of protection works including return/wing walls and any other work associated with culverts. |

@. For example, if the total length of bituminous work to be done is 100 km, the cost per km of bituminous work shall be determined as follows:

Cost per km = P x weightage for road work x weightage for bituminous work x (1/L)

Where P= Contract Price. And L = Total length in km.

Similarly, the rates per km for other stages shall be worked out accordingly.

Note: The length affected due to law-and-order problems or litigation during execution due to which the Contractor is unable to execute the work, may be deducted from the total project length for payment purposes. The total length calculated here is only for payment purposes and will not affect and referred in other clauses of the Contract Agreement.

#### 1.3.2	Minor Bridges and Underpasses/Overpasses.

Procedure for estimating the value of Minor Bridge and underpasses/Overpasses shall be as stated in table 1.3.2:

Table1.3.2

| Stage of Payment | Percentage -weight age | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| A.1-Widening and repair of minor bridges (length > 6m and < 60m) | 0.00% | Cost of each minor bridge shall be determined on pro rata basis with respect to the total linear length (m) of the minor bridges. |
| (i) Foundation: On completion of the foundation work of abutments and piers | 0.00% | (i) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage i.e completion of atleast two foundations of each bridge. In case where load testing is specified for foundation, the trigger of first payment shall include load testing also. |
| (ii) Sub – structure: | 0.00% | (ii) Sub - structure – Payment shall be made on pro-rata basis on completion of stage i.e. completion of atleast one sub-structure upto abutment/ pier cap level of each bridge. |
| (iii) Super-structure: On completion of the super-structure in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road signs & markings, tests on completion etc. complete in all respect. | 0.00% | (iii) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e., completion of super-structure of at least one span in all respects as specified in the column of "Stage of Payment" in this sub-clause. |
| (iv) Approaches: On completion of approaches including Retaining walls, stone pitching, protection works for floor, embankment slope etc. complete in all respect and fit for use. | 0.00% | (iv) Approaches: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of approaches including wing walls/ return walls, retaining walls, stone pitching in all respect as specified in the column of “Stage of Payment” in this sub- clause for each bridge. |
| A.2- New minor bridges | 0.00% | Cost of each minor bridge shall be determined on pro rata basis with respect to the total linear length (m) of the minor bridges. |
| (i) Foundation: On completion of the foundation work of abutments and piers. | 0.00%0.00% | (i) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage completion of atleast two foundations of each bridge. In case where load testing is specified for foundation, the trigger of first payment shall include load testing also. |
| (ii) Sub – structure: | 0.00% | (ii) Sub – structure: Payment shall be made on pro-rata basis on completion of stage i.e. completion of atleast one sub-structure upto abutment/ pier cap level of each bridge. |
| (iii) Super-structure: On completion of the super-structure upto deck slab including bearings. | 0.00% | (iii) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e., completion of super-structure of at least one span upto deck slab including bearing as specified in the column of "Stage of Payment" in this sub- clause. If pre-cast girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book, applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
| (iv) Miscellaneous Works: | 0.00% | (iv) Miscellaneous Works: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of wearing coat, expansion joint, crash barrier, railing, protection works, drainage and any other remaining work associated to bridge including tests on bridge for each bridge |
| (v) Approaches: On completion of approaches including Retaining walls, stone pitching, protection works for floor, embankment slope etc. complete in all respect and fit for use. | 0.00% | (v) Approaches: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of approaches including wing walls/ return walls, retaining walls, stone pitching in all respect as specified in the column of “Stage of Payment” in this sub- clause for each bridge. |
| (vi) Guide Bunds and River Training Works: On completion of Guide Bunds and river Training Works complete in all respects | 0.00% | (vi) Guide Bunds and River Training Works: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of Guide Bunds and River training Works in all respects as specified for each bridge. |
| B.1-Widening and repair of underpasses/ overpasses | 0.00% | Cost of each underpass/overpass shall be determined on pro rata basis with respect to the total linear length of the underpasses/overpasses. Payment shall be made on the completion of widening & repair works of a underpass/overpass. |
| B.2- New Underpasses/ Overpasses: | 0.00% | Cost of each Underpass/Overpass shall be determined on pro rata basis with respect to the total linear length (m) of the Underpasses/Overpasses. |
| (i) Foundation: On completion of the foundation work including foundations, of abutments and piers | 0.00% | (i) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. completion of foundation(s) of each underpass/overpass. In case where load testing is specified for foundation, the trigger of first payment shall include load testing also. |
| (ii) Sub-structure : | 0.00% | (ii) Sub-structure: Payment shall be made on pro-rata basis on completion of stage i.e. completion of atleast one sub-structure upto abutment/ pier cap level of each bridge. |
| (iii) Super-structure: On completion of the super-structure upto deck slab, | 0.00% | (iii) Super-structure: Payment shall be made on pro-rata basis on completion of a stage 'i.e. completion of super-structure of at least one span upto deck slab including bearing as specified in the column of "Stage of Payment" in this sub- clause: If pre-cast girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book, applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
| (iv) Miscellaneous Works: | 0.00% | (iv) Miscellaneous Works: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of wearing coat, expansion joint, crash barrier, railing, protection works and any other remaining work associated to bridge including tests on bridge for each bridge. |
| (v) Approaches: On completion of approaches including wing wall/ return wall, Retaining walls/ Reinforced Earth walls, stone pitching, protection works complete in all respect and fit for use. | 0.00% | (v) Approaches: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of approaches including wing wall/ return wall, retaining walls, Reinforced Earth walls, stone pitching, protection works complete in all respect for each bridge. |

#### 1.3.3	Major Bridge works, ROB/RUB and Structures

Procedure for estimating the value of major Bridge works, ROB/RUB and structure work shall be as stated in table 1.3.3:

Table 1.3.3

| Stage of Payment | Percentage -weight age | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| A.1- Widening and repairs of Major Bridges | 0.00% | Cost of each Major Bridge shall be determined on pro rata basis with respect to the total linear length (m) of the Major Bridges. |
| (1) Foundation |  | (1) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. completion of atleast one foundation of each of the major Bridge as specified hereinunder. |
| (i) Pile Foundation | 0.00% | (i) Pile Foundation |
| (a) Piling – On completion of pile upto bottom of pile cap |  | (a) Piling : Payment of 70% shall be made on completion of piling upto bottom of pile cap for each pile on prorate basis. |
| (b) Pile Cap : On completion of pile cap |  | (b) Pile Cap : Payment of 30% on pro- rata basis shall be made on completion of pile cap. |
|  |  | In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (ii) Open Foundation | 0.00% | (ii) Open Foundation: Payment shall be made on completion of a stage i.e. on completion of atleast one foundation. |
| (2) Sub-structure | 0.00% | (2) Sub-Structure:. Payment against Sub-structure shall be made on pro- rata basis on completion of a stage i.e. completion of atleast one sub- structure of abutments/piers upto abutment/pier cap level of each of the major bridge. |
| (3) Super-structure (including bearings) | 0.00% | (3) Super-structure: Payment shall be made on prorata basis on completion of a stage i.e. completion of superstructure upto deck slab including bearings of at least one span as specified here in under : |
|  |  | If pre-cast RCC/PSC/Steel girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book, applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
| (4) Wearing Coat including expansion joints | 0.00% | (4) Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified for each major bridge. |
| (5) Miscellaneous Items like | 0.00% | (5) Miscellaneous: Payments shall be |
| hand rails, crash barriers, |  | made on completion of all |
| road markings etc. |  | miscellaneous works like hand rails, |
|  |  | crash barriers, road markings etc. |
|  |  | complete in all respects as specified |
|  |  | for each major bridge. |
| (6) Wing walls/return walls | 0.00% | (6) Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified for each major bridge. |
| (7) Guide Bunds, River | 0.00% | (7) Guide Bunds, River Training |
| Training works etc. |  | works: Payments shall be made on completion of all guide bunds/river |
|  |  | training works etc. complete in all |
|  |  | respects as specified for each major |
|  |  | bridge. |
| (8) Approaches (including | 0.00% | (8) Approaches: Payments shall be |
| Retaining walls, stone |  | made on completion of both |
| pitching and protection |  | approaches including stone pitching, |
| works) |  | protection works, etc. complete in all respects as specified for each major bridge. |
| A.2- New Major Bridges | 0.00% | Cost of each Major Bridge shall be determined on pro rata basis with respect to the total linear length (m) of the Major Bridge. |
| (1) Foundation |  | (1) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. completion of atleast one foundation of each of the major Bridge as specified here in under: |
| (i) Well Foundation | 0.00% | (i) Well Foundation |
| (a) On completion of Cutting Edge + Well Curb |  | (a) Cutting Edge + Well Curb: Payment of 10% shall be made on completion of a stage i.e. completion of cutting edge + well curb. |
| (b) Wellsteining : On completion of well steining upto bottom of well cap. |  | (b) Well steining : Payment of 65% shall be made on completion of well steining upto bottom of well cap. The payment stage shall be further sub-divided on pro-rata basis i.e. (i) on completion upto 10 m and (ii) on completion of each subsequent 5 m or part thereof. |
| (c) On completion of bottom plug + top plug (if provisioned as per design) + well cap |  | (c) Bottom plug + top plug (if provisioned as per design) + well cap: Payment of 25% shall be made on completion of a stage i.e. completion of bottom plug, back fill, top plug and well cap. |
| (ii) Pile Foundation | 0.00% | (ii) Pile Foundation |
| (a) Piling – On completion of pile upto bottom of pile cap |  | (a) Piling : Payment of 70% shall be made on completion of piling upto bottom of pile cap for each pile on prorota basis. |
| (b) Pile Cap : On completion of pile cap |  | (b) Pile Cap : Payment of 30% shall be made on completion of pile cap. In case where load testing is required for foundation, the trigger of first payment shall include load testing |
|  |  | also where specified. |
| (iii) Open Foundation | 0.00% | (iii) Open Foundation: Payment shall be made on completion of a stage i.e. on completion of atleast one foundation. |
| (2) Sub-structure | 0.00% | (ii) Sub-Structure:. Payment against Sub-structure shall be made on pro- rata basis on completion of a stage i.e. completion of atleast one sub- structure of abutments/piers upto abutment/pier cap level of each of the major bridge. |
| (3) Super-structure (including bearings) | 0.00% | (3) Super-structure: Payment shall be made on prorata basis on completion of a stage i.e. completion of superstructure upto deck slab including bearings of at least one span as specified here in under: |
|  |  | If pre-cast girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book, applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
|  |  | (For cable stayed bridge and suspension cable bridge, detailed payment stage may be included on case to case basis) |
| (4) Wearing Coat including expansion joints | 0.00% | (4) Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified for each major bridge. |
| (5) Miscellaneous Items like | 0.00% | (5) Miscellaneous: Payments shall be |
| hand rails, crash barriers, |  | made on completion of all |
| road markings etc. |  | miscellaneous works like hand rails, |
|  |  | crash barriers, road markings etc. |
|  |  | complete in all respects as specified |
|  |  | for each major bridge. |
| (6) Wing walls/return walls | 0.00% | (6) Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified for each major bridge. |
| (7) Guide Bunds, River | 0.00% | (7) Guide Bunds, River Training |
| Training works etc. |  | works: Payments shall be made on |
|  |  | completion of all guide bunds/river |
|  |  | training works etc. complete in all |
|  |  | respects as specified for each major |
|  |  | bridge. |
| (8) Approaches (including | 0.00% | (8) Approaches: Payments shall be |
| Retaining walls, stone |  | made on completion of both |
| pitching and protection |  | approaches including stone pitching, |
| works for floor, |  | protection works, etc. complete in |
| embankment slope etc.) |  | all respects as specified for each |
|  |  | major bridge. |
| - -Widening and repairs of - ROB - RUB |  | Cost of each ROB/RUB shall be determined on pro rata basis with respect to the total linear length (m) of the ROBs/RUBs. |
| (1) Foundation | 0.00% | (1) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. completion of atleast one foundation of each of the ROB/RUB as specified here in under. |
| (i) Pile Foundation (a) Piling – On completion of pile upto bottom of pile cap | 0.00% | (i) Pile Foundation (a) Piling : Payment of 70% shall be made on completion of piling upto bottom of pile cap for each pile on prorata basis. |
| (b) Pile Cap : On completion of pile cap |  | (b) Pile Cap : Payment of 30% on pro- rata basis shall be made on completion of pile cap. |
|  |  | In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (ii) Open Foundation | 0.00% | (ii) Open Foundation: Payment shall |
|  |  | be made on completion of a stage i.e. on completion of atleast one foundation. |
| (2) Sub-structure | 0.00% | (2) Sub-Structure:. Payment against Sub-structure shall be made on pro-rata basis on completion of a stage i.e. completion of atleast one sub- structure of abutments/piers upto abutment/pier cap level of each of the ROB/RUB. |
| (3) Super-structure (including bearings) | 0.00% | (3) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of superstructure upto deck slab including bearings of at least one span as specified here in under : |
|  |  | If pre-cast girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book, applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
| (4) Wearing Coat including expansion joints in case of | 0.00% | (4) Wearing Coat: Payment shall be made on completion of (a) in case of |
| ROB. In case of RUB, rigid |  | ROB- wearing coat including |
| pavement under RUB |  | expansion joints complete in all |
| including drainage facility |  | respects as specified for each of the |
| as specified. |  | ROB and (b) in case of RUB- rigid |
|  |  | pavement under RUB including |
|  |  | drainage facility complete in all |
|  |  | respects as specified for each of the |
|  |  | RUB. |
| (5) Miscellaneous Items like hand rails, crash barriers, | 0.00% | (5) Miscellaneous: Payments shall be made on completion of all |
| road markings etc. |  | miscellaneous works like hand rails, crash barriers, road markings etc. |
|  |  | complete in all respects as specified |
|  |  | for each of the ROB/ RUB. |
| (6) Wing walls/return walls | 0.00% | (6) Wing walls/return walls: |
|  |  | Payments shall be made on completion of all wing walls/return walls complete in all respects as specified for each of the ROB/ RUB. |
| (7) Approaches (including Retaining walls, stone | 0.00% | (7) Approaches: Payments shall be made on completion of both |
| pitching and protection |  | approaches including stone pitching, |
| works) |  | protection works, etc. complete in all respects as specified for each of |
|  |  | the ROB/ RUB. |
| B.2- New - ROB - RUB |  | Cost of each ROB/RUB shall be determined on pro rata basis with respect to the total linear length (m) of the ROBs/RUBs. |
| (1) Foundation | 0.00% | (1) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. completion of atleast one foundation of each of the ROB/RUB as specified here in under: |
| (i) Well Foundation | 0.00% | (i) Well Foundation |
| (a) On completion of Cutting Edge + Well Curb |  | (a) Cutting Edge + Well Curb: Payment of 10% shall be made on completion of a stage i.e. completion of cutting edge + well curb. |
| (b) Wellsteining : On completion of well steining upto bottom of well cap. |  | (b) Well steining : Payment of 65% shall be made on completion of well steining upto bottom of well cap. The payment stage shall be further sub-divided on pro-rata basis i.e. (i) on completion upto 10 m and (ii) on completion of each subsequent 5 m or part thereof. |
| (c) On completion of bottom plug + top plug (if provisioned as per design) + well cap |  | (c) Bottom plug + top plug (if provisioned as per design) + well cap: Payment of 25% shall be made on completion of a stage i.e. completion of bottom plug, back fill, top plug and well cap. |
| (ii) Pile Foundation (a) Piling – On completion of pile upto bottom of pile | 0.00% | (ii) Pile Foundation (a) Piling : Payment of 70% shall be made on completion of piling upto |
| cap | 0.00% | bottom of pile cap for each pile on prorota basis. |
| (b) Pile Cap : On completion of pile cap |  | (b) Pile Cap : Payment of 30% shall be made on completion of pile cap. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (iii) Open Foundation | 0.00% | (iii) Open Foundation: Payment shall be made on completion of a stage i.e. on completion of atleast one foundation. |
| 2) Sub-structure | 0.00% | (2) Sub-Structure: Payment against Sub-structure shall be made on pro- rata basis on completion of a stage i.e. completion of atleast one sub- structure of abutments/piers upto abutment/pier cap level of each of the ROB/RUB. |
| (3) Super-structure (including bearings) | 0.00% | (3) Super-structure: Payment shall be made on prorata basis on completion of a stage i.e. completion of superstructure upto deck slab including bearings of at least one span as specified here in under : |
|  |  | If pre-cast girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book. Applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
| (4) Wearing Coat including expansion joints in case of | 0.00% | (4) Wearing Coat: Payment shall be made on completion of (a) in case of |
| ROB. In case of RUB, rigid |  | ROB- wearing coat including |
| pavement under RUB |  | expansion joints complete in all |
| including drainage facility |  | respects as specified for each of the |
| as specified. |  | ROB and (b) in case of RUB- rigid pavement under RUB including |
|  |  | drainage facility complete in all |
|  |  | respects as specified for each of the |
|  |  | RUB. |
| (5) Miscellaneous Items like hand rails, crash barriers, | 0.00% | (5) Miscellaneous: Payments shall be made on completion of all |
| road markings etc. |  | miscellaneous works like hand rails, crash barriers, road markings etc. |
|  |  | complete in all respects as specified |
|  |  | for each of the ROB/RUB. |
| (6) Wing walls/return walls | 0.00% | (6) Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified for each of the ROB/RUB. |
| (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% | (7) Approaches: Payments shall be made on completion of both approaches of each ROB including stone pitching, protection works, etc. complete in all respects as specified here in under : |
|  |  | If reinforced soil wall is used with |
|  |  | facia panel/blocks, interim payment |
|  |  | shall be made @75% of the Cost of |
|  |  | that element as derived from MoRTH |
|  |  | data Book. Applicable SOR of State |
|  |  | PWD on Base Date with tender |
|  |  | discount/premium applied thereon. |
| C.1- Widening and repairs of Elevated Section/Flyovers/ Grade Separators | 0.00% | Cost of each structure shall be determined on pro rata basis with respect to the total linear length (m) of the structures. |
| (i) Foundation |  | (1) Foundation : Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. completion of atleast one foundation of each of the structure as specified here in under : |
| (i) Pile Foundation | 0.00% | (i) Pile Foundation |
| (a) Piling – On completion of pile upto bottom of pile cap |  | (a) Piling : Payment of 70% shall be made on completion of piling upto bottom of pile cap for each pile on prorate basis. |
| (b) Pile Cap : On |  | (b) Pile Cap : Payment of 30% on pro- |
| completion of pile cap |  | rata basis shall be made on completion of pile cap. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (ii) Open Foundation | 0.00% | (ii) Open Foundation: Payment shall be made on completion of a stage i.e. on completion of atleast one foundation. |
| (2) Sub-structure | 0.00% | (2) Sub-Structure:. Payment against Sub-structure shall be made on pro- rata basis on completion of a stage i.e. completion of atleast one sub- structure of abutments/piers upto abutment/pier cap level of each of the structure. |
| (3) Super-structure (including bearings) | 0.00% | (3) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super- structure upto deck slab including bearings of at least one span as specified here in under : If pre-cast girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book, applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
| (4) Wearing Coat including expansion joints | 0.00% | (4) Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified for each of the structure. |
| (5) Miscellaneous Items like hand rails, crash barriers, road markings etc. | 0.00% | (5) Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified for each of the structure. |
| (6) Wing walls/return walls | 0.00% | (6) Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified for each of the structure. |
| (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% | (7) Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects of each structure. |
| C.2 -New Elevated Section/Flyovers/ Grade Separators (1) Foundation | 0.00% | Cost of each structure shall be determined on pro rata basis with respect to the total linear length (m) of the structures. (1) Foundation: Payment against foundation shall be made on pro-rata basis on completion of a stage i.e. completion of atleast one foundation of each of the structure as specified here in under : |
| (i) Well Foundation - On completion of Cutting Edge + Well Curb - Wellsteining : On completion of well steining upto bottom of well cap. - On completion of bottom plug + top plug (if provisioned as per design) + well cap | 0.00% | (i) Well Foundation - Cutting Edge + Well Curb: Payment of 10% shall be made on completion of a stage i.e. completion of cutting edge + well curb. - Well steining : Payment of 65% shall be made on completion of well steining upto bottom of well cap. The payment stage shall be further sub-divided on pro-rata basis i.e. (i) on completion upto 10 m and (ii) on completion of each subsequent 5 m or part thereof. - Bottom plug + top plug (if provisioned as per design) + well cap: Payment of 25% shall be made on completion of a stage i.e. completion of bottom plug, back fill, top plug and well cap. |
| (ii) Pile Foundation |  | (ii) Pile Foundation |
| - Piling – On completion of pile upto bottom of pile cap - Pile Cap : On completion of pile cap | 0.00% | - Piling : Payment of 70% shall be made on completion of piling upto bottom of pile cap for each pile on pro-rata basis. - Pile Cap : Payment of 30% shall be made on completion of pile cap. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified. |
| (iii) Open Foundation | 0.00% | (iii) Open Foundation: Payment shall be made on completion of a stage i.e. on completion of atleast one foundation. |
| (2) Sub-structure | 0.00% | (2) Sub-Structure:. Payment against Sub- structure shall be made on pro- rata basis on completion of a stage i.e. completion of atleast one sub- structure of abutments/piers upto abutment/pier cap level of each of the structure. |
| (3) Super-structure (including bearings) | 0.00% | (3) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super- structure upto deck slab including bearings of at least one span as specified here in under: If pre-cast girders/ segments are used, interim payments shall be made at 75% of the cost of that element, as derived from MoRTH Data Book, applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |
| (4) Wearing Coat including expansion joints | 0.00% | (4) Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified for each of the structure. |
| (5) Miscellaneous Items like hand rails, crash barriers, road markings etc. | 0.00% | (5) Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified for each of the structure. |
| (6) Wing walls/return walls | 0.00% | (6) Wing walls/return walls: Payments shall be made on completion of all wing walls/return walls complete in all respects as specified for each of the structure. |
| (7) Approaches (including Retaining walls/Reinforced Earth wall, stone pitching and protection works) | 0.00% | (7) Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified here in under : If reinforced soil wall is used with facia panel/blocks, interim payment shall be made @75% of the Cost of that element as derived from MoRTH data Book. Applicable SOR of State PWD on Base Date with tender discount/premium applied thereon. |

#### 1.3.4	Other works.

Procedure for estimating the value of other works done shall be as stated in table 1.3.4:

Table 1.3.4

| Stage of Payment | Percentage –weight age | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| (i) Excavation of existing Pavement up to bottom of subgrade | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in a length of not less than 10 (ten) percent of the total length or 500m whichever is less |
| (ii) Site clearance, Tree cutting/uprooting and Dismantling of existing roads | 0.748 % | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in a length of not less than 10 (ten) percent of the total length or 500m whichever is less |
| (iii) Road signs, markings, km stones safety Devices, boundary pillars, RPM, Place Identification signs, Painting of Crash Barrier etc. | 1.633 % | Unit of measurement is linear length in km. Payment shall be made on pro rata basis on completion of a stage in a length of not less than one Km on both sides. |
| (iv) Utility Ducts | 0.00% | Unit of measurement is linear length in metre . Payment shall be made on pro rata basis on completion of a stage in a length of not less than 24 m across the road. |
| (v) Junction improvement works | 0.00% | Unit of measurement is each number. Payment shall be made on pro rata basis for completed improvement works.. |
| (vi) Road side RCC drains/Toe wall | 32.332% | Unit of measurement is linear length in metre . Payment shall be made on pro rata basis on completion of a stage in a length of not less than 100 m on one side. |
| (vii) Safety and traffic management during construction | 0.00% | Payment shall be made on prorate basis every six months. |
| (viii) Concrete Safety Barrier/Crash barrier & stone and boulder pitching | 65.287 % | Unit of measurement is linear length. Payment shall be made on pro rata basis on completion of a stage in a length of not less than 10% (ten per cent) of the total length and 100 m whichever is less. |
| (ix) Plantation of shrubs in road median | 0.00% | Unit of measurement is linear length in Km. Payment shall be made on pro rata basis on completion of one Km. |

#### 1.3.5	Utility Shifting

Procedure for estimating the value of utility shifting works done shall be as stated in Table 1.3.5:

#### Table 1.3.5

| Stage of Payment | Percentage -weight age | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| Pipeline Utility Shifting | 0.00% | Payment is divided in following activities and Payment of each activity shall be made on pro rata basis on completion of 5km of linear project length. Removal of existing utility; 30%. Erection/ Laying; 30%. Commissioning; 40%. Dismantling will include proper listing and stocking of usable and non-usable items. Commissioning will be completed on furnishing the commissioning certificate from concerned utility owning department. |
| Electrical Utility Shifting | 0.00% |  |

Note: (1) In case of innovative Major Bridge Projects like cable suspension/cable stayed and exceptionally long span bridges, the schedule may be modified as per site requirements before bidding with due approval of Competent Authority.

(2)	The Schedule for exclusive Tunnel Projects may be prepared as per site requirements before bidding with due approval of Competent Authority.

(3)	(a) In order to maintain cash flow in the project, the Authority shall also make interim monthly payments to the Contractor for the work done during the month for which the corresponding stage, as mentioned in Schedule-H, has not been achieved. Such work shall be measured, in a length, number or area as specified in corresponding stage of Schedule-H and valued in accordance with the proportion of the weightage of Contract Price assigned to that stage in Schedule-H.   '90% of value of such work shall be paid as an 'Interim Monthly Payment’ under clause 19.3 (i) of Contract Agreement.

(b) For Pre cast/ pre-fabricated elements to be used in permanent works, interim payments to be made @ 75% of cost of that element ( to be derived from MoRT&H data book) as per schedule H.

(c) Upon completion of the defined 'stage’, a reconciliation of the interim payments shall be carried out, and any balance amount shall be paid. For the avoidance of doubt, it is clarified that the interim monthly payments are made solely to maintain cash flow in the project. In the event of termination of the project, under Clause23.1, 23.2 or 23.3, as the case may be, such interim payments shall be dealt with as per Clause 23.5 (i) (b) of the Contract Agreement.

#### 2.	Procedure for payment for Maintenance.

#### 2.1	The cost for maintenance shall be as stated in Clause 14.1.(i)

#### 2.2	Payment for Maintenance shall be made in quarterly instalments in accordance with the provisions of Clause 19.7.

Schedule - I

(See Clause 10.2 (IV))

1. Drawings

Drawings In compliance of the obligations set forth in Clause 10.2 of this Agreement, the Contractor shall furnish to the Authority’s Engineer, free of cost, all Drawings listed in Annex-I of this Schedule-I.

2. Additional Drawings: -

If the Authority’s Engineer determines that for discharging its duties and functions under this Agreement, it requires any drawings other than those listed in Annex-I, it may by notice require the Contractor to prepare and furnish such drawings forthwith. Upon receiving a requisition to this effect, the Contractor shall promptly prepare and furnish such drawings to the Authority’s Engineer, as if such drawings formed part of Annex-I of this Schedule-I.

Annex – I

(Schedule - I)

List of Drawings

1.	A minimum list of the drawings of the various components/elements of the project highway and project facility required to be submitted by the Contractor is given below:

(a) 	Drawing of horizontal alignment, vertical profile and detailed cross sections;

(b) 	Drawings of cross drainage works, i.e. Bridges/Culverts/Flyovers and Other Structures;

(c) 	Drawings for River Training works;

(d)	Drawings of interchanges, major intersections and underpasses;

(e)	Drawing of control centre;

(f)	Drawings of road furniture items including traffic signage, marking, safety barriers, etc;

(g)	Drawings of traffic diversions plans and traffic control measures;

(h)	Drawings of road drainage measures;

(i)	Drawings of typical details slope protection measures;

(j)	Drawings of landscaping and horticulture;

(k)	Drawings of pedestrian crossing;

(l)	General Arrangement showing Base Camp and Administrative Block;

(m)	Any other drawings as per instruction of Authority Engineer.

Schedule-J

(See Clause 10.3.2)

PROJECT COMPLETION SCHEDULE

1.	Project Completion Schedule

During Construction period, the Contractor shall comply with the requirements set forth in this Schedule J for each of the Project Milestones and the Scheduled Completion Date.  Within 15 (fifteen) days of the date of each Project Milestone, the Contractor shall notify the Authority of such compliance along with necessary particulars thereof.

2.	Project Milestone-I

2.1	Project Milestone-I shall occur on the date falling on the 135th(One Hundred and Twentieth) day from the Appointed Date (25 % of schedule con   period the “Project Milestone-I”).

2.2 	Prior to the occurrence of Project Milestone-I, the Contractor shall have commenced construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 10% (ten per cent) of the Contract Price.

3.	Project Milestone-II$

3.1 	Project Milestone-II shall occur on the date falling on the 324th(Two hundred and Tenth) day from the Appointed Date (60% of schedule con  period the “Project Milestone-II”).

3.2  	Prior  to  the  occurrence  of  Project Milestone-II, the Contractor shall have continued with construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 30% (thirty per cent) of the Contract Price.

4.	Project Milestone-III

4.1 	Project Milestone-III shall occur on the date falling on the 459th(Three hundredth) day from the Appointed Date 85% of schedule con period  (the “Project Milestone-III”).

4.2  	Prior  to  the  occurrence  of  Project Milestone-III, the Contractor shall have continued with construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 60% (sixty per cent) of the Contract Price.

5	Schedule Completion Date

5.1 	The Scheduled Completion Date shall occur on the 540th(Three Hundred Sixty Fifth) day from the Appointed Date.

5.2 	On or before the Scheduled Completion Date, the Contractor shall have completed construction in accordance with this Agreement.

6	Extension of time

Upon extension of any or all of the aforesaid Project Milestones or the Scheduled Completion Date, as the case may be, under and in accordance with the provisions of this Agreement, the Project Completion Schedule shall be deemed to have been amended accordingly.

Schedule-K

(See Clause 12.1.2)

Tests on Completion

1.	Schedule for Tests

  - The Contractor shall, no later than 30 (thirty) days prior to the likely completion of construction, notify the Authority’s Engineer and the Authority of its intent to subject the Project Highway to Tests, and no later than 10 (ten) days prior to the actual date of Tests, furnish to the Authority’s Engineer and the Authority detailed inventory and particulars of all works and equipment forming part of Works.

  - The Contractor shall notify the Authority’s Engineer of its readiness to subject the Project Highway to Tests at any time after 10 (ten) days from the date of such notice, and upon receipt of such notice, the Authority’s Engineer shall, in consultation with the Contractor, determine the date and time for each Test and notify the same to the Authority who may designate its representative to witness the Tests. The Authority’s Engineer shall thereupon conduct the Tests itself or cause any of the Tests to be conducted in accordance with Article 12 and this Schedule K.

- Tests

  - Visual and physical test: The Authority’s Engineer shall conduct a visual and physical check of construction to determine that all works and equipment forming part thereof conform to the provisions of this Agreement.  The physical tests shall include all the tests specified in IRC code, manual and MORTH specifications for the road and Bridge works, 5th revision, and 1st July 2022.

  - Riding quality test: Riding quality of each lane of the carriageway shall be checked with the help of a calibrated bump integrator and the maximum permissible roughness for purposes of this Test shall be [2,000 (two thousand)] mm for each kilometer.

  - Tests for bridges: All major and minor bridges shall be subjected to the rebound hammer and ultrasonic pulse velocity tests, to be conducted in accordance with the procedure described in Special Report No. 17: 1996 of the IRC Highway Research Board on Nondestructive Testing Techniques, at two spots in every span, to be chosen at random by the Authority’s Engineer.  Bridges with a span of 15 (fifteen) meters or more shall also be subjected to load testing.

  - Other tests: The Authority’s Engineer may require the Contractor to carry out or cause to be carried additional tests, in accordance with Good Industry Practice, for determining the compliance of the Project Highway with Specifications and Standards.

  - Environmental audit: The Authority’s Engineer shall carry out a check to determine conformity of the Project Highway with the environmental requirements set forth in Applicable Laws and Applicable Permits.

2.6	Safety Audit: The Authority’s Engineer shall carry out or cause to be carried out, a safety audit to determine conformity of the Project Highway with the safety requirements and Good Industry Practice.

- Agency for conducting Tests

All Tests set forth in this Schedule-K shall be conducted by the Authority’s Engineer or such other agency or person as it may specify in consultation with the Authority.

4.	Completion Certificate

Upon successful completion of Tests, the Authority’s Engineer shall issue the Completion Certificate in accordance with the provisions of Article 12.

Schedule-L

(See Clause 12.2 and 12.4)

PROVISIONAL CERTIFICATE

I, …………….. (Name of the Authority’s Engineer), acting as the Authority’s Engineer, under and in accordance with the Agreement dated ………....….. (the “Agreement”), for construction of  the“construction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of Bhopalpatnam-Venktapuram-Warangal-Hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis ………………….(Name of Contractor), hereby certify that the Tests in accordance with Article 12 of the Agreement have been undertaken to determine compliance of the Project Highway with the provisions of the Agreement.

- Works that are incomplete on account of Time Extension have been specified in the Punch List appended hereto, and the Contractor has agreed and accepted that it shall complete all such works in the time and manner set forth in the Agreement. In addition, certain minor works are incomplete and these are not likely to cause material inconvenience to the Users of the Project Highway or affect their safety. The Contractor has agreed and accepted that as a condition of this Provisional Certificate, it shall complete such minor works within 30 (thirty) days hereof. These minor works have also been specified in the aforesaid Punch List.

- In view of the foregoing, I am satisfied that that Project Highway from .............................. can be safety and reliably placed in service of the users thereof, and in terms of the Agreement, the Project Highway is hereby provisionally declared fit for entry into operation on this the …day of……. 20 ………

ACCEPTED, SIGNED, SEALED		SIGNED, SEALED AND

AND DELIVERED                                              DELIVERED

For and on behalf of 				for and on behalf of

CONTRACTOR by                                           AUTHORITY’s ENGINEER by:

(Signature)                                                                     (Signature)

COMPLETION CERTIFICATE

- I, ………………….(Name of the Authority’s Engineer), acting as Authority’s Engineer, under and in accordance with the Agreement dated ……........…….(the “Agreement”), for construction of  the “construction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of Bhopalpatnam-Venktapuram-Warangal-Hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basisthrough ” through …………………. (Name of Contractor), hereby certify that the Tests in accordance with Article 12 of the Agreement have been successfully undertaken to determine compliance of the Project Highway with the provisions of the Agreement, and I am satisfied that the Project Highway can be safety and reliably placed in service of the Users thereof.

- It is certified that, in terms of the aforesaid Agreement, all works forming part of Project Highway have been completed, and the Project Highway is hereby declared fit for entry into operation on this the….…day of……      20……..

SIGNED, SEALED AND DELIVERED

For and on behalf of

The Authority’s Engineer by:

(Signature)

(Name)

(Designation)

(Address)

Schedule-M

(See Clauses 14.6., 15.2 and 19.7)

PAYMENT REDUCTION FOR NON-COMPLIANCE

- Payment reduction for non-compliance with the Maintenance Requirements

  - Monthly lump sum payments for maintenance shall be reduced in the case of non-compliance with the Maintenance Requirements set forth in Schedule-E.

  - Any deduction made on account of non-compliance with the maintenance Requirements shall not be paid even after compliance subsequently. The deduction shall continue to be made every month until compliance is done.

  - The Authority’s Engineer shall calculate the amount of payment reduction on the basis of weight age in percentage assigned to non-conforming items as given in Paragraph 2.

- Percentage reductions in lump sum payments

  - The following percentages shall govern the payment reduction:

| S. No. | Item/Defect/Deficiency | Percentage |
| --- | --- | --- |
| (a) | Carriageway/Pavement |  |
| (i) | Potholes, cracks, other surface defects | 15% |
| (ii) | Repairs of Edges, Rutting | 5% |
| (b) | Road, Embankment, Cuttings, Shoulders |  |
| (i) | Edge drop, inadequate cross fall, undulations, settlement, potholes, ponding, obstructions | 10% |
| (ii) | Deficient slopes, rain cuts, disturbed pitching, vegetation growth, pruning of trees | 5% |
| (c) | Bridges and Culverts |  |
| (i) | Desalting, cleaning. vegetation growth, damaged pitching, flooring, parapets, wearing course, footpaths, any damage to foundations | 20% |
| (ii) | Any Defects in superstructures, bearings and sub-structures | 10% |
| (iii) | Painting, repairs/replacement kerbs, railings, parapets, guideposts/crash barriers | 5% |
| (d) | Roadside Drains |  |
| (i) | Cleaning and repair of drains | 5% |
| (e) | Road Furniture |  |
| (i) | Cleaning, painting, replacement of road signs, delineators, road markings, 200 m/km/5th km stones | 5% |
| (f) | Miscellaneous Items |  |
| (i) | Removal of dead animals, broken down/accidental vehicles, fallen trees, road blockades or malfunctioning of mobile crane | 10% |
| (ii) | Any other Defects in accordance with paragraph 1. | 5% |
| (g) | Defects in Other Project Facilities | 5% |

2.2	The amount to be deducted from monthly lump-sum payment for non-compliance of particular item shall be calculated as under:

R=P/100 x M xL1/L

Where: P = Percentage of particular item//Defect/deficiency for deduction

M = Monthly lump-sum payment in accordance with the Bid

L1 = Non-complying length

L = Total length of the road,

R = Reduction (the amount to be deducted for noncompliance for a particular item/Defect/deficiency)

The total amount of reduction shall be arrived at by summation of reductions for such items/Defects/deficiency or non compliance.

For any Defect in a part of one kilometer, the non-conforming length shall be taken as one kilometer.

Schedule-N

(See Clause 18.1.1)

SELECTION OF AUTHORITY’S ENGINEER

1 	Selection of Authority’s Engineer

1.1	The provisions of the Model Request for Proposal for Selection of Technical Consultants, issued by the Ministry of Finance in May 2009, or any substitute thereof or ‘Guidelines for Employment of Consultants under Japanese ODA Loans’ or a combination of certain provisions thereof shall apply for selection of an experienced firm to discharge the functions and duties of an Authority’s Engineer.

1.2	The Authority shall invite Expression of Interest from Consulting Engineering firms or bodies corporate to undertake and perform the duties and functions set forth in Annexure-I of Schedule-N and thereupon shortlist qualified firms in accordance with pre-determined criteria.

1.3	The Authority shall invite the aforesaid shortlisted firms to submit their respective technical and financial offers, each in separate sealed cover and/or upload online. All the technical bids so received shall be opened and pursuant to the evaluation thereof, the Authority shall open the financial bids in respect of each shortlisted firm and the order of priority as among these firms shall be determined on the basis of a weighted evaluation where technical and financial score shall be assigned respective weights of 80:20.

1.4	In the event of termination of the Technical Consultants appointed in accordance with the provisions of above Paragraphs 1.1 to 1.3, the Authority shall appoint another firm of Technical Consu////]ltants forthwith and may engage a government-owned entity in accordance with the provisions of Paragraph 3 of this Schedule-N.

2 	Terms of Reference

The Terms of Reference for the Authority’s Engineer (the “TOR”) shall substantially conform with Annex 1 to this Schedule N.

3	Appointment of Government entity as Authority’s Engineer

Notwithstanding anything to the contrary contained in this Schedule, the Authority may in its discretion appoint a government-owned entity as the Authority’s Engineer; provided that such entity shall be a body corporate having as one of its primary functions the provision of consulting, advisory and supervisory services for engineering projects; provided further that a government-owned entity which is owned or controlled by the Authority shall not be eligible for appointment as Authority’s Engineer.

Annex – I

(Schedule - N)

TERMS OF REFERENCE FOR AUTHORITY’S ENGINEER

1. 	Scope

1.1	 These Terms of Reference (the “TOR”) for the Authority’s Engineer are being specified pursuant to the EPC Agreement dated........... (The “Agreement), which has been entered into between the Ministry of Road Transport and Highways (the “Authority”) and.......... (the “Contractor”) for “construction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of Bhopalpatnam-Venktapuram-Warangal-Hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis

” and a copy of which is annexed hereto and marked as Annex-A to form part of this TOR.

1.2 	The TOR shall apply to construction and maintenance of the Project Highway.

2. 	Definitions and interpretation

2.1 	The words and expressions beginning with or in capital letters and not defined herein but defined in the Agreement shall have, unless repugnant to the context, the meaning respectively assigned to them in the Agreement.

2.2 	References to Articles, Clauses and Schedules in this TOR shall, except where the context otherwise requires, be deemed to be references to the Articles, Clauses and Schedules of the Agreement, and references to Paragraphs shall be deemed to be references to Paragraphs of this TOR.

2.3 	The rules of interpretation stated in Clauses 1.2, 1.3 and 1.4 of the Agreement shall apply, mutatis mutandis, to this TOR.

3. 	General

  - The Authority’s Engineer shall discharge its duties in a fair, impartial and efficient manner, consistent with the highest standards of professional integrity and Good Industry Practice.

  - The Authority’s Engineer shall perform the duties and exercise the authority in accordance with the provisions of this Agreement, but subject to obtaining prior written approval of the Authority before determining:

(a)        Any Time extension;

(b) 	Any additional cost to be paid by the Authority to the Contractor;

(c) 	The Termination Payment; or

(d) 	Any other matter which is not specified in (a), (b) or (c) above and which creates an obligation or liability on either Party for a sum exceeding 0.2% of Contract Price.

  - The Authority’s Engineer shall submit regular periodic reports, at least once every month, to the Authority in respect of its duties and functions under this Agreement. Such reports shall be submitted by the Authority’s Engineer within 10 (ten) days of the beginning of every month.

3.4 	The Authority’s Engineer shall inform the Contractor of any delegation of its duties and responsibilities to its suitably qualified and experienced personnel; provided, however, that it shall not delegate the authority to refer any matter for the Authority’s prior approval in accordance with the provisions of Clause 18.2.

3.5	 The Authority’s Engineer shall aid and advise the Authority on any proposal for Change of Scope under Article 13.

3.6 	In the event of any disagreement between the Parties regarding the meaning, scope and nature of Good Industry Practice, as set forth in any provision of the Agreement, the authority’s Engineer shall specify such meaning, scope and nature by issuing a reasoned written statement relying on good industry practice and authentic literature.

4 	Construction Period

4.1	 During the Construction Period, the Authority’s Engineer shall review the Drawings furnished by the Contractor along with supporting data, including the geo-technical and hydrological investigations, characteristics of materials from borrow areas and quarry sites, topographical surveys, and the recommendations of the Safety Consultant in accordance with the provisions of Clause 10.1.6. The Authority’s Engineer shall complete such review and send its observations to the Authority and the Contractor within 15 (fifteen) days of receipt of such Drawings; provided, however that in case of a Major Bridge or Structure, the aforesaid period of 15 (fifteen) days may be extended up to 30 (thirty) days. In particular, such comments shall specify the conformity or otherwise of such Drawings with the Scope of the Project and Specifications and Standards.

4.2 	The Authority’s Engineer shall review any revised Drawings sent to it by the Contractor and furnish its comments within 10 (ten) days of receiving such Drawings.

4.3 	The Authority’s Engineer shall review the Quality Assurance Plan submitted by the Contractor and shall convey its comments to the Contractor within a period of 21 (twenty-one) days stating the modifications, if any, required thereto.

4.4 	The Authority’s Engineer shall complete the review of the methodology proposed to be adopted by the Contractor for executing the Works, and convey its comments to the Contractor within a period of 10 (ten) days from the date of receipt of the proposed methodology from the Contractor.

4.5 	The Authority’s Engineer shall grant written approval to the Contractor, where necessary, for interruption and diversion of the flow of traffic in the existing lane(s) of the Project Highway for purposes of maintenance during the Construction Period in accordance with the provisions of Clause 10.4.

4.6 	The Authority’s Engineer shall review the monthly progress report furnished by the Contractor and send its comments thereon to the Authority and the Contractor within 7 (seven) days of receipt of such report.

4.7 	The Authority’s Engineer shall inspect the Construction Works and the Project Highway and shall submit a monthly Inspection Report bringing out the results of inspections and the remedial action taken by the Contractor in respect of Defects or deficiencies. In particular, the Authority’s Engineer shall include in its Inspection Report, the compliance of the recommendations made by the Safety Consultant.

4.8 	The Authority’s Engineer shall conduct the pre-construction review of manufacturer's test reports and standard samples of manufactured Materials, and such other Materials as the Authority’s Engineer may require.

4.9 	For determining that the Works conform to Specifications and Standards, the

Authority’s Engineer shall require the Contractor to carry out, or cause to be carried out, tests at such time and frequency and in such manner as specified in the Agreement and in accordance with Good Industry Practice for quality assurance. For purposes of this Paragraph 4.9, the tests specified in the IRC Special Publication-11 (Handbook of Quality Control for Construction of Roads and Runways) and the Specifications for Road and Bridge Works issued by MORTH (the “Quality Control Manuals”) or any modification/substitution thereof shall be deemed to be tests conforming to Good Industry Practice for quality assurance.

4.10 	The Authority’s Engineer shall test check at least 20 (twenty) percent of the quantity or number of tests prescribed for each category or type of test for quality control by the Contractor.

4.11 	The timing of tests referred to in Paragraph 4.9, and the criteria for acceptance/ rejection of their results shall be determined by the Authority’s Engineer in accordance with the Quality Control Manuals. The tests shall be undertaken on a random sample basis and shall be in addition to, and independent of, the tests that may be carried out by the Contractor for its own quality assurance in accordance with Good Industry Practice.

4.12	 In the event that results of any tests conducted under Clause 11.10 establish any Defects or deficiencies in the Works, the Authority’s Engineer shall require the Contractor to carry out remedial measures.

4.13 	The Authority’s Engineer may instruct the Contractor to execute any work which is urgently required for the safety of the Project Highway, whether because of an accident, unforeseeable event or otherwise; provided that in case of any work required on account of a Force Majeure Event, the  provisions of Clause 21.6 shall apply.

4.14 	In the event that the Contractor fails to achieve any of the Project Milestones, the Authority’s Engineer shall undertake a review of the progress of construction and identify potential delays, if any. If the Authority’s Engineer shall determine that completion of the Project Highway is not feasible within the time specified in the Agreement, it shall require the Contractor to indicate within 15 (fifteen) days the steps proposed to be taken to expedite progress, and the period within which the Project Completion Date shall be achieved. Upon receipt of a report from the Contractor, the Authority’s Engineer shall review the same and send its comments to the Authority and the Contractor forthwith.

4.15 	The Authority’s Engineer shall obtain from the Contractor a copy of all the Contractor’s quality control records and documents before the Completion Certificate is issued pursuant to Clause 12.4.

4.16 	Authority’s Engineer may recommend to the Authority suspension of the whole or part of the Works if the work threatens the safety of the Users and pedestrians. After the Contractor has carried out remedial measure, the Authority’s Engineer shall inspect such remedial measures forthwith and make a report to the Authority recommending whether or not the suspension hereunder may be revoked.

4.17 	In the event that the Contractor carries out any remedial measures to secure the safety of suspended works and Users, and requires the Authority’s Engineer to inspect such works, the Authority’s Engineer shall inspect the suspended works within 3 (three) days of receiving such notice, and make a report to the Authority forthwith, recommending whether or not such suspension may be revoked by the Authority.

4.18 	The Authority’s Engineer shall carry out, or cause to be carried out, all the Tests specified in Schedule-K and issue a Completion Certificate or Provisional Certificate, as the case may be. For carrying out its functions under this Paragraph 4.18 and all matters incidental thereto, the Authority’s Engineer shall act under and in accordance with the provisions of Article 12 and Schedule-K.

5. 	Maintenance Period

5.1 	The Authority’s Engineer shall aid and advise the Contractor in the preparation of its monthly Maintenance Programmer and for this purpose carry out a joint monthly inspection with the Contractor.

5.2 	The Authority’s Engineer shall undertake regular inspections, at least once every month, to evaluate compliance with the Maintenance Requirements and submit a Maintenance Inspection Report to the Authority and the Contractor.

5.3 	The Authority’s Engineer shall specify the tests, if any, that the Contractor shall carry out, or cause to be carried out, for the purpose of determining that the Project Highway is in conformity with the Maintenance Requirements. It shall monitor and review the results of such tests and the remedial measures, if any, taken by the Contractor in this behalf.

5.4 	In respect of any defect or deficiency referred to in Paragraph 3 of Schedule- E, the Authority’s Engineer shall, in conformity with Good Industry Practice, specify the permissible limit of deviation or deterioration with reference to the Specifications and Standards and shall also specify the time limit for repair or rectification of any deviation or deterioration beyond the permissible limit.

5.5 	The Authority’s Engineer shall examine the request of the Contractor for closure of any lane(s) of the Project Highway for undertaking maintenance/repair thereof, and shall grant permission with such modifications, as it may deem necessary, within 5 (five) days of receiving a request from the Contractor. Upon expiry of the permitted period of closure, the Authority’s Engineer shall monitor the reopening of such lane(s), and in case of delay, determine the Damages payable by the Contractor to the Authority under Clause 14.5.

6	Determination of costs and time

6.1	The Authority’s Engineer shall determine the costs, and/or their reasonableness, that are required to be determined by it under the Agreement.

6.2 	The Authority’s Engineer shall determine the period of Time Extension that is required to be determined by it under the Agreement.

6.3 	The Authority’s Engineer shall consult each Party in every case of determination in accordance with the provisions of Clause 18.5.

7.	Payments

7.1 	The Authority’s Engineer shall withhold payments for the affected works for which the Contractor fails to revise and resubmit the Drawings to the Authority’s Engineer in accordance with the provisions of Clause 10.2.4 (d).

7.2 	Authority’s Engineer shall -

(a) 	within 10 (ten) days of receipt of the Stage Payment Statement from the Contractor pursuant to Clause 19.4, determine the amount due to the Contractor and recommend the release of 90 (ninety) percent of the amount so determined as part payment, pending issue of the Interim Payment Certificate; and

(b) 	within 15 (fifteen) days of the receipt of the Stage Payment Statement referred to in Clause 19.4, deliver to the Authority and the Contractor an Interim Payment Certificate certifying the amount due and payable to the Contractor, after adjustments in accordance with the provisions of Clause 19.10.

7.3	 The Authority’s Engineer shall, within 15 (fifteen) days of receipt of the Monthly Maintenance Statement from the Contractor pursuant to Clause 19.6, verify the Contractor’s monthly statement and certify the amount to be paid to the Contractor in accordance with the provisions of the Agreement.

7.4 	The Authority’s Engineer shall certify final payment within 30 (thirty) days of the receipt of the final payment statement of Maintenance in accordance with the provisions of Clause 19.16.

8.	Other duties and functions

The Authority’s Engineer shall perform all other duties and functions as specified in the Agreement.

9 	Miscellaneous

- A copy of all communications, comments, instructions, Drawings or Documents sent by the Authority's Engineer to the Contractor pursuant to this TOR, and a copy of all 	the test results with comments of the Authority's Engineer thereon, shall be furnished by the Authority's Engineer to the Authority forthwith.

- The Authority's Engineer shall retain at least one copy each of all Drawings and Documents received by it, including 'as-built' Drawings, and keep them in its safe custody.

9.3	Within 90 (ninety) days of the Project Completion Date, the Authority's Engineer shall obtain a complete set of as-built Drawings, in 2 (two) hard copies and in micro film form or in such other medium as may be acceptable to the Authority, reflecting the Project Highway as actually designed, engineered and constructed, including an as-built survey illustrating the layout of the Project Highway and setback lines, if any, of the buildings and structures forming part of Project Facilities; and shall hand them over to the Authority against receipt thereof.

9.4	The Authority's Engineer, if called upon by the Authority or the Contractor or both, shall mediate and assist the Parties in arriving at an amicable settlement of any Dispute between the Parties.

9.5	The Authority's Engineer shall inform the Authority and the Contractor of any event of Contractor's Default within one week of its occurrence.

SCHEDULE - O

(See Clauses 19.4.1, 19.6.1, and 19.8.1)

Forms of Payment Statements

- Stage Payment Statement for Works

The Stage Payment Statement for Works shall state:

(a) 	The estimated amount for the Works executed in accordance with Clause 19.3.1 subsequent to the last claim;

(b) 	Amounts reflecting adjustments in price for the aforesaid claim;

(c)	The estimated amount of each Change of Scope Order executed subsequent to the last claim;

(d) 	Amounts reflecting adjustment in price, if any, for (c) above in accordance with the provisions of Clause 13.2.3 (a);

(e)	Total of (a), (b), (c) and (d) above;

(f)	Deductions:

- Any amount to be deducted in accordance with the provisions of the Agreement except taxes;

- Any amount towards deduction of taxes; and

- Total of (i) and (ii) above.

(g)	Net claim: (e) – (f) (iii);

(h) 	The amounts received by the Contractor up to the last claim:

- For the Works executed (excluding Change of Scope orders);

- For Change of Scope Orders, and

- Taxes deducted

- Monthly Maintenance Payment Statement

The monthly Statement for Maintenance Payment shall state:

- the monthly payment admissible in accordance with the provisions of the agreement;

- the deductions for maintenance work not done;

- net payment for maintenance due, (a) minus (b);

- amounts reflecting adjustments in price under Clause 19.12; and

- amount towards deduction of taxes

- Contractor’s claim for Damages

Note: The Contractor shall submit its claims in a form acceptable to the Authority.

Monthly Maintenance Payment Statement

The monthly Statement for Maintenance Payment shall state:

- the monthly payment admissible in accordance with the provisions of the agreement;

- the deductions for maintenance work not done;

- net payment for maintenance due, (a) minus (b);

- amounts reflecting adjustments in price under Clause 19.12; and

- amount towards deduction of taxes

- Contractor’s claim for Damages

Note: The Contractor shall submit its claims in a form acceptable to the Authority.

Schedule-P

(See Clause 20.1)

INSURANCE

1. 	Insurance during Construction Period

1.1	The Contractor shall effect and maintain at its own cost, from the Appointed Date till the date of issue of the last Completion Certificate, the following insurances for any loss or damage occurring on account of Non Political Event of Force Majeure, malicious act, accidental damage, explosion, fire and terrorism:

(a) 	insurance of Works, Plant and Materials and an additional sum of [15 (fifteen)] per cent of such replacement cost to cover any additional costs of and incidental to the rectification of loss or damage including professional fees and the cost of demolishing and removing any part of the Works and of removing debris of whatsoever nature; and

(b) 	Insurance for the Contractor’s equipment and Documents brought onto the Site by the   Contractor, for a sum sufficient to provide for their replacement at the Site.

1.2	The insurance under paragraph 1.1 (a) and (b) above shall cover the authority and the Contractor against all loss or damage from whatsoever cause arising under paragraph 1.1 other than risks which are not insurable at commercial terms.

- Insurance for Contractor’s Defects Liability

The Contractor shall effect and maintain insurance cover for the works from the date of issue of the Completion Certificate until the end of the Defects Liability Period for any loss or damage for which the Contractor is liable and arises from a cause occurring prior to the issue of Completion Certificate. The Contractor shall also maintain other insurances for maximum sums as may be required under the Applicable Laws and in accordance with Good Industry Practice.

- Insurance against injury to persons and damage to property

3.1. 	The Contractor shall insure against each Party’s liability for any loss, damage, death or bodily injury which may occur to any physical property (except things insured under Paragraph l and 2 of this Schedule or to any person (except persons insured under Clause 20.9), which may arise out of the Contractor’s performance of this Agreement. This insurance shall be for a limit per occurrence of not less than the amount stated below with no limit on the number of occurrences. The insurance cover shall be not less than: Rs. [*****]

3.2 	The insurance shall be extended to cover liability for all loss and damage to the Authority’s property arising out of the Contractor’s performance of this Agreement excluding:

- the Authority’s right to have the construction works executed on, over, under, in or through any land, and to occupy this land for the Works; and

- Damage which is and unavoidable result of the Contractor’s obligations to execute the Works.

- Insurance to be in joint names

The insurance under paragraphs 1 to 3 above shall be in the joint names of the Contractor and the Authority.

SCHEDULE-Q

(See Clause 14.10)

Tests on Completion of Maintenance Period

1. Riding Quality test:

Riding quality test: Riding quality of each lane of the carriageway shall be checked with the help of a calibrated bump integrator and the maximum permissible roughness for purposes of this Test shall be 2,500 (two thousand five hundred) mm for each kilometer.

2. Visual and physical test:

The Authority’s Engineer shall conduct a visual and physical check of construction to determine that all works and equipment forming part thereof conform to the provisions of this Agreement. The physical tests shall include measurement of cracking, rutting, stripping and potholes and the permissible values are given below: • Area of cracking not more than 2 % area

• Area of rutting with rut depth more than 10 mm - not more than 1 …. % area

• Area of stripping: not more than 2 % area

• Area of potholes: Nil

• Edge drop – Shall not be more than 15 mm

SCHEDULE-R

(See Clause 14.10)

Taking Over Certificate

I, ……………………. (Name and designation of the Authority’s representative) under and in accordance with the Agreement dated……........…… (the “Agreement”), for “Reconstruction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of Bhopalpatnam-Venktapuram-Warangal-Hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis

”………………….  (Name  of  Contractor), hereby certify that the Tests on completion of Maintenance Period in accordance with Article 14 of the Agreement have been successfully undertaken to determine compliance of the Project Highway with the provisions of the Agreement and I hereby certify that the Authority has Taken over the Project Highway from the Contractor on this day ...............

SIGNED, SEALED AND DELIVERED

(Signature)

(Name of Authority’s Engineer)

(Address)

SCHEDULE-S

(See Clause 17.7.2)

Performance Certificate

I, ……………………. (Name and designation of the Authority’s representative) under and in accordance with the Agreement dated ………......… (the “Agreement”), for [construction and maintenance of the “Reconstruction of two lane road of sumerged length km 5.90 to 7.575 and km 32.275 to 33.00 of Bhopalpatnam-Venktapuram-Warangal-Hyderabad road of NH-163 in the State of Chhattisgarh through EPC Basis

…………………. (Name of Contractor), hereby certify that the Contractor has discharged all its obligations under the Agreement and in accordance with Article 17 of the Agreement I hereby issue Performance Certificate to the Contractor on this day.........

SIGNED, SEALED AND DELIVERED

(Signature)

(Name of Authority’s Engineer)

(Address)

SCHEDULE-T

(See Clause 19.1.6)

| Name of Currency | A Amount of Currency | B Rate of Exchange* (Local Currency per Unit of Foreign Currency) | C Local Currency Equivalent | D Percentage of Net Bid Price (NTP) (100 x C) / NTP |
| --- | --- | --- | --- | --- |
| Local Currency (Indian Rupees) |  |  |  |  |
| Foreign Currency 1 (Japanese Yen) |  |  |  |  |
| Foreign Currency 2 (US Dollar) |  |  |  |  |
| Net Bid Price |  |  |  | 100.00 |
| * The fixed rates of exchange shall be the selling rates 28 days prior to the deadline for submission of bids published by the Reserve Bank of India. |  |  |  |  |
| 1. Change in scope would require agreement between parties on currency. |  |  |  |  |
| 2. Regarding damages by the Authority, financing charges for a payment delays will be in corresponding currency amounts. |  |  |  |  |
| 3. Delay damages will be recovered in currencies in proportion which in which contract price is payable. |  |  |  |  |

NOTE:The contractor shall mark the Row with boundary stones, in accordance with the provision of manual and IRC 25, immediately as the land is handed over to the contractor by the Authority and the Row shall be verified and cross checked by the contractor in consultation with Authority, Authority Engineer and District Administration, prior to commencement of works.

$ Insert date being 2 (two) years from the date of issuance of this Guarantee (in accordance with Clause 7.2 of the Agreement).

$The Guarantee Amount should be equivalent to 110% of the value of the applicable installment.

$Insert a date being 90 (ninety) days after the end of        ----------- from the date of payment of the Advance payment to the Contractor (in accordance with Clause 19.2 of the Agreement).