### Schedules

Schedule-A

(See Clauses 2.1 and 8.1)

# Site of the Project

### 1	The Site

- Site of the [Two-Lane] Project Highway existing road 7.00m width carriageway NH-221 (New NH-30) include the land, buildings, structures and road works as described in Annex-I of this Schedule-A.

- The dates of handing over the Right of Way to the Contractor are specified in Annex-II of this Schedule-A.

- An inventory of the Site including the land, buildings, structures, road works, trees and any other immovable property on, or attached to, the Site shall be prepared jointly by the Authority Representative and the Contractor, and such inventory shall form part of the memorandum referred to in Clause 8.2 (i) of this Agreement.

- The alignment plans of the Project Highway are specified in Annex-III. In the case of sections where no modification in the existing alignment of the Project Highway is contemplated, the alignment plan has not been provided. Alignment plans have only been given for sections where the existing alignment is proposed to be upgraded. The proposed profile of the Project Highways shall be followed by the contractor with minimum FRL as indicated in the alignment plan/Attached GAD. The Contractor, however, improve/upgrade the Road Profile as indicated in Annex-III based on site/design requirement.

- The status of the environment clearances obtained or awaited is given in Annex-IV.

Annex – I (Schedule-A)

#### Site

### Site

The Site of the [Two-Lane] Project Highway comprises the section of [National Highway 221(New NH-30) commencing from Construction of 4 nos. Bridges at Km 47.000 (Jhiram nalla), Km. 123.000 (Kerlapal nalla), Km. 127.800 (Bodaguda nalla) and Km. 137.400 (Dubbatota nalla) on NH-30 (Old NH-221) Jagdalpur-Sukma-Konta road in the state of Chhattisgarh.

***. The land, carriageway and structures comprising the Site are described below.

### Land

The Site of the Project Highway comprises the land (sum total of land already in possession and land to be possessed) as described below: :(The Project Highway is proposed in the new alignment)

| S. No. | Chainage (km) |  | Right of Way (m) | Remarks |
| --- | --- | --- | --- | --- |
|  | From | To |  |  |
| 1. | Km. 46.850 | Km. 47.110 | 30.00 m |  |
| 2. | Km. 122.870 | Km. 123.160 | 30.00 m |  |
| 3. | Km. 127.660 | Km. 128.060 | 30.00 m |  |
| 4. | Km. 137.300 | Km. 137.540 | 30.00 m |  |

### Carriageway

The present carriageway of the Project Highway is 7.00m of NH-221(New NH-30) under Chhattisgarh .

The type of the existing pavement is flexible Road condition is good.

- Major Bridges

The Site includes the following Major Bridges:

| S. No. | Chainage (km) | Type of Structure |  |  | No. of Spans with span length (m) | Width (m) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Sub- structure | Super- structure |  |  |
| 1 | 47.00 | Open Foundation | Stone masonry | R.C.C Solid Slab | 4 Span x 10m | 7.80 Mt. |
| 2 | 127.800 | Open Foundation | Stone masonry | R.C.C Solid Slab | 5 Span x 8.50m | 7.00 Mt. |

### Road over-bridges (ROB)/ Road under-bridges(RUB)

The Site includes the following ROB (road over railway line)/RUB (road under railway line):

| S. No. | Chainage (km) | Type of Structure |  | No. of Spans with span length (m) | Width (m) | ROB/ RUB |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Superstructure |  |  |  |
| NIL |  |  |  |  |  |  |

### Grade separators

The Site includes the following grade separators:

| S. No. | Chainage (km) | Type of Structure |  | Remark |  |
| --- | --- | --- | --- | --- | --- |
|  |  | LOCATION | Superstructure |  |  |
| NIL |  |  |  |  |  |

### Minor bridges

The Site includes the following minor bridges:

| S. No. | Chainage (km) | Type of Structure |  |  | No. of Spans with span length (m) | Width (m) |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Foundation | Sub- structure | Super- structure |  |  |
| 1 | 123.000 | Open Foundation | Stone masonry | R.C.C Solid Slab | 5 Span x 7.20m | 7.00 Mt. |
| 2 | 137.400 | Open Foundation | Stone masonry | R.C.C Solid Slab | 5 Span x 5.40m | 7.80 Mt. |

### Railway level crossings

The Site includes the following railway level crossings:

| S. No. | Location (km) | Remarks |
| --- | --- | --- |
| NIL |  |  |

- Underpasses (vehicular, non vehicular) The Site includes the following underpasses:

| S. No. | Chainage (km) | Type of Structure | No. of Spans with span length (m) | Width (m) |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

### Culverts

The Site has the following culverts:

| S. No. | Chainage (km) | Type of Culvert | Span /Opening with span length (m) | Width (m) |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

### Bus bays

The details of bus bays on the Site are as follows:

| S. No. | Chainage (km) | Length (m) | Left Hand Side | Right Hand Side |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

### Truck Lay byes

The details of truck lay byes are as follows:

| S. No. | Chainage (km) | Length (m) | Left Hand Side | Right Hand Side |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

### Road side drains

The details of the roadside drains are as follows:

| S. No. | Location |  | Type |  |
| --- | --- | --- | --- | --- |
|  | From km | to km | Masonry/cc (Pucca) | Earthen (Kutcha) |
| NIL |  |  |  |  |

### Major junctions

The details of major junctions are as follows:

| S. No. | Location |  | At grade | Separated | Category of Cross Road |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From km | to km |  |  | NH | SH | MDR | Others |
| NIL |  |  |  |  |  |  |  |  |

(NH: National Highway, SH: State Highway, MDR: Major District Road)

### Minor junctions

The details of the minor junctions are as follows:

| S. No. | Location |  | Type |  |
| --- | --- | --- | --- | --- |
|  | From km | To km | T -junction | Cross road |
| NIL |  |  |  |  |

### Bypasses

The details of the existing road sections proposed to be bypassed are as follows:

| S. No. | Name of bypass (town) | Chainage (km) From km to km | Length (in Km) |
| --- | --- | --- | --- |
| NIL |  |  |  |

### [17.	Other structures]

[Provide details of other structures, if any.]

Sheet-I (Annexure-I to Schedule-A)

## Electrical utitities

The site includes the following electrical utilities: -

- Extra High-Tension Lines (ENT Lines) *

| S. No | Chainage |  | Length(in Km) |  |  |  | Crossings |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From | To |  |  |  |  |  |  |  |  |
| - |  |  |  |  |  |  |  |  |  |  |

- High Tension/Low Tension Lices (HT/LT Lines) *

| S. NO | Chainage |  | Length(in Km) |  |  | Crossings |  |  | Transformers |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From | To | 33KV | 11KV | LT | 33KV | 11KV | LT | No | Capacity |
| 1 | 46.850 | 47.110 | 8 |  |  |  |  |  |  |  |

## Public Health utilities (Water/Sewage Pipe Lines) ” The site includes the following Public Health utilities: -

| S. **O | Chainage |  | Length(in Km) |  |  |  | Crossings |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From | To | Water Supply line |  | Sewage line |  | Water Supply line |  | Sewage line |  |
|  |  |  | With Pumping | With Gravity flow | With Pumping | With Gravity Flow | With Pumping y | With Gravit flow | With Pumping | With Gravity Flow |
| NIL |  |  |  |  |  |  |  |  |  |  |

## (iii) CREDA utilities (Solor Street Light Pole) ” The site includes the following CREDA utilities: -

| S. No. | Chainage |  | Length(in Km) |  |  |  | Crossings |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From | To | Solor Street Light Pole |  | Solar Mast |  | Solor Street Light Pole |  | Solar Mast |  |
|  |  |  | 200W | 300W | 800W | 1200W | 200W | 300W | 800W | 1200W |
| 1 | 122.870 | 123.160 | 6 | - | - | - | - | - | - | - |

### Annex – II

(As per Clause 8.3 (i)) (Schedule-A)

### Dates for providing Right of Way of Construction Zone

The dates on which the Authority shall provide Right of Way of Construction Zone to the Contractor on different stretches of the Site are stated below:

| S.no | Existing Chainage | Design chainage |  | Length | ROW | Date of providing Right of way |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Km. 46.850 to Km. 47.110 | Km. 46.850 to Km. 47.110 |  | 0.260 Km. | 30.00 m | As on handing over of the site day of appointed date |  |
| 2 | Km. 122.870 to Km. 123.160 | Km. 122.870 to Km. 123.160 |  | 0.290 Km. | 30.00 m | As on handing over of the site day of appointed date |  |
| 3 | Km. 127.660 to Km. 128.060 | Km. 127.660 to Km. 128.060 |  | 0.400 Km. | 30.00 m | As on handing over of the site day of appointed date |  |
| 4 | Km. 137.300 to Km. 137.540 | Km. 137.300 to Km. 137.540 |  | 0.240Km. | 30.00 m | As on handing over of the site day of appointed date |  |
|  |  |  | 1.190 Km. |  |  |  |

Annex - III (Schedule-A) Alignment Plans

The existing alignment of the Project Highway shall followed for Construction of 2-Lane Major/Minor Bridges along with approaches on both side as per the attached alignment plan (refer Drawing Volume)

- The alignment of the Project Highway is enclosed in alignment plan. Finished road level indicated in the alignment plan/Attached GAD shall be followed by the contractor as minimum FRL. In any case, the finished road level of the project highway shall not be less than those indicated in the alignment plan. The contractor shall, however, improve/upgrade the Road profile as indicated in Annex-III based on site/design requirement.

- The Contractor shall provide traffic signage on site as indicated in Schedule – B.

- Rove/upgrade upon the traffic signage plan as indicated in Annex-III based on site/design requirement as per the relevant specifications/IRCCodes/Manual.

1. Km. 47.000 (Jhiram Nalla)

2. Km. 123.000 (Kerlapal Nalla)

3. Km. 127.800 (Bodaguda Nalha)

4. Km. 137.400 (Dubbatota Nalla)

Annex – IV (Schedule-A)

### Environment Clearances

The following environment clearances have been obtained: NA

The following environment clearances are awaited: NA

Appendix A-I

Index Map of Project Highway

INDIA 								1. Km. 47.000 (Jhiram Nalla)

2. Km. 127.800 (Bodaguda Nalla)			3. Km. 137.400 (Dubbatota Nalla)

4. Km. 123.000 (Kerlapal Nalla)

Fig- LINE DIAGRA

Annex – V

(Schedule-A)

| S.no | Existing chainage | Design chainage |
| --- | --- | --- |
| 1 | Km. 46.850 to Km. 47.110 | Km. 46.850 to Km. 47.110 |
| 2 | Km. 122.870 to Km. 123.160 | Km. 122.870 to Km. 123.160 |
| 3 | Km. 127.660 to Km. 128.060 | Km. 127.660 to Km. 128.060 |
| 4 | Km. 137.300 to Km. 137.540 | Km. 137.300 to Km. 137.540 |

Schedule - B (See Clause 2.1)

# Development of the Project Highway

### Development of the Project Highway

Development of the Project Highway shall include design and construction of the Project Highway as described in this Schedule-B and in Schedule-C.

### [Rehabilitation and augmentation]

Rehabilitation and augmentation shall include Bridge of the Project Highway as described in Annex-I of this Schedule-B and in Schedule-C

### Specifications and Standards

The Project Highway shall be designed and constructed in conformity with the Specifications and Standards specified in Annex-I of Schedule-D.

Annex – I (Schedule-B)

### Description of [Construction of 4 nos. Bridges at Km 47.000 (Jhiram nalla), Km. 123.000 (Kerlapal nalla), Km. 127.800 (Bodaguda nalla) and Km. 137.400 (Dubbatota nalla) on NH-30 (Old NH-221) Jagdalpur-Sukma-Konta road in the state of Chhattisgarh on EPC Mode]$

### New Construction as Major Bridges of the existing Highway

- The Project Highway shall follow the existing alignment unless otherwise specified by the Authority and shown in the alignment plans specified in Annex-III of Schedule-A. Geometric deficiencies, if any, in the existing horizontal and vertical profiles shall be corrected as per the prescribed standards for [plain/rolling] terrain to the extent land is available.

- Width of Carriageway

  - Two-Laning [with/without] paved shoulders shall be undertaken. The paved carriageway shall be [16 m] wide in accordance with the typical cross sections drawings in the Manual.

Provided that in the built-up areas [refer to paragraphs 2.1 (ii) (a) of the Manual and provide necessary details]: the width of the carriageway shall be as specified in the following table:

(A) Major Bridge Portion

1. Km. 47.000 (Jhiram Nalla)

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 47.000 | 80m | 16 m | TCS 1 |

Both side Approach Road

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 47.000 (Jagdalpur site) | 30 m | 16 m + 12 m 2 | TCS 2 (i) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 10 m | 7 m |  |
| 2 | 47.000 (Sukma site) | 30 m | 16 m + 12 m 2 | TCS 2 (i) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 50 m | 7 m |  |

2. Km. 127.800 (Bodaguda Nalla)

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 127.800 | 60m | 16 m | TCS 1 |

Both side Approach Road

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 127.800 (Sukma site) | 30 m | 16 m + 12 m 2 | TCS 2 (ii) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 80 m | 7 m |  |
| 2 | 127.800 (Konta site) | 30 m | 16 m + 12 m 2 | TCS 2 (ii) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 140 m | 7 m |  |

(B) Minor Bridge Portion

1. Km. 123.000 (Kerlapal Nalla)

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 123.000 | 40m | 16 m | TCS 1 |

Both side Approach Road

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 123.000 (Sukma site) | 30 m | 16 m + 12 m 2 | TCS 2 (ii) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 70 m | 7 m |  |
| 2 | 123.000 (Konta site) | 30 m | 16 m + 12 m 2 | TCS 2 (ii) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 60 m | 7 m |  |

2. Km. 137.400 (Dubbatota Nalla)

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 137.400 | 40m | 16 m | TCS 1 |

Both side Approach Road

| Sl. No. | Location (km to km) | Length | Carriageway Width (m) | Typical cross section |
| --- | --- | --- | --- | --- |
| 1 | 137.400 (Sukma site) | 30 m | 16 m + 12 m 2 | TCS 2 (ii) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 60 m | 7 m |  |
| 2 | 137.400 (Konta site) | 30 m | 16 m + 12 m 2 | TCS 2 (ii) & TCS 2(iii) |
|  |  | 30 m | 12 m + 7 m 2 |  |
|  |  | 60 m | 7 m |  |

### Geometric Design and General Features

- General

Geometric design and general features of the Project Highway shall be in accordance with Section 2 of the Manual.

- Design speed

The design speed shall be the minimum design speed of [100 km per hr for plain/ rolling terrain].

- Improvement of the existing road geometrics

In the following sections, where improvement of the existing road geometrics to the prescribed standards is not possible, the existing road geometrics shall be improved to the extent possible within the given right of way and proper road signs and safety measures shall be provided.

- Right of Way

Details of the Right of Way are given in Annex II of Schedule-A.

- Type of shoulders

Design and specifications of granular material shall conform to the specifications for road and bridge work -MORTH Clause 407 and IRC SP 84-2014

| Sl. No. | Stretch (from km to km) | Type of deficiency | Remarks |
| --- | --- | --- | --- |
| 1 | Km. 47.000 (Jagdalpur Side) | 70 m | TCS 3 |
| 2 | Km. 47.000 (Sukma Side) | 110 m | TCS 3 |
| 3 | Km. 123.000 (Sukma Side) | 130 m | TCS 3 |
| 4 | Km. 123.000 (Konta Side) | 120 m | TCS 3 |
| 5 | Km. 127.800 (Sukma Side) | 140 m | TCS 3 |
| 6 | Km. 127.800 (Konta Side) | 200 m | TCS 3 |
| 7 | Km. 137.400 (Sukma Side) | 100 m | TCS 3 |
| 8 | Km. 137.400 (Konta Side) | 100 m | TCS 3 |

- Lateral and vertical clearances at underpasses

  - Lateral and	vertical	clearances	at	underpasses	and	provision	of guardrails/crash barriers shall be as per the provision of relevant Manual.

  - Lateral clearance: The width of the opening at the underpasses shall be as follows:

| Sl. No. | Location (Chainage) (from km to km) | Span/ opening (m) | Remarks |
| --- | --- | --- | --- |
| NIL |  |  |  |

- Lateral and vertical clearances at overpasses

  - Lateral and vertical clearances at overpasses shall be as per the provision of relevant Manual.

  - Lateral clearance: The width of the opening at the overpasses shall be as follows:

| Sl. No. | Location (Chainage) (from km to km) | Span/ opening (m) | Remarks |
| --- | --- | --- | --- |
| NIL |  |  |  |

- Service roads

Service roads shall be constructed/Overlaid at the locations and for the lengths indicated below:

| Sl. No. | Design Chainage From Km to km | Right hand side (RHS)/Left hand side (LHS)/ or Both sides | Length (km) of service road | Remarks |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

- Grade separated structures

  - Grade separated structures shall be provided as per provision of the relevant Manual. The requisite particulars are given below:

[Refer to the provision of relevant Manual and provide details]

| Sl. No. | Location of structure | Length (m) | Number and length of spans (m) | Approach gradient | Remarks, if any |
| --- | --- | --- | --- | --- | --- |
| NIL |  |  |  |  |  |

  - In the case of grade separated structures, the type of structure and the level of the Project Highway and the cross roads shall be as follows: [Refer to the provision of relevant Manual and specify the type of vehicular under pass/ overpass structure and whether the cross road is to be carried at the existing level, raised or lowered]

| Sl. No. | Location | Type of structure Length (m) | Cross road at |  |  | Remarks, if any |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Existing Level | Raised Level | Lowered Level |  |
| NIL |  |  |  |  |  |  |

- Cattle and pedestrian underpass/overpass

Cattle and pedestrian underpass/ overpass shall be constructed as follows: [Refer to the provision of relevant Manual and specify the requirements of cattle and pedestrian underpass/ overpass]

| Sl. No. | Location | Type of crossing |
| --- | --- | --- |
| NIL |  |  |

- Typical cross-sections of the Project Highway

Following Typical Cross section shall be followed throughout the project stretch:-

  - TCS-1 for Major/Minor Bridge Construction Portion

(b)  TCS 2 (i) For Flexible Pavement

(c) TCS 2 (ii) For Rigid Pavement

(D) TCS 2(iii) Plan for Approach Road

(e) TCS-3 for Shoulder

Note: -	 The Granular Material for construction of shoulder shall be used.

Note:-

- The Above Typical Cross Section may vary with respect to the site conditions

- The Cross Section Schedule given in above table is indicative and stretches may increase or decrease depending upon field conditions however any increase or decrease in length upto (+-) 10 %shall not be treated as change of scope.

- Intersections and Grade Separators

All intersections and grade separators shall be as per the provision of relevant Manual. Existing intersections which are deficient shall be improved to the prescribed standards.

Properly designed intersections shall be provided at the locations and of the types and features given in the tables below:

- At-grade intersections As per IRC:SP:73-2015

| Sl. No. | Location of intersection | Type of intersection | Other features |
| --- | --- | --- | --- |
| NIL |  |  |  |

- Grade separated intersection with/without ramps

| Sl. No. | Location | Salient features | Minimum length of viaduct to be provided | Road to be carried over/under the structures |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

### Road Embankment and Cut Section

- Widening and improvement of the existing road embankment/cuttings and construction of new road embankment/ cuttings shall conform to the Specifications and Standards given in Section 4 of the Manual and the specified cross sectional details. Deficiencies in the plan and profile of the existing road shall be corrected.

- Raising of the existing road [Refer to the provision of relevant Manual and specify sections to be raised]

The existing road shall be raised in the following sections:

| Sl. No. | Section (from km to km) | Length | Extent of raising [Top of finished road level] |
| --- | --- | --- | --- |
| NIL |  |  |  |

### Pavement Design

- Pavement design shall be carried out in accordance with the provision of relevant Manual.

- Type of pavement :- Flexible Pavement

- Design requirements

  - Design Period and strategy

Flexible pavement shall be designed for a minimum design period of 20 years. Stage construction shall not be permitted.

  - Design Parameters

Notwithstanding anything to the contrary contained in this Agreement or the Manual, the Contractor shall design the pavement for a design traffic of 30 Million Standard Axles

The minimum thickness of crust of flexible pavement to be adopted shall be as follows:-

| S. No. | Crust Composition of the Flexible/Rigid Pavement (Carriageway) |  |  | Remark |
| --- | --- | --- | --- | --- |
|  | Item | for BT | for CC |  |
| 1. | GSB | 300mm | 300mm |  |
| 2. | W.M.M. | 250mm | 250mm |  |
| 3. | DLC |  | 100mm |  |
| 4. | PQC |  | 300mm |  |
| 5. | D.B.M | 100mm |  |  |
| 6. | B.C | 40 mm |  |  |
|  | Total | 690mm | 950mm |  |

Following provisions for pavement construction shall be adopted.

- The minimum DBM thickness of 100 mm shall be maintained at every section (longitudinal & cross) of the pavement after providing 2.5% camber across the road.

- Paving Bitumen of VG-40 Grade confirming to IS:73-2012 shall be used

- New construction of stretches:-

The following stretches of the new construction of ROB/Bypass, these shall be designed as new pavement.

| Sl. No. | Stretch From km to km | Length | Remarks |
| --- | --- | --- | --- |
| NIL |  |  |  |

### Roadside Drainage

Drainage system including surface and subsurface drains for the Project Highway shall be provided as per design specification and standards.

- RCC Drain:-The Longitudinal drains shall be designed and provided at the location specified below.

| Sl No. | Chainage |  | Side | Length (m) | Drain size |  |
| --- | --- | --- | --- | --- | --- | --- |
|  | From | To |  |  | Width | Height |
|  |  |  | Nil |  |  |  |

### Toe Wall: - Toe wall shall be provided as per design, guidelines given in relevant clause of MoRTH specification at following locations: - drawing given schedule-I

| Sl No. | Chainage | Sides | Length (m) | Wall size |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Width | Height |
| 1 | 47.000 | Both side | 2 x 50m 2 x 80m | 0.30 Mt | 0.80 Mt above O.G.L. |
| 2 | 127.800 | Both side | 4X 70m | 0.30 Mt | 0.80 Mt above O.G.L. |
| 3 | 137.400 | Both side | 4X 20m | 0.30 Mt | 0.80 Mt above O.G.L. |

### (iii)Retaining wall   : - Retaining wall shall be provided as per design, guidelines given in relevant clause of MoRTH specification at following locations

| Sl No. | Chainage | Sides | Length (m) | Wall size |  |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Width | Height |
|  |  | NIL |  |  |  |

Note:- The provision of Toe wall and Retaining wall is minimum. If length/height is required to be increased as per site conditions, the length/height shall be increase as per requirement in accordance with manual, in consultation with the Authority' Engineer. No Change of Scope will be allowed.

### Design of Structures

- General

  - All bridges, culverts and structures shall be designed and constructed in accordance with the provision of relevant Manual and shall conform to the cross- sectional features and other details specified therein.

  - Width of the carriageway of new bridges and structures shall be as follows:

| Sl. No. | Bridge at km | Length | Width of carriageway and cross-sectional features* (Refer Drawing Volume) |
| --- | --- | --- | --- |
| 1. | 47.000 | 80m | TCS-1 |
| 2. | 123.000 | 40m | TCS-1 |
| 3. | 127.800 | 60m | TCS-1 |
| 4. | 137.800 | 40m | TCS-1 |

  - The following structures shall be provided with footpaths:

| Sl. No. | Location at km | Length | Remarks (Refer Drawing Volume) |
| --- | --- | --- | --- |
| NIL |  |  |  |

  - All bridges shall be high-level bridge

  - The following structures shall be designed to carry utility services specified in table below:

| Sl. No. | Bridge at km | Utility service to be carried | Remarks |
| --- | --- | --- | --- |
| NIL |  |  |  |

  - Cross-section of the new culverts and bridges at deck level for the Project Highway shall conform to the typical cross-sections given in the provision of relevant Manual.

- Culverts

  - Overall width of all culverts shall be equal to the roadway width of the approaches.

  - Reconstruction of existing culverts:

The existing culverts at the following locations shall be re-constructed as new culverts:

| Sl. No. | Culvert location | Span/Opening (m) | Remarks, if any* |
| --- | --- | --- | --- |
| NIL |  |  |  |

  - Widening of existing culverts:

All existing culverts which are not to be reconstructed shall be widened tothe roadway width of the Project Highway as per the typical cross section given in the provision of relevant Manual. Repairs and strengthening of existing structures where required shall be carried out.

| Sl. No. | Culvert location | Type, span, height and width of existing culvert (m) | Repairs to be carried out [specify] |
| --- | --- | --- | --- |
| NIL |  |  |  |

  - Additional new culverts shall be constructed as per particulars given in the table below:

| Sl No. | Culvert location | Span/Opening (m) |
| --- | --- | --- |
| 1. | As per requirement in Additional Connecting Road Portion |  |
| 2. |  |  |
| 3. |  |  |

  - Repairs/replacements of railing/parapets, flooring and protection works of the existing culverts shall be undertaken as follows:

[Refer to the provision of relevant Manual and provide details]

| Sl. No. | Location at km | Type of repair required |
| --- | --- | --- |
| NIL |  |  |

  - Floor protection works shall be as specified in the relevant IRC Codes and Specifications.

- Bridges

  - Existing bridges to be re-constructed/widened

[(i)	The existing bridges at the following locations shall be re-constructed as new Structure

| Sl. No. | Bridge location (km) | Salient details of existing bridge | Adequacy or otherwise of the existing waterway, vertical clearance, etc* | Remarks |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

(ii)	The following narrow bridges shall be widened:

| Sl. No. | Location (km) | Existing width (m) | Extent of widening (m) | Cross-section at deck level for widening @ |
| --- | --- | --- | --- | --- |
| NIL |  |  |  |  |

@ Attach cross-section

  - Additional new bridges

[Specify additional new bridges if required, and attach GAD]

New bridges at the following locations on the Project Highway shall be constructed. GADs for the new bridges are attached in the drawings folder.

| Sl. No. | Existing Chainage (Km.) | Design Chainage (Km.) | Proposed Structure Type | Proposed Span Arrangement (Mt) | Overall Length (Mt) | Width Of Structure |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Km. 46.850 to Km. 47.110 | Km. 46.850 to Km. 47.110 | High Level Bridge | 4x20 m | 80 m | 16.00 m |
| 2 | Km. 122.870 to Km. 123.160 | Km. 122.870 to Km. 123.160 | High Level Bridge | 2x20 m | 40 m | 16.00 m |
| 3 | Km. 127.660 to Km. 128.060 | Km. 127.660 to Km. 128.060 | High Level Bridge | 3x20 m | 60 m | 16.00 m |
| 4 | Km. 137.300 to Km. 137.540 | Km. 137.300 to Km. 137.540 | High Level Bridge | 2x20 m | 40 m | 16.00 m |

  - The railings of existing bridges shall be replaced by crash barriers at the following locations:

[Refer to the provision of relevant Manual and provide details:]

| Sl. No. | Location at km | Remarks |
| --- | --- | --- |
| NIL |  |  |

  - Repairs/replacements of railing/parapets of the existing bridges shall be undertaken as follows:

[Refer to the provision of relevant Manual and provide details]

| Sl. No. | Location at km | Remarks |
| --- | --- | --- |
| NIL |  |  |

  - Drainage system for bridge decks

An effective drainage system for bridge decks shall be provided as specified in the provision of relevant Manual

  - Structures in marine environment:-NIL

- Rail-road bridges

  - Design, construction and detailing of ROB/RUB shall be as specified in the provision of relevant Manual. [Refer to the provision of relevant Manual and specify modification, if any]

  - Road over-bridges

Road over-bridges (road over rail) shall be provided at the following level crossings, as per GAD drawings attached:

| Sl. No. | Location of Level crossing (Chainage km) | Length of bridge (m) |
| --- | --- | --- |
|  | NIL |  |

  - Road under-bridges

Road under-bridges (road under railway line) shall be provided at the following level crossings, as per GAD drawings attached:

| Sl. | Location of Level crossing (Chainage | Number and length of |
| --- | --- | --- |
| No. | km) | span (m) |
| NIL |  |  |

- Grade separated structures

The grade separated structures shall be provided at the locations and of the type and length specified in paragraphs 2 (ix) and 3 of this Annex-I.

- Repairs and strengthening of bridges and structures

The existing bridges and structures to be repaired/strengthened, and the nature and extent of repairs /strengthening required are given below:

  - Bridges

| Sl. No. | Location of bridge (km) | Nature and extent of repairs /strengthening to be carried out |
| --- | --- | --- |
| NIL |  |  |

  - ROB /RUB

| Sl. No. | Location of ROB/RUB (km) | Nature and extent of repairs /strengthening to be carried out |
| --- | --- | --- |
| NIL |  |  |

  - Overpasses/Underpasses and other structures

| Sl. No. | Location of Structure (km) | Nature and extent of repairs /strengthening to be carried out |
| --- | --- | --- |
| NIL |  |  |

- List of Major/Minor Bridges and Structures

The following is the list of the Major/Minor Bridges and Structures:

| Sl. No. | Location |
| --- | --- |
| 1 | Km. 47.000 (Jhiram Nalla) |
| 2 | Km. 123.000 (Kerlapal Nalla) |
| 3 | Km. 127.800 (Bodaguda Nalha) |
| 4 | Km. 137.400 (Dubbatota Nalla) |

Note;- "Minimum 25%of total concrete volume other than the foundations & sub-structures of Bridges/ Viaduct/RoB for new construction, reconstruction and widening shall be mandatorily factory manufactured pre-cast concrete elements, if such factory is there within 100 km distance from any point on the project. Any relaxation to the use of factory manufactured pre-cast concrete elements may be granted by Authority only if the contractor/ concessionaire is able to demonstrate that the manufacturer(s) is not able to provide such products matching to the works programme of the contractor or the prices of such products demanded by the manufacturer for onsite delivery is more than the prices derived for corresponding cast-insitu item at the SoR rates prevailing on 28th day before the Bid Due Date."

### 8.	Traffic Control Devices and Road Safety Works:-As per relevant manual.

### Minimum Provision will be as follows

- Traffic control devices and road safety works shall be provided in accordance with the provision of relevant Manual.

The Contractor shall provide minimum numbers of traffic control devices and road safety works as follows:

| Sl. N. | Description | Nos | Size |
| --- | --- | --- | --- |
| 1. | Gaurd Stone | 750 | 200 x 200 x 900 |
| 2. | Retro- reflection Traffic sings | 8 | 80cm x 60cm Rectangle |
|  |  | 8 | 90cm Circular |
| 3. | ''W'' Metal Crash Barrier | 560 m | 150 x 75 x 5 |
| 4. | Hazard Marker | 8 |  |
| 5. | Direction and Place identification signs upto 0.9 sqm size board | 8.64 sqm |  |
| 6. | Road Marking | 324 Sqm. |  |

- Specifications of the reflective sheeting. :-Type-XI reflective sheeting as per manual/SOR NH (PWD) Raipur, Date 01.06.2021

### 9.	 Road side Furniture

- Roadside furniture shall be provided in accordance with the provision of relevant Manual.

- Overhead traffic signs: Nil

### Compulsory Afforestation:-NIL

### Hazardous Locations

The Metal Beam Crash Barrier type "A" shall also be provided at the following hazardous locations:

| Sl. No. | Location stretch from (km) to (km) | LHS/RHS |
| --- | --- | --- |
| 1 | Km. 46.870 to Km. 46.920 | Both Side |
| 2 | Km. 47.000 to Km. 47.050 | Both Side |
| 3 | Km. 122.980 to Km. 123.000 | Both Side |
| 4 | Km. 123.040 to Km. 123.060 | Both Side |
| 5 | Km. 127.750 to Km. 127.800 | Both Side |
| 6 | Km. 127.860 to Km. 127.910 | Both Side |
| 7 | Km. 137.380 to Km. 137. 400 | Both Side |
| 8 | Km. 137.440 to Km. 137. 460 | Both Side |

### Special Requirement for Hill Roads - Not Applicable

### Change of Scope

The length of Structures and bridges specified hereinabove shall be treated as an approximate assessment. The actual lengths as required on the basis of detailed investigations shall be determined by the Contractor in accordance with the Specifications and Standards. Any variations in the lengths specified in this Schedule- B shall not constitute a Change of Scope, save and except any variations in the length arising out of a Change of Scope expressly undertaken in accordance with the provisions of Article 13.

# (Schedule B-1)

  - The shifting of utilities shall be carried out by the Contractor. The details of utilities are as follows:

| Sr. No | Type of Utility | Unit | Quantity | Location/stretch (LHS/RHS) |
| --- | --- | --- | --- | --- |
| A | Electrical Utilities |  | - |  |
| A1 | Electrical Poles | Nos. | 8 Nos. 11/33 KV Poles & Line |  |
| A2 | Electrical cables | Meters | As per site |  |
| A3 | Transformers | Nos. | NIL |  |
| B | Water/Sewage pipeline | Meters | NIL |  |
| B1 | Tube well | Nos. | NIL |  |
| B2 | Water supply | Meters | NIL |  |
| C | Solar Street Light Pole | Nos. | 6 Nos. Poles & Line |  |

Sheet-II (Annexure-I to Schedule-B1)

Utility Shifting

Shifting of obstructing existing utilities indicated in Schedule A to an appropriate location in accordance with the standards and specifications of concerned Utility Owning Department is part of the scope of work of the Contractor/Concessionaire*. The bidders may visit the site and assess the quantum of shifting of utilities for the projects before submission of their bid. Copy of utility relocation plan is enclosed. The specifications of concerned Utility Owning Department shall be applicable and followed.

Notes:

- The type/ spacing/ size/ specifications of poles/ towers/ lines/ cables to be used in shifting work shall be as per the guidelines of utility owning department and it is to be agreed solely between the Contractor/Concessionaire“ and the utility owning department. No change of scope shall be admissible and no cost shall be paid for using different type/ spacing/ size/ specifications in shifted work in comparison to those in the existing work or for making any overhead crossings to underground as per requirement of utility owning department and/or construction of project highway. The Contractor/Concessionaire” shall carry out joint inspection with utility owning department and get the estimates from the utility owning department. The assistance of the Authority is limited to giving forwarding letter on the proposal of Contractor/Concessionaire* to utility owning department whenever asked by the Contractor/Concessionaire“. The decision/ approval of utility owning department shall be binding on the Contractor/Concessionaire“.

- The supervision charges at the rates/ charges applicable of the utility owning department shall be paid directly by the Authority for the Utility Owning department as and when Contractor/Concessionaire” furnishes demand of Utility Owning Department along with a copy of estimated cost given by the later.

- The dismantled material/scrap of existing Utility to be shifted/ dismantled shall belong to the Contractor/ Concessionaire* who would be free to dispose-off the dismantled material as deemed fit by them unless the Contractor/Concessionaire“ is required to deposit the dismantled material to utility owning department as per the norm and practice and in that case the amount of credit for dismantled material may be availed by the Contractor/Concessionaire” as per estimate agreed between them.

- The utilities shall be handed over after shifting work is completed to Utility Owning Department to their entire satisfaction. The maintenance liability shall rest with the Utility Owning Department after handing over process is complete as far as utility shifting works are concerned.

Note -II 	Copy of utility shifting plans enclosed as Annexure-II to Schedule B1.

*Strike out which is not applicable.

# Schedule - C

(See Clause 2.1)

# Project Facilities

### Project Facilities

The Contractor shall construct the Project Facilities in accordance with the provisions of this Agreement. Such Project Facilities shall include:

  - Road side furniture;

  - Pedestrian facilities;

  - Electrification

  - Rain Water Harvesting

  - Stair Case

### Description of Project Facilities

### (aaa) Roadside furniture

### Traffic signs and pavements marking

### Traffic signs and pavements markings shall include road signs, curve mounted signs and road marking along the project highway. The location for these provisions shall be finalized in consultation with Authority and as per latest IRC Standards

### (b) Pedestrian facilities: NIL

(C) Electrification:- NIL

(d) Rain Water Harvesting:- NIL

(e) Stair case:-NIL

Note: Provide adequate details of each Project Facility to ensure their design and completion in accordance with the project-specific requirements and the provisions of the Manual.

Schedule - D (See Clause 2.1)

# Specifications and Standards

### Construction

The Contractor shall comply with the Specifications and Standards set forth in Annex- I of this Schedule-D for construction of the Project Highway.

### Design Standards

The Project Highway including Project Facilities shall conform to design requirements set out in the following documents:

- MoRTH Specification for Road and Bridge works, 5thRevision, 2013 and in accordance with IRC:SP:55-2001

- IRC:SP73-2018 '' Manual of specification and standard for two lanning of highways with paved shoulders '' and amendment upto Bid date

- IRC:SP:102-2014 Guidelines for Design and Construction of Reinforced Soil walls

- Railway Standards & Specification and RDSO Design/Drawing for Railway Portion.

- All the MoRTH circular and amendments issued by the Ministry upto Bid date for execution of NH works will be applicable.

- Other relevant codes.

.Annex – I

(Schedule-D)

### Specifications and Standards for Construction

  - Specifications and Standards

All Materials, works and construction operations shall conform to the Manual of Specifications and Standards for [Two-Laning of Highways (IRC:SP:73:2015)], referred to  as the Manual, and MORTH Specifications for Road and Bridge Works. Where the specification for a work is not given, Good Industry Practice shall be adopted to the satisfaction of the Authority’s Engineer.

### Deviations from the Specifications and Standards

- The terms “Concessionaire”, “Independent Engineer” and “Concession Agreement” used in the Manual shall be deemed to be substituted by the terms “Contractor”, “Authority’s Engineer” and “Agreement” respectively.

| SI.NO | Clause referred in the manual | Item | Description of deviation |
| --- | --- | --- | --- |
| 1. | IRC : SP : 73-2018 Fig 7.6 Page No. 61 TCS for Bridge of 2-Lane Highway with Paved Shoulder and protected footpath. | Provision of steel Barrier in inner side | Provision of Concrete Crash Barrier in inner side |
| 2. | IRC : SP : 73-2018 Fig 2.1 TCS for 2-Lane Highway (Open Country-Plain/Rolling terrain) | Provision of earthen shoulder | Provision of Granular shoulder |

- Notwithstanding anything to the contrary contained in Paragraph 1 above, the following Specifications and Standards shall apply to the Project Highway, and for purposes of this Agreement, the aforesaid Specifications and Standards shall be deemed to be amended to the extent set forth below:

"Design, fabrication/ casting and launching/installation of factory manufactured. pre-cast concrete elements will be done as per relevant IRC/BIS standards/guidelines/codes duly considering expected handling/lifting stresses. Any international guidelines such as ASHTO, FHWA (Accelerated Bridge Construction. Guidelines), Japan ft Euro codes, may be followed in case of any gaps in IRC/BIS standards/ guidelines/ codes. The pre-cast factory shall have minimum facility of fully automatic RMC plant, arrangement for steam curing, mechanical handling of concrete and pre-cast components, bar bending machines, stacking yard, in-house design team and NABL accredited quality control laboratory, RO plant for water purification, etc. The precast factory shall be certified by Quality Council of India if it is so mandated by MoRTH."

- [Note 1: Deviations from the aforesaid Specifications and Standards shall be listed out here. Such deviations shall be specified only if they are considered essential in view of project-specific requirements.]

### Schedule - E

(See Clauses 2.1 and 14.2)

# Maintenance Requirements

### Maintenance Requirements

  - The Contractor shall, at all times maintain the Project Highway in accordance with the provisions of this Agreement, Applicable Laws and Applicable Permits.

  - The Contractor shall repair or rectify any Defect or deficiency set forth in Paragraph 2 of this Schedule-E within the time limit specified therein and any failure in this behalf shall constitute non-fulfillment of the Maintenance obligations by the Contractor.  Upon occurrence of any breach hereunder, the Authority shall be entitled to effect reduction in monthly lump sum payment as set forth in Clause 14.6 of this Agreement, without prejudice to the rights of the Authority under this Agreement, including Termination thereof.

  - All Materials, works and construction operations shall conform to the MORTH Specifications for Road and Bridge Works, and the relevant IRC publications. Where the specifications for a work are not given, Good Industry Practice shall be adopted.

[Specify all the relevant documents]

### Repair/rectification of Defects and deficiencies

The obligations of the Contractor in respect of Maintenance Requirements shall include repair and rectification of the Defects and deficiencies specified in Annex - I of this Schedule-E within the time limit set forth therein.

### Other Defects and deficiencies

In respect of any Defect or deficiency not specified in Annex - I of this Schedule-E, the Authority’s Engineer may, in conformity with Good Industry Practice, specify the permissible limit of deviation or deterioration with reference to the Specifications  and Standards, and any deviation or deterioration beyond the permissible limit shall be repaired or rectified by the Contractor within the time limit specified by the Authority’s Engineer.

### Extension of time limit

Notwithstanding anything to the contrary specified in this Schedule-E, if the nature and extent of any Defect or deficiency justifies more time for its repair or rectification than the time specified herein, the Contractor shall be entitled to additional time in conformity with Good Industry Practice. Such additional time shall be determined by the Authority’s Engineer and conveyed to the Contractor and the Authority with reasons thereof.

### Emergency repairs/restoration

Notwithstanding anything to the contrary contained in this Schedule-E, if any Defect, deficiency or deterioration in the Project Highway poses a hazard to safety or risk of damage to property, the Contractor shall promptly take all reasonable measures for eliminating or minimizing such danger.

### Daily inspection by the Contractor

The Contractor shall, through its engineer, undertake a daily visual inspection of the Project Highway and maintain a record thereof in a register to be kept in such form and manner as the Authority’s Engineer may specify. Such record shall be kept in safe custody of the Contractor and shall be open to inspection by the Authority and the Authority’s Engineer at any time during office hours.

### Pre-monsoon inspection / Post-monsoon inspection

The Contractor shall carry out a detailed pre-monsoon inspection of all bridges, culverts and drainage system before [1st June] every year in accordance with the guidelines contained in IRC: SP35. Report of this inspection together with details of proposed maintenance works as required on the basis of this inspection shall be sent to the Authority’s Engineer before the [10th June] every year. The Contractor shall complete the required repairs before the onset of the monsoon and send to the Authority’s Engineer a compliance report. Post monsoon inspection shall be done by the [30th September] and the inspection report together with details of any damages observed and proposed action to remedy the same shall be sent to the Authority’s Engineer.

### Repairs on account of natural calamities

All damages occurring to the Project Highway on account of a Force Majeure Event or willful default or neglect of the Authority shall be undertaken by the Authority at its own cost. The Authority may instruct the Contractor to undertake the repairs at the rates agreed between the Parties.

# Annex – I

# (Schedule-E) Repair/rectification of Defects and deficiencies

The Contractor shall repair and rectify the Defects and deficiencies specified in this Annex-I of Schedule-E within the time limit set forth in the table below.

### Table -1: Maintenance Criteria for Pavements:

| Asset Type | Perform ance Parameter | Level of Service (LOS) |  | Frequency of Inspect ion | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
| Flexible Pavement (Pavement of MCW, Service Road, approach | Potholes | Nil | < 0.1 % of area and subject to limit of 10 mm in depth | Daily | Length Measurement Unit like Scale, Tape, odometer etc. | IRC 82: 2015 and Distress Identification Manual for Long Term Pavement Performance Program, FHWA 2003 (http://www.tfhrc.com/pavement/lttp/ reports/03031/) | 24-48 hours | MORT&H Specification 3004.2 |

| Asset Type | Performance Parameter | Level of Service (LOS) |  | Frequency of Inspect ion | Tools/Equip ment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
| s of Grade structure, approache s of connecting roads, slip roads, lay byes etc. as applicable ) | Cracking | Nil | < 5 % subject to limitof 0.5 sqm for any 50 m length | Daily |  |  | 7-15 days | MORT&H Specification 3004.3 |
|  | Rutting | Nil | < 5 mm | Daily | Straight Edge |  | 15 -30 days | MORT&H Specification 3004.2 |
|  | Corrugations and Shoving | Nil | < 0.1% Of area | Daily | Length Measurement Unit like |  | 2-7 days | IRC:82- 2015 |

| Asset Type | Performance Parameter | Level of Service (LOS) |  | Frequency of Inspect ion | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
|  | Bleeding | Nil | < 1 % of area | Daily | Scale, Tape, odometer etc. |  | 3-7 days | MORT&H Specification 3004.4 |
|  | Ravelling / Stripping | Nil | < 1 % of area | Daily |  |  | 7-15 days | IRC:82- 2015 read with IRC SP 81 |
|  | Edge Deformati on/ Breaking | Nil | < 1 m for any 100 m section and width < 0.1 m at any location, restricte | Daily |  |  | 7- 15 days | IRC:82- 2015 |

| Asset Type | Performance Parameter | Level of Service (LOS) |  | Frequency of Inspect ion | Tools/Equipment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
|  |  |  | d to 30 cm from the edge |  |  |  |  |  |
|  | Roughness BI | 2000 mm/km | 2400 mm/km | Bi- Annuall y | Class I Profilometer SCRIM (Sideway- force Coefficient Routine Investigation Machine or equivalent) | Class I Profilometer : ASTM E950 (98) :2004 –Standard Test Method for measuring Longitudinal Profile of Travelled Surfaces with Accelerometer Established Inertial Profiling Reference ASTM E1656 -94: 2000- Standard Guide for Classification of Automatic Pavement Condition Survey Equipment | 180 days | IRC:82- 2015 |
|  | Skid Number | 60SN | 50SN | Bi- Annuall y |  |  | 180 days | BS: 7941-1: 2006 |
|  | Pavement Condition Index | 3 | 2.1 | Bi- Annuall y |  |  | 180 days | IRC:82- 2015 |

| Asset Type | Perform anceParameter | Level of Service (LOS) |  | Frequency of Inspect ion | Tools/Equip ment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | MaintenanceSpecifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
|  | Other Pavement Distresses |  |  | Bi- Annuall y |  |  | 2-7 days | IRC:82- 2015 |
|  | Deflection/ Remaining Life |  |  | Annual ly | Falling Weight Deflectomete r | IRC 115: 2014 | 180 days | IRC:115- 2014 |
| Rigid Pavement (Pavemen t of MCW, Service Road, Grade structure, | Roughness BI | 2200m m/km | 2400mm /km | Bi- Annuall y | Class I Profilometer | ASTM E950 (98) :2004 and ASTM E1656 - 94: 2000 | 180 days | IRC:SP:83- 2008 |
|  | Skid | Skid Resistance no. at different speed of vehicles |  | Bi- Annuall y | SCRIM (Sideway- force | IRC:SP:83-2008 | 180 days | IRC:SP:83- 2008 |

| AssetType approach es of connectin g roads, slip roads, lay byes etc. as applicabl e) | Perform anceParameter | Level of Service (LOS) |  |  | Frequency of Inspect ion | Tools/Equip ment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |  |
|  |  | Minimum SN |  | Traffic Speed (Km/h) |  | Coefficient Routine Investigation Machine or equivalent) |  |  |  |
|  |  | 36 |  | 50 |  |  |  |  |  |
|  |  | 33 |  | 65 |  |  |  |  |  |
|  |  | 32 |  | 80 |  |  |  |  |  |
|  |  | 31 |  | 95 |  |  |  |  |  |
|  |  | 31 |  | 110 |  |  |  |  |  |

| Asset Type | Perform anceParameter | Level of Service (LOS) |  | Frequency of Inspect ion | Tools/Equip ment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | Maintenance Specifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
| Embankment/ Slope | Edge drop at shoulders | Nil | 40m m | Daily | Length Measuremen t Unit like Scale, Tape, odometer etc. | IRC | 7-15 days | MORT&H Specification 408.4 |
|  | Slope of camber/c ross fall | Nil | <2% variation in prescribed slope of camber /cross fall | Daily |  |  | 7-15 days | MORT&H Specification 408.4 |
|  | Embankment Slopes | Nil | <15 % variation in prescribe | Daily |  |  | 7-15 days | MORT&H Specification 408.4 |

| Asset Type | Perform anceParameter | Level of Service (LOS) |  | Frequency of Inspect ion | Tools/Equip ment | Standards and References for Inspection and Data Analysis | Time limit for Rectification/ Repair | MaintenanceSpecifications |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Desirable | Acceptable |  |  |  |  |  |
|  |  |  | side slope |  |  |  |  |  |
|  | Embankment Protection | Nil | Nil | Daily | NA |  | 7-15 days | MORT&H Specification |
|  | Rain Cuts/ Gullies in slope | Nil | Nil | Daily Speciall y During Rainy Season | NA |  | 7-15 days | MORT&H Specification |

In addition to the above performance criterion, the contractor shall strictly maintain the rigid pavements as per requirements in the following table Table -2: Maintenance Criteria for Rigid Pavements:

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| CRACKING |  |  |  |  |  |  |
| 1 | Single Discrete Cracks Not intersecting with any joint | w = width of crack L = length of crack d = depth of crack D = depth ofslab | 0 | Nil, not discernible | No Action | Not applicable |
|  |  |  | 1 | w < 0.2 mm. hair cracks |  |  |
|  |  |  | 2 | w = 0.2 - 0.5 mm, discernible from slow-movingcar | Seal without delay | Seal, and stitch if L >lm. Within 7days |
|  |  |  | 3 | w = 0.5 - 1.5 mm, discernible from fast-movingcar |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  | 4 | w = 1.5 - 3.0 mm | Seal, and stitch if L > l m. Within 7 days | Staple or Dowel Bar Retrofit, FDR for affected portion. Within 15days |
|  |  |  | 5 | w > 3 mm. |  |  |
| 2 | Single Transverse (or Diagonal) Crack intersecting with one or morejoints | w = width of crack L = length of crack d = depth of crack D = depth ofslab | 0 | Nil, not discernible | No Action |  |
|  |  |  | 1 | w < 0.2 mm, hair cracks | Route and seal with epoxy. Within 7 days | Staple or Dowel Bar Retrofit. Within 15days |
|  |  |  | 2 | w = 0.2 - 0.5 mm, discernible from slow vehicle |  |  |
|  |  |  | 3 | w = 0.5 - 3.0 mm, discernible from fast vehicle | Route, seal and stitch, if L > 1m. Within 7 days |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  | 4 | w = 3.0 - 6.0 mm | Dowel Bar Retrofit. Within 15 days | Full Depth Repair Dismantle and reconstructaffected. Portion with norms and specifications - See Para 5.5 & 9.2 Within 15days |
|  |  |  | 5 | w > 6 mm, usually associated with spalling, and/or slab rocking under traffic | Not Applicable, as it may befull depth |  |
| 3 | Single Longitudinal Crack intersecting with one or more joints | w = width of crack L = length of crack d = depth of crack D = depth ofslab | 0 | Nil, not discernible | No Action |  |
|  |  |  | 1 | w < 0.5 mm, discernable from slow movingvehicle | Seal with epoxy, if L > 1 m. Within 7 days | Staple or dowel bar retrofit. Within 15days |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  | 2 | w = 0.5 - 3.0 mm, discernible from fast vehicle | Route seal and stitch, ifL >l m. Within 15 days | - |
|  |  |  | 3 | w = 3.0 - 6.0 mm | Staple, if L > 1 m. Within 15 days | Partial Depth Repair withstapling. Within 15 days |
|  |  |  | 4 | w = 6.0 - 12.0 mm, usually associated withspalling | Not Applicable, as it may befull depth |  |
|  |  |  | 5 | w > 12 mm, usually associated with spalling, and/or slab rocking under traffic |  | Full Depth Repair Dismantle and reconstruct affected portion as pernorms and specifications - |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  |  |  |  | See Para 5.6.4 Within 15 days |
| 4 | Multiple Cracks intersecting with one or morejoints | w = width of crack | 0 | Nil, not discernible | No Action | - |
|  |  |  | 1 | w < 0.2 mm, hair cracks | Seal, and stitch if L > l m. Within 15 days |  |
|  |  |  | 2 | w = 0.2 - 0.5 mm. discernible from slow vehicle |  |  |
|  |  |  | 3 | w = 0.5 - 3.0 mm, discernible from fast vehicle | Full depth repair within 15 days | Dismantle, Reinstate sub base, Reconstruct whole slab as per specifications within 30 days |
|  |  |  | 4 | w = 3.0 - 6.0 mm panel broken into 2 or 3pieces |  |  |
|  |  |  | 5 | w > 6 mm and/or panel broken into more than 4 pieces |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| 5 | Corner Break | w = width of crack L = length of crack | 0 | Nil, not discernible | No Action | - |
|  |  |  | 1 | w < 0.5 mm; only 1 corner broken | Seal with low viscosity epoxy to secure broken parts Within 7 days | Seal with epoxy seal with epoxy Within 7days |
|  |  |  | 2 | w < 1.5 mm; L < 0.6 m, only one corner broken |  |  |
|  |  |  | 3 | w < 1.5 mm; L < 0.6 m, two corners broken | Partial Depth (Refer Figure 8.3 of IRC:SP: 83-2008) Within 15 days | Full depth repair |
|  |  |  | 4 | w > 1.5 mm; L > 0.6 m or three corners broken |  |  |
|  |  |  | 5 | ree or four corners broken |  | Reinstate sub-base, and reconstruct the |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  |  |  |  | slab as per norms and specifications within 30days |
| 6 | Punch out (Applicable to Continuous Reinforced Concrete Pavement (CRCP) only) | w = width of crack L = length(m/m2) | 0 | Nil, not discernible |  | No Action |
|  |  |  | 1 | w < 0.5 mm; L < 3 m/m2 | Not Applicable, as it may be full depth | Seal with low viscosity epoxy to secure broken parts. Within 15days |
|  |  |  | 2 | either w > 0.5 mm or L < 3 m/m2 |  |  |
|  |  |  | 3 | w > 1.5 mm and L < 3 m/m2 |  |  |
|  |  |  | 4 | w > 3 mm, L < 3 m/m2 and deformation |  | Full depth repair - Cut out and replace damaged area taking care not to damage reinforcement. Within30days |
|  |  |  | 5 | w > 3 mm, L > 3 m/m2 and deformation |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
| Surface Defects |  |  |  |  |  |  |
| 7 | Ravelling or Honeycomb type surface | r = area damaged surface/total surface of slab (%) h = maximum depth of damage | 0 | Nil, not discernible | Short Term | Long Term |
|  |  |  |  |  | No action. | Not Applicable |
|  |  |  | 1 | r < 2 % | Local repair of areas damaged and liable to be damaged. Within 15 days |  |
|  |  |  | 2 | r = 2 - 10 % |  |  |
|  |  |  | 3 | r = 10-25% | Bonded Inlay, 2 or 3 slabs if affecting. |  |
|  |  |  | 4 | r = 25 - 50 % |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  |  |  | Within 30 days |  |
|  |  |  | 5 | r > 50% and h > 25 mm | Reconstruct slabs, 4 or more slabs ifaffecting. Within 30 days |  |
| 8 | Scaling | r = damaged surface/total surface of slab (%) h = maximum depth of damage | 0 | Nil, not discernible | Short Term | Long Term |
|  |  |  |  |  | No action. | Not Applicable |
|  |  |  | 1 | r <2 % | Local repair of areas damaged and liable to be damaged. Within 7days |  |
|  |  |  | 2 | r = 2 - 10 % |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  | 3 | r = 10 - 20% | Bonded Inlay within 15 days |  |
|  |  |  | 4 | r = 20 - 30 % |  |  |
|  |  |  | 5 | r > 30 % and h > 25 mm | Reconstruct slab within 30 days |  |
| 9 | Polished Surface/Glazing | t = texture depth, sand patchtest | 0 |  | No action. | Not Applicable |
|  |  |  | 1 | t > 1 mm |  |  |
|  |  |  | 2 ' | t = 1 - 0.6 mm | Monitor rate of deterioration |  |
|  |  |  | 3 | t = 0.6 - 0.3 mm |  |  |
|  |  |  | 4 | t = 0.3 - 0.1 mm |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  | 5 | t < 0.1 mm | Diamond Grinding if affecting 50% or more slabs ina continuous stretch of minimum 5 km. Within 30 days |  |
| 10 | Popout (Small Hole), Pothole Refer Para 8.4 | n = number/m2 d = diameter h = maximum depth | 0 | d < 50 mm; h < 25 mm; n < 1 per 5 m2 | No action. | Not Applicable |
|  |  |  | 1 | d=50-100mm;h<50mm;n<1 per 5 m2 | Partial depth repair 65 mm deep. Within 15 days |  |
|  |  |  | 2 | d=50-100mm;h>50mm;n<1 per 5 m2 |  |  |

| S.No. | Type of Distress | Measured Parameter | Degree of Severity | Assessment Rating | Repair Action |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | For the case d < D/2 | For the case d > D/2 |
|  |  |  | 3 | d = 100 - 300 mm; h < 100 mm n < 1 per 5m2 | Partial depth repair 110mm i.e.10 mm more than the depth of the hole. Within 30 days |  |
|  |  |  | 4 | d = 100 - 300 mm; h > 100 mm; n < 1 per 5m2 |  |  |
|  |  |  | 5 | d > 300 mm; h > 100 mm: n > 1 per 5 m2 | Full depth repair. Within 30 days |  |

| Joint Defects |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 11 | Joint Seal Defects | loss or damage L = Length as % total joint length | 0 | Difficult to discern. | Short Term | Long Term |
|  |  |  |  |  | No action. | Not Applicable |
|  |  |  | 1 | Discernible, L< 25% but of little immediate consequence with regard to ingress of water or trapping incompressible material. | Clean joint, inspect later. |  |
|  |  |  | 3 | Notable. L > 25% insufficient protection against ingress of water and trapping incompressible material. | Clean and reapply sealant in selected locations. Within 7 days |  |
|  |  |  | 5 | Severe; w > 3 mm negligible protection against ingress of water and trapping incompressible material | Clean, widen and reseal the joint. Within 7 days |  |

| 12 | Spalling of Joints | w = width on either side of the joint L = length of spalled portion (as % joint length) | 0 | Nil, not discernible | No action. | Not Applicable |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | w < 10 mm | Apply low viscosity epoxy resin/ mortar in cracked portion. Within 7 days |  |
|  |  |  | 2 | w = 10 - 20 mm, L < 25% |  |  |
|  |  |  | 3 | w = 20 - 40 mm, L > 25% | Partial Depth Repair. Within 15 days |  |
|  |  |  | 4 | w = 40 - 80 mm, L > 25% | 30 - 50 mm deep, h = w + 20% of w, within 30 days |  |
|  |  |  | 5 | w > 80 mm, and L > 25% | 50 - 100 mm deep repair. H = w + 20% of w. Within 30 days |  |
| 13 | Faulting (or Stepping) | f = difference of level | 0 | not discernible, < 1 mm | No action. | No action. |

|  | in Cracks or Joints |  | 1 | f < 3 mm |  |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 2 | f = 3 - 6 mm | Determine cause and observe, take action for diamondgrinding | Replace the slab as appropriate. Within 30days |
|  |  |  | 3 | f = 6 - 12 mm | Diamond Grinding |  |
|  |  |  | 4 | f= 12 - 18 mm | Raise sunken slab. | Replace the slab as appropriate. Within 30days |
|  |  |  | 5 | f> 18 mm | Strengthen subgrade and sub-base by groutingand raising sunken slab |  |
| 14 | Blowup or Buckling | h = vertical displacement from normal profile | 0 | Nil, not discernible | Short Term | Long Term |
|  |  |  |  |  | No Action |  |
|  |  |  | 1 | h < 6 mm |  |  |
|  |  |  | 2 | h = 6 - 12 mm | Install Signs to Warn Traffic |  |

|  |  |  | 3 | h = 12 - 25 mm | within 7 days |  |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 4 | h > 25 mm | Full Depth Repair. Within 30 days |  |
|  |  |  | 5 | shattered slabs, ie 4 or more pieces | Replace broken slabs. Within 30 days |  |
| 15 | Depression | h = negative vertical displacement from normal profile L =length | 0 | Not discernible, h < 5 mm | No action. | Not Applicable |
|  |  |  | 1 | h = 5 - 15 mm |  |  |
|  |  |  | 2 | h = 15-30 mm, Nos<20% joints | Install Signs to Warn Traffic within 7 days |  |
|  |  |  | 3 | h = 30 - 50 mm |  |  |
|  |  |  | 4 | h > 50 mm or > 20% joints | Strengthen subgrade. Reinstate pavement at normal level |  |

|  |  |  | 5 | h > 100 mm | if L < 20 m. Within 30 days |  |
| --- | --- | --- | --- | --- | --- | --- |
| 16 | Heave | h = positive vertical displacement from normal profile. L = length | 0 | Not discernible. h < 5 mm | Short Term | Long Term |
|  |  |  |  |  | No action. | scrabble |
|  |  |  | 1 | h = 5 - 15 mm | Follow up. |  |
|  |  |  | 2 | h = 15 - 30 mm, Nos <20% joints | Install Signs to Warn Traffic within 7 days |  |
|  |  |  | 3 | h = 30 - 50 mm |  |  |
|  |  |  | 4 | h > 50 mm or > 20% joints | Stabilise subgrade. Reinstate pavement at normal level if length < 20 m. Within 30 days |  |
|  |  |  | 5 | h > 100 mm |  |  |
| 17 | Bump | h = vertical | 0 | h < 4 mm | No action |  |

|  |  | displacement from normal profile | 1 | h = 4 - 7 mm | Grind, in case of new construction within 7 days | Construction Limit for New Construction. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 3 | h = 7 - 15 mm | Grind, in case of ongoing Maintenance within 15 days | Replace in case of new construction. Within 30days |  |
|  |  |  | 5 | h > 15 mm | Full Depth Repair. Within 30 days | Full Depth Repair. Within 30days |  |
| 18 | Lane to Shoulder Dropoff | f = difference of level | 0 | Nil, not discernible < 3mm | Short Term | Long Term |  |
|  |  |  |  |  | No action. |  |  |
|  |  |  | 1 | f = 3 - 10 mm | Spot repair of shoulder within 7 days |  |  |
|  |  |  | 2 | f = 10 - 25 mm |  |  |  |
|  |  |  | 3 | f = 25 - 50 mm | Fill up shoulder |  |  |
|  |  |  | 4 | f = 50 - 75 mm | within 7 dayss | For any 100 m stretch Reconstruct shoulder, if affecting 25% or more ofstretch. Within 30days |
|  |  |  | 5 | f > 75 mm |  |  |
| Drainage |  |  |  |  |  |  |
| 19 | Pumping | quantity of fines and water expelled through open joints and cracks Nos | 0 | not discernible | No Action |  |
|  |  |  | 1 to 2 | slight/ occasional Nos< 10% | Repair cracks and joints Without delay. | Inspect and repair sub-drainage at distressed sections and upstream. |
|  |  |  | 3 to 4 | appreciable/ Frequent 10 -25% | Lift or jack slab within 30 days. |  |
|  |  | Nos/100 m stretch | 5 | abundant, crack development >25% | Repair distressed pavement sections. Strengthen subgrade and subbase. Replace slab. Within 30 days |  |
| 20 | Ponding | Ponding on slabs due to blockage of drains | 0-2 | No discernible problem | No action. |  |  |
|  |  |  | 3 to 4 | Blockages observed in drains, but water flowing | Clean drains etc within 7 days, Follow up | Action required to stop water damaging foundation within 30 days. |  |
|  |  |  | 5 | Ponding, accumulation of water observed | -do- |  |  |

### Table -3: Maintenance Criteria for Safety Related Items and Other Furniture Items:

| Asset Type | Performance Parameter | Level of Service (LOS) |  |  | Frequency of Measuremen t | Testing Method | Recommended Remedial measures | Time limit for Rectification |  | Specification s and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Highway | Availability of Safe Sight Distance | As per IRC SP :84-2014, a minimum of safe stopping sight distance shall be available throughout. |  |  | Monthly | Manual Measurement s with Odometer along with video/ image backup | Removal of obstruction within 24 hours, in case of sight line affected by temporary objects such as trees, temporary encroachments. In case of permanent structure or design deficiency: Removal of obstruction/improvement of deficiency at theearliest Speed Restriction boards and suitable traffic calming measures such as transverse bar marking, blinkers, etc. shall be applied during the period of rectification. |  |  | IRC:SP 84-2014 |
|  |  | Design Speed, kmph | Desirable Minimum Sight Distance (m) | Safe Stoppin g Sight Distance (m) |  |  |  |  |  |  |
|  |  | 100 | 360 | 180 |  |  |  |  |  |  |
|  |  | 80 | 260 | 130 |  |  |  |  |  |  |
|  |  |  |  |  |  | Visual | Re - painting | Cat-1 Defect – |  | IRC:35- |
| Pavement Marking | Wear | <70% of marking remaining |  |  | Bi- Annually | Assessment as per Annexure-F of IRC:35-2015 |  | within 24 hours Cat-2 Defect within 2months | - | 2015 |

| Asset Type | Performance Parameter | Level of Service (LOS) |  |  | Frequency of Measuremen t | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification s and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Day time Visibility | During expected life Service Time Cement Road - 130mcd/m2/lux Bituminous Road - 100mcd/m2/lux |  |  | Monthly | As per Annexure-D of IRC:35-2015 | Re - painting | Cat-1 Defect – within 24 hours Cat-2 Defect – within 2 months | IRC:35- 2015 |
|  |  | Initial and Minimum Performancefor Dry Retro reflectivity during night time: |  |  |  | As per Annexure-E of IRC:35-2015 | Re - painting | Cat-1 Defect – within 24 hours Cat-2 Defect – within 2 months | IRC:35-2015 |
|  |  | Design | (RL) Retro |  |  |  |  |  |  |
|  |  | Speed | Reflectivity |  |  |  |  |  |  |
|  |  |  | (mcd/m2/lux) |  |  |  |  |  |  |
|  |  |  | Initial | Minimum |  |  |  |  |  |
|  |  |  | (7 days) | Threshold level |  |  |  |  |  |
|  |  |  |  | (TL) & warranty |  |  |  |  |  |
|  | Night Time Visibility |  |  | period required up to 2 years | Bi-Annually |  |  |  |  |
|  |  | Up to 65 | 200 | 80 |  |  |  |  |  |
|  |  | 65 - 100 | 250 | 120 |  |  |  |  |  |
|  |  | Above | 350 | 150 |  |  |  |  |  |
|  |  | 100 |  |  |  |  |  |  |  |
|  |  | Initial and Minimum Performance for Night Visibility under wet condition(Retro reflectivity): |  |  |  |  |  |  |  |

| Asset Type | Performance Parameter |  | Level of Service (LOS) | Frequency of Measuremen t | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification s and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Initial 7 days Retro reflectivity: 100 mcd/m2/lux Minimum Threshold Level: 50 mcd/m2/lux |  |  |  |  |  |
|  | Skid Resistance |  | Initial and Minimum performance for SkidResistance: Initial (7days): 55BPN Min. Threshold: 44BPN *Note: shall be considered under urban/city traffic condition encompassing the locations like pedestrian crossings, bus bay, bus stop, cycle track intersection delineation, transverse bar markings etc | Bi-Annually | As per Annexure-G of IRC:35-2015 |  | Within 24 hours | IRC:35-2015 |
| Road Signs | Shape Position | and | Shape and Position as per IRC:67- 2012. Signboard should be clearly visible for the design speed of the section. | Daily | Visual with video/image backup | Improvement of shape, in case if shape is damaged. Relocation as per requirement | 48 hours in case of Mandatory Signs, Cautionary and Informatory Signs (Single and Dual post signs) 15 Days in case of | IRC:67-2012 |
|  |  |  |  |  |  |  | Gantry/Cantileve r Sign boards |  |
|  | Retro reflectivity |  | As per specifications in IRC:67-2012 | Bi-Annually | Testing of each | hange of ignboard | 48 hours in case of Mandatory | RC:67-2012 |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measuremen t | TestingMethod | Recommended Remedial measures | Time limit for Rectification | Specification s and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | signboard using Retro Reflectivity Measuring Device. In accordance with ASTM D 4956-09. |  | Signs, Cautionary and Informatory Signs (Single and Dual postsigns) 1 Month in case of Gantry/Cantilev er Sign boards |  |
| Kerb | Kerb Height | As per IRC 86:1983 depending upon type of Kerb | Bi-Annually | Use of distance measuring tape | Raising KerbHeight | Within 1 Month | RC 86:1983 |
|  | Kerb Painting | Functionality: Functioning of Kerb painting as intended | Daily | Visual with video/image backup | Kerb Repainting | Within 7-days | RC 35:2015 |
| Other Road Furnitur e | Reflective Pavement Markers (Road Studs) | Numbers and Functionality as per specifications in IRC:SP:84-2014 and IRC:35-2015, unless specified in Schedule-B. | Daily | Counting | New Installation | Within 2 months | IRC:SP:84- 2014,IRC:35- 2015 |
|  | Pedestrian Guardrail | Functionality: Functioning of guardrail asintended | Daily | Visual with video/image backup | Rectification | Within 15 days | IRC:SP:84- 2014 |
|  | Traffic Safety Barriers | Functionality: Functioning of Safety Barriers as intended | Daily | Visual with video/image backup | Rectification | Within 7 days | IRC:SP:84- 2014, IRC:119- 2015 |
|  | End Treatment of | Functionality: Functioning of End Treatment as intended | Daily | Visual with video/image | Rectification | Within 7 days | IRC:SP:84- 2014, |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measuremen t | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification s and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Traffic Safety Barriers |  |  | backup |  |  | IRC:119- 2015 |
|  | Attenuators | Functionality: Functioning of Attenuators asintended | Daily | Visual with video/image backup | Rectification | Within 7 days | IRC:SP-2014, IRC:119- 2015 |
|  | Guard Posts and Delineators | Functionality: Functioning of Guard Posts and Delineators as intended | Daily | Visual with video/image backup | Rectificatio n | Within 15 days | IRC: 79 - 1981 |
|  | Overhead Sign Structure | Overhead sign structure shall be structurally adequate | Daily | Visual with video/image backup | Rectification | Within 15 days | IRC:67-2012 |
|  | Traffic Blinkers | Functionality: Functioning of Traffic Blinkers as intended | Daily | Visual with video/image backup | Rectification | Within 7 days | IRC:SP:84- 2014 |
| Highway Lighting System | Highway Lights | Illumination: Minimum 40 Lux illumination on the road surface | Daily | The illumination level shall be measured with luxmeter | Improvement in Lighting System | 24 hours | IRC:SP:84- 2014 |
|  |  | No major failure in the lighting system | Daily | - | Rectification of failure | 24 hours | IRC:SP:84- 2014 |
|  |  | No minor failure in the lighting system | Monthly | - | Rectification of failure | 8 hours | IRC:SP:84- 2014 |
|  | Toll Plaza Canopy Lights | Minimum 40 Lux illumination on the road surface | Daily | The illumination level shall be measured with luxmeter | Improvement in Lighting System | 24 hours | IRC:SP:84- 2014 |
|  |  | No major/minor failure in the lighting system | Daily | - | Rectification of failure | 8 hours | IRC:SP:84- 2014 |

| Asset Type | Performance Parameter | Level of Service (LOS) | Frequency of Measuremen t | Testing Method | Recommended Remedial measures | Time limit for Rectification | Specification s and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Trees and Plantatio n including median plantatio n | Obstruction in a minimum head-room of 5.5 m above carriageway or obstruction in visibility of road signs | No obstruction due to trees | Monthly | Visual with video/image backup | Removal of trees | Immediate | IRC:SP:84- 2014 |
|  | Deterioration in health of trees and bushes | Health of plantation shall be as per requirement of specifications & instructions issued by Authority from time to time | Daily | Visual with video/image backup | Timely watering and treatment. Or Replacement of Trees and Bushes. | Within 90 days | IRC:SP:84- 2014 |
|  | Vegetation affecting sight line and road Structures | Sight line shall be free from obstruction byvegetation | Daily | Visual with video/image backup | Removal of Trees | Immediate | IRC:SP 84- 2014 |
| Rest Areas | Cleaning of Toilets | - | Daily | - | - | Every 4 hours |  |
|  | Defects in electrical, water and sanitary installations | - | Daily | - | Rectification | 24 hours |  |

| Asset Type | Performance Parameter |  | Level of Service (LOS) |  |  | Frequency of Measuremen t |  | Testing Method |  | Recommended Remedial measures | Time limit for Rectification |  |  | Specification s and Standards |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Other |  |  |  |  |  |  |  | - |  | Rectification | 15 days |  |  | IRC:SP 84- |
| Project Facilities | Damage or deterioration in Approach Roads, pedestrian facilities, truck lay-bys, bus-bays,bus- |  |  |  |  | Daily |  |  |  |  |  |  |  | 2014 |
| and | shelters, cattle crossings, Traffic Aid Posts, Medical |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Approac | Aid Posts and other works |  |  |  |  |  |  |  |  |  |  |  |  |  |
| h roads |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Asset Type |  | Performanc e Parameter |  | Level of Service (LOS) | Frequency of Measuremen t |  | Testing Method |  | Recommended Remedial measures |  |  | Time limit for Rectification | Specifications and Standards |  |
| Pipe/box/slab culverts |  | Free waterway/ unobstructe d flow section |  | 85% of culvert normal flow area to available. | 2 times in a year (before and after rainy season) |  | Inspection by Bridge Engineer as per IRC SP: 35-1990 and recording of depth of silting and area of vegetation. |  | Cleaning silt up soils and debris in culvert barrel after rainy season, removal of bushes and vegetation, U/s of barrel, under barrel and D/s of barrelbefore rainy season. |  |  | 15 days before onset of monsoon and within 30 days after end ofrainy season. | IRC 5-2015, IRC SP:40- 1993 and IRC SP:13- 2004 |  |
|  |  | Leak-proof expansion joints if any |  | No leakage through expansionjoints | Bi-Annually |  | Physical inspection of expansion joints as per IRC SP: 35- 1990 if any, for leakage strains on walls at joints. |  | Fixing with sealant suitably |  |  | 30 days or before onset of rains whichever comes earlier | IRC SP:40- 1993 and IRC SP:69-2011 |  |
|  |  | Structurally sound |  | Spalling of concrete not more than 0.25 sqm | Bi-Annually |  | Detailed inspection of all components of culvert as per IRC SP:35-1990 and recording the defects |  | Repairs to spalling, cracking, delamination, rusting shall be followed as perIRC:SP:40-1993. |  |  | 15 days | IRC SP 40- 1993 and MORTH Specification s clause 2800 |  |
|  |  |  |  | Delamination of concrete not more than 0.25 sq.m. |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  | Cracks wider than 0.3 mm not more than 1m aggregate length |  |  |  |  |  |  |  |  |  |  |

|  | Protection works in good condition | Damaged of rough stone apron or bank revetment not more than 3 sqm, damage to solid apron (concrete apron) not more than 1 sqm | 2 times in a year (before and after rainy season) | Condition survey as per IRC SP:35-1990 | Repairs to damaged aprons andpitching | 30 days after defect observation or 2 weeks before onset of rainy season whichever is earlier. | IRC: SP 40- 1993 and IRC:SP:13- 2004. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bridges including ROBs Flyover etc. as applicable | Riding quality or user comfort | No pothole in wearing coat on bridge deck | Daily | Visual inspection as per IRC SP:35-1990 | Repairs to BC or wearing coat | 15 days | MORT&H Specification 2811 |
| Bridge -Super Structure | Bumps | No bump at expansionjoint | Daily | Visual inspection as per IRC SP:35- 1990 | Repairs to BC on either side of expansion joints, profile correction course on approach slab in case of settlement to approach embankment | 15 days | MORT&H Specification 3004.2 & 2811. |
|  | User safety (condition of crash barrier andguard rail) | No damaged or missing stretch of crash barrier or pedestrian hand railing | Daily | Visual inspection and detailed condition survey as per IRC SP: 35- 1990. | Repairs and replacement of safety barriers as the case may be | 3days | IRC: 5-1998, IRC SP: 84- 2014 and IRC SP: 40- 1993. |

|  | Rusted reinforcement | Not more than 0.25 sq.m | Bi- Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | All the corroded reinforcement shall need to be thoroughly cleaned from rusting and applied with anti-corrosive coating before carrying out the repairs to affected concrete portion with epoxy mortar / concrete. | 15 days | IRC SP: 40- 1993 and MORTH Specification 1600. |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Spalling of concrete | Not more than 0.50 sq.m |  |  |  |  |  |
|  | Delaminatio n | Not more than 0.50 sq.m |  |  |  |  |  |
|  | Cracks wider than 0.30 mm | Not more than 1m total length | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | Grouting with epoxy mortar, investigating causes for cracks development and carry out necessary rehabilitation. | 48 Hours | IRC SP: 40- 1993 and MORTH Specification 2800. |
|  | Rainwater seepage through deck slab | Leakage - nil | Quarterly | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | Grouting of deck slab at leakage areas, waterproofing, repairs to drainage spouts | 1 months | MORTH specifications 2600 & 2700. |
|  | Deflection due to permanent loads and | Within design limits. | Once in every 10 years for spans more | Load test method | Carry out major rehabilitation works on bridge to retain original design loads capacity | 6 months | IRC SP: 51- 1999. |

|  | live loads |  |  | than 40 m |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Vibrations in bridge deck due to moving trucks | Frequency of vibrations shall not be more than 5 Hz |  | Once in every 5 years for spans more than 30m and every 10 years for spans between 15 to 30 m | Laser displacement sensors or laser vibro-meters | Strengthening structure | of | super | 4 months | AASHTO LRFD specifications |
|  | Leakage in Expansion joints | No damage to elastomeric sealant compound in strip seal expansion joint, no leakage of rain water through expansion joint in case of buried and asphalt plug and copper stripjoint. |  | Bi-Annually | Detailed condition survey as per IRC SP:35-1990 using Mobile Bridge Inspection Unit | Replace of expansion joint | seal | in | 15 days | MORTH specifications 2600 and IRC SP: 40-1993. |
|  | Debris and dust in strip seal | No dust debris expansion | or in joint | Monthly | Detailed condition survey as per IRC SP:35-1990 using | Cleaning of expansion joint gaps thoroughly |  |  | 3 days | MORTH specification s 2600 and |

|  | expansion joint | gap. |  | Mobile Bridge Inspection Unit |  |  | IRC SP: 40- 1993. |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | Drainage spouts | No down take pipe missing/broken below soffit of the deck slab. No silt, debris, clogging of drainage spout collection chamber. | Monthly | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | Cleaning of drainage spouts thoroughly. Replacement of missing/broken down take pipes with a minimum pipe extension of 500mm below soffit of slab. Providing sealant around the drainage spout if any leakages observed. | 3 days | MORTH specification 2700. |
| Bridge- substructure | Cracks/spalling of concrete/ rusted steel | No cracks, spalling of concrete and rusted steel | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge Inspection Unit | All the corroded reinforcement shall need to be thoroughly cleaned from rusting and applied with anti-corrosive coating before carrying out repairs to substructure by grouting/guniting and micro concreting depending on type of defect noticed | 30 days | IRC SP: 40- 1993 and MORTH specification 2800. |

|  | Bearings | Delamination of bearing reinforcement not more than 5%, cracking or tearing of rubber not more than 2 locations per side, no rupture ofreinforcement or rubber | Bi-Annually | Detailed condition survey as per IRC SP: 35-1990 using Mobile Bridge InspectionUnit | In case of failure of even one bearing on any pier/abutment, all the bearings on that pier/abutment shall be replaced, in order to get uniform load transfer on tobearings. | 3 months | MORTH specificatio n 2810and IRC SP: 40- 199. |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Bridge Foundations | Scouring around foundatio ns | Scouring shall not be lower than maximum scour level for the bridge | Bi-Annually | Condition survey and visual inspection as per IRC SP:35-1990 using Mobile Bridge Inspection Unit. In case of doubt, use Underwater camera for inspection of deep wells inmajor Rivers. | Suitable protection works around pier/abutment | 1 month | IRC SP: 40- 1993, IRC 83-2014, MORTH specificatio n 2500 |
|  | Protectio n works in good condition | Damaged of rough stone apron or bank revetment not more than 3 | 2 times in a year (before and after rainy season) | Condition survey as per IRC SP:35- 1990 | Repairs to damaged aprons andpitching. | 30 days after defect observatio n or 2 | IRC: SP 40- 1993 and IRC:SP:13- 2004. |

|  |  | sq.m, damage to solid apron (concrete apron) not more than 1 sq.m |  |  |  | weeks before onset of rainy season whichever is earlier. |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Note:Any Structure during the entire contract period which is found that does not complies with all requirements of this Table will be prepared, rehabilitated or even reconstructed under the scope of thecontractor. |  |  |  |  |  |  |  |

Table 4: Maintenance Criteria for Structures and Culverts:

Table 5: Maintenance Criteria for Hill Roads

In addition to above, for hill roads the following provisions for maintenance is also to done.

| Hill Roads |  |  |
| --- | --- | --- |
| (i) | Damage to Retaining wall/ Breast wall | 7 (Seven) days |
| (ii) | Landslides requiring clearance | 12 (Twelve) hours |
| (iii) | Snow requiring clearance | 24 (Twenty Four) hours |

### Note: For all tables 1 to 5 above, latest BIS & IRC standards (even those not indicated herewith) along with MoRTH specifications shall be binding for all maintenance activities.

A.	Flexible/Rigid Pavement

| Nature of Defect or deficiency |  |  |  |  | Time limit for repair/ rectification |
| --- | --- | --- | --- | --- | --- |
| (b) Granular earth shoulders, side slopes, drains and culverts |  |  |  |  |  |
| (i) | Variation by more than 1 % in the prescribed slope of camber/cross fall (shall not be less than the camber on the main carriageway) |  |  |  | 7 (seven) days |
| (ii) | Edge drop at shoulders exceeding 40 mm |  |  |  | 7 (seven) days |
| (iii) | Variation by more than 15% in the prescribed side (embankment) slopes |  |  |  | 30 (thirty) days |
| (iv) | Rain cuts/gullies in slope |  |  |  | 7 (seven) days |
| (v) | Damage to or silting of culverts and side drains |  |  |  | 7 (seven) days |
| (vi) | Desilting of drains in urban/semi- urban areas |  |  |  | 24 (twenty four) hours |
| (vii) | Railing, parapets, crash barriers |  |  |  | 7 (seven) days (Restore immediately if causing safety hazard) |
| (c) Road side furniture including road sign and pavement marking |  |  |  |  |  |
| (i) | Damage to shape or position, poor visibility or loss of retro- reflectivity |  |  |  | 48 (forty eight) hours |
| (ii) | Painting of km stone, railing, parapets, crash barriers |  |  |  | As and when required/ Once every year |
| (iii) | Damaged/missing replacement | signs | road | requiring | 7 (seven) days |
| (iv) | Damage to road mark ups |  |  |  | 7 (seven) days |
| (d) Road lighting |  |  |  |  |  |
| (i) | Any major failure of the system |  |  |  | 24 (twenty four) hours |
| (ii) | Faults and minor failures |  |  |  | 8 (eight) hours |
| (e) Trees and plantation |  |  |  |  |  |

| Nature of Defect or deficiency |  | Time limit for repair/ rectification |
| --- | --- | --- |
| (i) | Obstruction in a minimum head- room of 5 m above carriageway or obstruction in visibility of road signs | 24 (twenty four)hours |
| (ii) | Removal of fallen trees from carriageway | 4 (four) hours |
| (iii) | Deterioration in health of trees and bushes | Timely watering and treatment |
| (iv) | Trees and bushes requiring replacement | 30 (thirty) days |
| (v) | Removal of vegetation affecting sight line and road structures | 15 (fifteen) days |
| (f) Rest area |  |  |
| (i) | Cleaning of toilets | Every 4 (four) hours |
| (ii) | Defects in electrical, water and sanitary installations | 24 (twenty four) hours |
| (g) [Toll Plaza] |  |  |
| (h) | Other Project Facilities and Approach roads |  |
| (i) | Damage in approach roads, pedestrian facilities, truck lay- byes, bus-bays, bus-shelters, cattle crossings, [Traffic Aid Posts, Medical Aid Posts] and service roads | 15 (fifteen) days |
| (ii) | Damaged vehicles or debris on the road | 4 (four) hours |
| (iii) | Malfunctioning of the mobile crane | 4 (four) hours |
| Bridges |  |  |
| (a) Superstructure |  |  |
| (i) | Any damage, cracks, spalling/ scaling Temporary measures Permanent measures | within 48 (forty eight) hours within 15 (fifteen) days or as specified by the Authority’s Engineer |
| (b) Foundations |  |  |

| Nature of Defect or deficiency |  | Time limit for repair/ rectification |
| --- | --- | --- |
| (i) | Scouring and/or cavitations | 15 (fifteen) days |
| (c) Piers, abutments, return walls and wing walls |  |  |
| (i) | Cracks and damages including settlement and tilting, spalling, scaling | 30 (thirty) days |
| (d) Bearings (metallic) of bridges |  |  |
| (i) | Deformation, damages, tilting or shifting of bearings | 15 (fifteen) days Greasing of metallic bearings once in a year |
| (e) Joints |  |  |
| (i) | Malfunctioning of joints | 15 (fifteen) days |
| (f) Other items |  |  |
| (i) | Deforming of pads in elastomeric bearings | 7 (seven) days |
| (ii) | Gathering of dirt in bearings and joints; or clogging of spouts, weep holes and vent-holes | 3 (three) days |
| (iii) | Damage or deterioration in kerbs, parapets, handrails and crash barriers | 3 (three) days (immediately within 24 hours if posing danger to safety) |
| (iv) | Rain-cuts or erosion of banks of the side slopes of approaches | 7 (seven) days |
| (v) | Damage to wearing coat | 15 (fifteen) days |
| (vi) | Damage or deterioration in approach slabs, pitching, apron, toes, floor or guide bunds | 30 (thirty) days |
| (vii) | Growth of vegetation affecting the structure or obstructing the waterway | 15 (fifteen) days |
| (g) Hill Roads |  |  |
| (i) | Damage to retaining wall/breast wall | 7 (seven) days |
| (ii) | Landslides requiring clearance | 12 (twelve) hours |

| Nature of Defect or deficiency |  | Time limit for repair/ rectification |
| --- | --- | --- |
| (iii) | Snow requiring clearance | 24 (twenty four) hours |

[Note: Where necessary, the Authority may modify the time limit for repair/rectification, or add to the nature of Defect or deficiency before issuing the bidding document, with the approval	of	the	competent	authority.]

Schedule - F

(See Clause 4.1 (vii)(a)) Applicable Permits

### Applicable Permits

  - The Contractor shall obtain, as required under the Applicable Laws, the following Applicable Permits:

    - Permission of the State Government for extraction of boulders from quarry;

    - Permission of Village Panchayats and Pollution Control Board for installation of crushers;

    - License for use of explosives;

    - Permission of the State Government for drawing water from river/reservoir;

    - License from inspector of factories or other competent Authority for setting up batching plant;

    - Clearance of Pollution Control Board for setting up batching plant;

    - Clearance of Village Panchayats and Pollution Control Board for setting up asphalt plant;

    - Permission of Village Panchayats and State Government for borrow earth; and

    - Any other permits or clearances required under Applicable Laws.

  - Applicable Permits, as required, relating to environmental protection and conservation shall have been procured by the Authority in accordance with the provisions of this Agreement.

# Schedule – G

(See Clauses 7.1 and 19.2)

# Annex-I

(See Clause 7.1)

# Form of Bank Guarantee

[Performance Security/Additional Performance Security]

[DG(RD)&SS,

Ministry of Road Transport & Highways Transport Bhawan, New Delhi] WHEREAS:

- [name and address of contractor] (hereinafter called the “Contractor") and [Chief Engineer, NH PWD,Pension Bada,Raipur on behalf of Ministry of Road Transport and Highways ,New Delhi], (hereinafter called the “Authority”) have entered into an agreement (hereinafter called the “Agreement”) for the Construction of 4 nos. Bridges at Km 47.000 (Jhiram nalla), Km. 123.000 (Kerlapal nalla), Km. 127.800 (Bodaguda nalla) and Km. 137.400 (Dubbatota nalla) on NH-30 (Old NH-221) Jagdalpur-Sukma-Konta road in the state of Chhattisgarh] on Engineering, Procurement and Construction (the “EPC”) basis, subject to and in accordance with the provisions of the Agreement

- The Agreement requires the Contractor to furnish a Performance Security for due and faithful performance of its obligations, under and in accordance with the Agreement, during the {Construction Period/ Defects Liability Period and MaintenancePeriod}(asdefinedintheAgreement)inasumofRs…..cr.(Rupees

………..….. crore) (the “Guarantee Amount”).

- We, ………………….. through ourbranchat	(the “Bank”) have agreedto

furnish this bank guarantee (hereinafter called the “Guarantee”) by way of Performance Security.

NOW, THEREFORE, the Bank hereby, unconditionally and irrevocably, guarantees and affirms as follows:

- The Bank hereby unconditionally and irrevocably guarantees the due and faithful performance of the Contractor’s obligations during the {Construction Period/ Defects Liability Period and Maintenance Period} under and in accordance with the Agreement, and agrees and undertakes to pay to the Authority, upon its mere first written demand, and without any demur, reservation, recourse, contest or protest, and without any reference to the Contractor, such sum or sums up to an aggregate sum of the Guarantee Amount as the Authority shall claim, without the Authority being required to prove or to show grounds or reasons for its demand and/or for the sum specified therein.

- A letter from the Authority, under the hand of an officer not be low the rank of[General Manager in the National Highways Authority of India], that the Contractor has committed default in the due and faithful performance of all or any of its obligations under and in accordance with the Agreement shall  be conclusive, final and binding on the Bank. The Bank further agrees that the Authority shall be the sole judge as to whether the Contractor is in default in due and faithful performance of its obligations during and under the Agreement and its decision that the Contractor is in default shall be final and binding on the Bank, notwithstanding any differences between the Authority and the Contractor, or any dispute between them pending before any court, tribunal, arbitrators or any other authority or body, or by the discharge of the Contractor for any reason whatsoever.

- In order to give effect to this Guarantee, the Authority shall be entitled to act as if the Bank were the principal debtor and any change in the constitution of the Contractor and/or the Bank, whether by their absorption with any other body or corporation or otherwise, shall not in any way or manner affect the liability or obligation of the Bank under this Guarantee.

- It shall not be necessary, and the Bank hereby waives any necessity, for the Authority to proceed against the Contractor before presenting to the Bank its demand under this Guarantee.

- The Authority shall have the liberty, without affecting in any manner the liability of the Bank under this Guarantee, to vary at any time, the terms and conditions of the Agreement or to extend the time or period for the compliance with, fulfillment and/ or performance of all or any of the obligations of the Contractor contained in the Agreement or to postpone for any time, and from time to time, any of the rights and powers exercisable by the Authority against the Contractor, and either to enforce or forbear from enforcing any of the terms and conditions contained in the Agreement and/or the securities available to the Authority, and the Bank shall not be released from its liability and obligation under these presents by any exercise by the Authority of the liberty with reference to the matters aforesaid or by reason of time being given to the Contractor or any other forbearance, indulgence, act or omission on the part of the Authority or of any other matter or thing whatsoever which under any law relating to sureties and guarantors would but for this provision have the effect of releasing the Bank from its liability and obligation under this Guarantee and the Bank hereby waives all of its rights under any such law.

- This Guarantee is in addition to and not in substitution of any other guarantee or security now or which may hereafter be held by the Authority in respect of or relating to the Agreement or for the fulfillment, compliance and/or performance of all or any of the obligations of the Contractor under the Agreement.

- Notwithstanding anything contained hereinbefore, the liability of the Bank under this Guarantee is restricted to the Guarantee Amount and this Guarantee will remain in force for the period specified in paragraph 8 below and unless a demand or claim in writing is made by the Authority on the Bank under this Guarantee all rights of the Authority under this Guarantee shall before ited and the Bank shall be relieved from its liabilities hereunder.

- The Guarantee shall cease to be in force and effect on ****$. Unless a demand or claim under this Guarantee is made in writing before expiry of the Guarantee, the Bank shall be discharged from its liabilities here under.

- The Bank undertakes not to revoke this Guarantee during its currency, except with the previous express consent of the Authority in writing, and declares and warrants that it has the power to issue this Guarantee and the undersigned has full powers to do so on behalf of the Bank.

- Any notice by way of request, demand or otherwise hereunder may be sent by post addressed to the Bank at its above referred branch, which shall be deemed to have been duly authorized to receive such notice and to effect payment thereof forthwith, and if sent by post it shall be deemed to have been given at the time when it ought to have been delivered in due course of post and in proving such notice, when given by post, it shall be sufficient to prove that the envelope containing the notice was posted and a certificate signed by an officer of the Authority that the envelope was so posted shall be conclusive.

- This Guarantee shall come into force with immediate effect and shall remain in force and effect for up to the date specified in paragraph 8 above or until it is released earlier by the Authority pursuant to the provisions of the Agreement.

Signed and sealed this ………. day of ……….., 20……… at ………..

SIGNED, SEALED AND DELIVERED

For and on behalf of the Bank by:

(Signature) (Name) (Designation) (Code Number) (Address)

NOTES:

- Thebankguaranteeshouldcontainthename,designationandcodenumberofthe officer(s) signing the guarantee.

- The address, telephone number and other details of the head office of the Bank as

$ Insert date being 2 (two) years from the date of issuance of this Guarantee (in accordance with Clause 7.2 of the Agreement).

well as of issuing branch should be mentioned on the covering letter of issuing branch.

Annex – II (Schedule - G) (See Clause 19.2)

# Form for Guarantee for Advance Payment

[DG(RD)&SS,

Ministry of Road Transport & Highways Transport Bhawan, New Delhi] WHEREAS:

- [name and address of contractor] (hereinafter called the “Contractor") has executed an agreement (hereinafter called the “Agreement”) with the [Chief Engineer, NH PWD, Pension Bada, Raipur on behalf of Ministry of Road Transport and Highways ,New Delhi], (hereinafter called the “Authority”) for the construction of the Construction of 4 nos. Bridges at Km 47.000 (Jhiram nalla), Km. 123.000 (Kerlapal nalla), Km. 127.800 (Bodaguda nalla) and Km. 137.400 (Dubbatota nalla) on NH-30 (Old NH-221) Jagdalpur-Sukma-Konta road in the state of Chhattisgarh on Engineering, Procurement and Construction (the “EPC”) basis, subject to and in accordance with the provisions of the Agreement

- In accordance with Clause 19.2 of the Agreement, the Authority shall make to the Contractor an interest bearing @Bank Rate + 3% advance payment (herein after called“AdvancePayment”)equalto10%(tenpercent)oftheContractPrice;and that the Advance Payment shall be made in two installments subject to the Contractor furnishing an irrevocable and unconditional guarantee by a scheduled bank for an amount equivalent to 110% (one hundred and ten percent) of such installment to remain effective till the complete and full repayment of the installment of the Advance Payment as security for compliance with its obligations in accordance with the Agreement. The amount of {first/second} installment of the Advance Payment is Rs. ------ cr. (Rupees crore) andthe

amount of this Guarantee is Rs. ------- cr. (Rupees ------ crore) (the “Guarantee Amount”)$.

- We, ………………….. through our branch at	(the “Bank”) have agreed to

furnish this bank guarantee (hereinafter called the “Guarantee”) for the Guarantee Amount.

NOW, THEREFORE, the Bank hereby, unconditionally and irrevocably, guarantees and affirms as follows:

- The Bank hereby unconditionally and irrevocably guarantees the due and faithful repayment on time of the aforesaid installment of the Advance Payment under and in accordance with the Agreement, and agrees and undertakes to pay to the

$ The Guarantee Amount should be equivalent to 110% of the value of the applicable installment.

Authority, upon its mere first written demand, and without any demur, reservation, recourse, contest or protest, and without any reference to the Contractor, such sum or sums up to an aggregate sum of  the Guarantee Amount as the Authority shall claim, without the Authority being required to prove or to show grounds or reasons for its demand and/or for the sum specified therein.

A letter from the Authority, under the hand of an officer not below the rank of [General Manager in the National Highways Authority of India], that the Contractor has committed default in the due and faithful performance of all or any of its obligations for the repayment of the installment of the Advance Payment under and in accordance with the Agreement shall be conclusive, final and binding on the Bank. The Bank further agrees that the Authority shall be the sole judge as to whether the Contractor is in default in due and faithful performance of its obligations during and under the Agreement and its decision that the ContractorisindefaultshallbefinalandbindingontheBank,notwithstandingany differences between the Authority and the Contractor, or any dispute between them pending before any court, tribunal, arbitrators or any other authority or body, or by the discharge of the Contractor for any reason whatsoever.

- In order to give effect to this Guarantee, the Authority shall be entitled to act as if the Bank were the principal debtor and any change in the constitution of the Contractor and/or the Bank, whether by their absorption with any other body or corporation or otherwise, shall not in any way or manner affect the liability or obligation of the Bank under this Guarantee.

- It shall not be necessary, and the Bank hereby waives any necessity, for the Authority to proceed against the Contractor before presenting to the Bank its demand under this Guarantee.

- The Authority shall have the liberty, without affecting in any manner the liability of the Bank under this Guarantee, to vary at any time, the terms and conditions of the Advance Payment or to extend the time or period of its repayment or to postpone for any time, and from time to time, any of the rights and powers exercisable by the Authority against the Contractor, and either to enforce or forbear from enforcing any of the terms and conditions contained in the Agreement and/or the securities available to the Authority, and the Bank shall not be released from its liability and obligation under these presents by any exercise by the Authority of the liberty with reference to the matters aforesaid or by reason of time being given to the Contractor or any other forbearance, indulgence, act or omission on the part of the Authority or of any other matter or thing whatsoever which under any law relating to sureties and guarantors would but for this provision have the effect of releasing the Bank from its liability and obligation under this Guarantee and the Bank hereby waives all of its rights under any such law.

- This Guarantee is in addition to and not in substitution of any other guarantee or security now or which may hereafter be held by the Authority in respect of or relating to the Advance Payment.

- Notwithstanding anything contained hereinbefore, the liability of the Bank under this Guarantee is restricted to the Guarantee Amount and this Guarantee will remain in force for the period specified in paragraph 8 below and unless a demand or claim in writing is made by the Authority on the Bank under this Guarantee all rights of the Authority under this Guarantee shall be forfeited and the Bank shall be relieved from its liabilities here under.

- The Guarantee shall cease to be in force and effect on ****.$Unless a demand or claim under this Guarantee is made in writing on or before the aforesaid date, the Bank shall be discharged from its liabilities here under.

- The Bank undertakes not to revoke this Guarantee during its currency, except with the previous express consent of the Authority in writing, and declares and warrants that it has the power to issue this Guarantee and the undersigned has full powers to do so on behalf of the Bank.

- Any notice by way of request, demand or otherwise hereunder may be sent by post addressed to the Bank at its above referred branch, which shall be deemed to have been duly authorized to receive such notice and to effect payment thereof forthwith, and if sent by post it shall be deemed to have been given at the time when it ought to have been delivered in due course of post and in proving such notice, when given by post, it shall be sufficient to prove that the envelope containing the notice was posted and a certificate signed by an officer of the Authority that the envelope was so posted shall be conclusive.

- This Guarantee shall come into force with immediate effect and shall remain in force and effect up to the date specified in paragraph 8 above or until it is released earlier by the Authority pursuant to the provisions of the Agreement.

Signed and sealed this ………. day of ……….., 20……… at ………..

SIGNED, SEALED AND DELIVERED

For and on behalf of the Bank by:

(Signature) (Name) (Designation) (Code Number) (Address) NOTES:

- The bank guarantee should contain the name, designation and code number of the officer(s) signing the guarantee.

$ Insert a date being 90 (ninety) days after the end of one year from the date of payment of the Advance payment to the Contractor (in accordance with Clause 19.2 of the Agreement).

- The address, telephone number and other details of the head office of the Bank as well as of issuing branch should be mentioned on the covering letter of issuing branch.

## SCHEDULE - H

See Clauses10.1 (iv) and 19.3

Contract Price Weight ages

  - The contract price for this agreement is Rs 2181.02 Lakhs (including GST)

  - Proportions of the Contract Price for different Stages of Construction of the Project Highway shall be considered.

| Item | Weightage in Percentage to the contract Price | Stage of Payment | Percentage Weightage |
| --- | --- | --- | --- |
| 1 | 2 | 3 | 4 |
| Road works including culverts, widening and repair of culverts. | 0.00% | A- Widening and strengthening |  |
|  |  | of existing road |  |
|  |  | (1) Earthwork up to top of the sub- grade | 0.00% |
|  |  | (2) Sub-Base Course | 0.00% |
|  |  | (3) Non Bituminous Base Course | 0.00% |
|  |  | (4) Bituminous Base Course works | 0.00% |
|  |  | (5) Wearing Coat | 0.00% |
|  |  | (6) Widening and repair of culverts | 0.00% |
|  |  | B- Reconstruction/ New 2-lane realignment/ bypass (Flexible pavement) |  |
|  |  | (1) Earthwork up to top of the sub- grade | 0.00% |
|  |  | (2) Sub-Base Course | 0.00% |
|  |  | (3) Non Bituminous Base Course | 0.00% |
|  |  | (4) Bituminous Base Course works | 0.00% |
|  |  | (5) Wearing Coat | 0.00% |
|  |  | C- Reconstruction/ New service road (Flexible pavement) |  |
|  |  | (1) Earthwork up to top of the sub- grade | 0.00% |
|  |  | (2) Sub-Base Course | 0.00% |
|  |  | (3) Non Bituminous Base Course | 0.00% |
|  |  | (4) Bituminous Base Course works | 0.00% |
|  |  | (5) Wearing Coat | 0.00% |
|  |  | D- Re-Construction and New culverts on existing road, realignments, bypasses: |  |
|  |  | Culverts (length < 6 m) | 0.00% |
| Minor Bridges/ Underpasses/ Overpasses | 40.51% | A.1- Widening and Repair of Minor bridges (length > 6m and < 60 m) |  |
|  |  | Minor bridges | 0.00% |
|  |  | A.2- New Minor bridges (length >6 and <60 m.) |  |
|  |  | (1) Foundation + Sub-Structure: On completion of the foundation work including foundations for wind and return walls, abutments, piers upto the abutment/pier cap. | 41.01% |
|  |  | Km. 123.000 (Kerlapal Nalla) | 53.31% |
|  |  | Km. 137.400 (Dubbatota Nalla) | 46.69% |
|  |  | (2) Super-Structure: On Completion of the super-structure in all respects in all respects including wearing coat, bearings, expansion joints, hand rails, crash barriers, road signs & markings, tests on completion etc. complete in all respect. | 26.18% |
|  |  | Km. 123.000 (Kerlapal Nalla) | 50.37% |
|  |  | Km. 137.400 (Dubbatota Nalla) | 49.63% |
|  |  | (3) Approaches : On completion of approaches including Retaining walls, stone pitching, protection works complete in all respect and fit for use. | 32.81% |
|  |  | Km. 123.000 (Kerlapal Nalla) | 54.59% |
|  |  | Km. 137.400 (Dubbatota Nalla) | 45.41% |
|  |  | (4) Guide Bunds and River Training Works : On completion of guide bunds and river Training works complete in all respects . | 0.00% |
|  |  | Km. 123.000 (Kerlapal Nalla) | 0 |
|  |  | Km. 137.400 (Dubbatota Nalla) | 0 |
|  |  | B.1-Widening and Repair of underpasses/overpasses | 0 |
|  |  | B.2-New underpasses/Overpasses | 0 |
| Major Bridge (length > 60 m.) works and ROB/ RUB/ elevated sections/flyovers including viaducts, if any | 57.07% | A.1- Widening and repairs of Major Bridges |  |
|  |  | Major Bridge (length > 60 m.) | 0.00% |
|  |  | A.2- New Major Bridges |  |
|  |  | (1) Foundation | 25.16% |
|  |  | Km. 47.000 (Jiram Nalla) | 54.56% |
|  |  | Km. 127.800 (Bodaguda Nalla) | 45.44% |
|  |  | (2) Sub-structure | 14.65% |
|  |  | Km. 47.000 (Jiram Nalla) | 55.89% |
|  |  | Km. 127.800 (Bodaguda Nalla) | 44.11% |
|  |  | (3) Super-structure (including bearings) | 28.18% |
|  |  | Km. 47.000 (Jiram Nalla) | 56.74% |
|  |  | Km. 127.800 (Bodaguda Nalla) | 43.26% |
|  |  | (4) Wearing Coat including expansion joints | 3.08% |
|  |  | Km. 47.000 (Jiram Nalla) | 57.13% |
|  |  | Km. 127.800 (Bodaguda Nalla) | 42.87% |
|  |  | (5) Miscellaneous Items like hand rails, crash barriers etc.), Wing walls/return walls, Guide Bunds, River Training works etc. | 1.72% |
|  |  | Km. 47.000 (Jiram Nalla) | 57.04% |
|  |  | Km. 127.800 (Bodaguda Nalla) | 42.96% |
|  |  | (6) Approaches (including Toe walls, stone pitching and protection works) | 27.21% |
|  |  | Km. 47.000 (Jiram Nalla) | 37.84% |
|  |  | Km. 127.800 (Bodaguda Nalla) | 62.16% |
| Other Works | 1.84% | (i) Road signs Board, markings, km stones, safety devices like transverse rumble strip, pedestrian guard rail, overhead traffic signs etc. | 100.00% |
|  |  | Km. 47.000 (Jiram Nalla) | 32.09% |
|  |  | Km. 123.000 (Kerlapal Nalla) | 15.80% |
|  |  | Km. 127.800 (Bodaguda Nalla) | 34.36% |
|  |  | Km. 137.400 (Dubbatota Nalla) | 17.75% |
| Utility Shifting | 0.58% | (1) Utility Shifting | 100.00% |
|  |  | (i) Electrical Pole Shifting (Km. 47.000 (Jiram Nalla)) | 84.20% |
|  |  | (ii) Solar Street Pole Shifting (Km. 123.000 (Kerlapal Nalla)) | 15.80% |
|  |  | (2) PHE | 0.00% |

1.3 Procedure of estimating the value of work done

1.3.1 Road Works:

Table 1.3.1

| Stage of Payment | Percentage Weight age | Payment Procedure |
| --- | --- | --- |
| A-Widening and Strengthening of existing road | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length. |
| B1- New 4-lane realignment/ bypass (Flexible pavement | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length. |
| B.2- Reconstruction/New 2-lane realignment/bypass (Rigid pavement) | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length. |  |
| C.1-Reconstruction/ New service road (Flexible pavement) | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 5(five) km. length, whichever is less.. |  |
| C.2- Reconstruction/ New service road (Rigid pavement) | 0.00% | Unit of measurement is linear length. Payment of each stage shall be made on pro rata basis on completion of a stage in full length or 5(five) km. length, whichever is less.. |  |
| D- Re-Construction and New culverts on existing road, realignments, bypasses: | 0.00% | Cost of each culvert shall be determined on pro rata basis with respect to the total number of culverts. Payment shall be made on the completion of at least five culverts. |  |

## @. For example, if the total length of bituminous work to be done is 100 km, the cost per km of bituminous work shall be determined as follows:

Cost per km = P x weight age for road work x weight age for bituminous work x (1/L)

Where P= Contract Price L = Total length in km

Similarly, the rates per km for other stages shall be worked out accordingly.

Note: The length affected due to law and order problems or litigation during execution due to which the Contractor is unable to execute the work, may be deducted from the total project length for payment purposes. The total length calculated here is only for payment purposes and will not affect and referred in other clauses of the Contract Agreement.

1.3.2 Minor Bridges and Underpasses/Overpasses:- 40.51%

Procedure	for	estimating	the	value	of	Minor	bridge	and Underpasses/Overpasses shall be as stated in table1.3.2:

Table 1.3.2

| Stage of Payment | Weight age | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| A.1-Widening and repair of minor bridges (length > 6m and < 60m) | 0.00% |  |
| A.2- New minor bridges | 100.00% |  |
| (i) Foundation + Sub-Structure: On completion of the foundation work including foundations for wing and return walls,abutments, piers up to the abutment/pier cap. | 41.01% | (i) Foundation + Sub structure : Cost of each bridge shall be determined on pro rata basis with respect to the total linear length (m) of the minor bridges. Payment against foundation + sub-structure shall be made on pro rata basis i.e not less than 25% of the scope of the foundation + sub-structure of each bridge subject to completion of at-least two foundation along with sub-structure up to abutment/pier cap level of each bridge. In case where load testing is required for foundation , the trigger of first payment shall include load testing also where specified. |
| Km. 123.000 (Kerlapal Nalla) | 53.31% |  |
| Km. 137.400 (Dubbatota Nalla) | 46.69% |  |
| (ii) Super-structure: On completion of the super structure in all respects including hand rails/crash barriers, wing walls, expansion joints,wearing coat if any, tests on completion etc., bridge complete in all respects and fit for use. | 26.18% | (ii) Super-structure : Payment shall be made on pro rata basis on completion of a stage i.e completion of super-structure of at-least one span in all respects as specified in the column of "stage of payment" in this sub-clause of the minor Bridges. |
| Km. 123.000 (Kerlapal Nalla) | 50.37% |  |
| Km. 137.400 (Dubbatota Nalla) | 49.63% |  |
| (iii) Approaches: On completion of approaches including retaining walls, stone pitching, protection works complete in all respect and fit for use. | 32.81% | (iii) Approaches : Payment shall be made on pro rata basis on completion of a stage i.e completion of approaches in all respect as specified in the column of "stage of payment" in this sub-clause of the minor Bridge. |
| Km. 123.000 (Kerlapal Nalla) | 54.59% |  |
| Km. 137.400 (Dubbatota Nalla) | 45.41% |  |
| (iv) Guide Bunds and River Training Works : On the completion of Guide Bunds and river training works complete in all respects. | 0.00% | (iv) Guide Bunds and river training Works: Payment shall be made on pro rata basis on completion of a stage i.e completion of guide Bunds and River training Works in all respects as specified of the minor Bridge. |
| Km. 123.000 (Kerlapal Nalla) | 0.00% |  |
| Km. 137.400 (Dubbatota Nalla) | 0.00% |  |

1.3.3 Major Bridge works :- 57.07%

Procedure for estimating the value of Major Bridge works, ROB/RUB and Structures shall be as stated in table 1.3.3:

Table 1.3.3

| Stage of Payment | Weightage | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| A.1- Widening and repairs of Major Bridges | 0.00% |  |
| A.2- New Major Bridges | 100.00% |  |
| (i) Foundation | 25.16% | (i) Foundation: Cost of each Major Bridge shall be determined on pro rata basis with respect to the total linear length (m) of the Major Bridge. Payment against foundation shall be made on pro- rata basis on completion of a stage i.e. not less than 25% of the scope of foundation of the Major Bridge subject to completion of at least two foundations of the major Bridge. In case where load testing is required for foundation, the trigger of first payment shall include load testing also where specified of the major Bridge. |
| Km. 47.00 (Jhiram Nalla) | 54.56% |  |
| Km. 127.800 (Bodaguda Nalla) | 45.44% |  |
| (ii) Sub-structure | 14.65% | (ii) Sub-Structure: Payment against Sub- structure shall be made on pro-rata basis on completion of a stage i.e. not less than 25% of the scope of sub- structure of the major bridge subject to completion of atleast two sub-structures of abutments/piers upto abutment/pier cap level of the major bridge. |
| Km. 47.00 (Jhiram Nalla) | 55.89% |  |
| Km. 127.800 (Bodaguda Nalla) | 44.11% |  |
| (iii) Super-Structure | 28.18% | (iii) Super-structure: Payment shall be made on pro-rata basis on completion of a stage i.e. completion of super-structure including bearings of atleast one span in all respects as specified of the major Bridge. |
| Km. 47.00 (Jhiram Nalla) | 56.74% |  |
| Km. 127.800 (Bodaguda Nalla) | 43.26% |  |
| (iv) Wearing Coat | 3.08% | (iv) Wearing Coat: Payment shall be made on completion of wearing coat including expansion joints complete in all respects as specified of the major Bridge. |
| Km. 47.00 (Jhiram Nalla) | 57.13% |  |
| Km. 127.800 (Bodaguda Nalla) | 42.87% |  |
| (v) Miscellaneous | 1.72% | (v) Miscellaneous: Payments shall be made on completion of all miscellaneous works like hand rails, crash barriers, road markings etc. complete in all respects as specified. |
| Km. 47.00 (Jhiram Nalla) | 57.04% |  |
| Km. 127.800 (Bodaguda Nalla) | 42.96% |  |
| (vi) Approaches | 27.21% | (vi) Approaches: Payments shall be made on completion of both approaches including stone pitching, protection works, etc. complete in all respects as specified. |
| Km. 47.00 (Jhiram Nalla) | 37.84% |  |
| Km. 127.800 (Bodaguda Nalla) | 62.16% |  |

Note:(1)	In case of innovate Major Bridge projects like cable suspension/cable stayed/ Extra Dozed and exceptionally long span bridges, the schedule may be modified as per site requirements before bidding with due approval of Competent Authority.

(2)	The Schedule for exclusive tunnel projects may be prepared as per site requirements before bidding with due approval of Competent Authority.

## 1.3.4 Other works:-  1.84%

Procedure for estimating the value of other works done shall be as stated in table 1.3.4.

Table 1.3.4

| Stage of Payment | Weight age | Payment Procedure |
| --- | --- | --- |
| - Road signs, markings, km stones, safety devices, like transverse rumble strip, pedestrian guard rail, over head traffic signs etc. | 100.00% | Payments shall be made on completion of all Road signs, markings, km stones, safety devices, like transverse rumble strip, pedestrian guard rail, over head traffic signs etc. Of each Bridge in all respect |
| Km. 47.000 (Jiram Nalla) | 32.09% |  |
| Km. 123.000 (Kerlapal Nalla) | 15.80% |  |
| Km. 127.800 (Bodaguda Nalha) | 34.36% |  |
| Km. 137.400 (Dubbatota Nalla) | 17.75% |  |

1.3.5 UTILITY SHIFTING :-  0.58%

1.3.5 Electrical, Solar pole and public Health Utilities (Water pipe fines and sewage lines)

Procedure for estimating the value of other works done shall be as stated in:

Table 1.3.5

| Stage of Payment | Weightage | Payment Procedure |
| --- | --- | --- |
| 1 | 2 | 3 |
| (1) Utility Shifting | 100.00% | Payment is divided in following activities and Payment of each activity shall be made on prorata basis on completion of 5km of linear project length. Removal of existing utility; 30%. Erection/ Laying; 30%. Commissioning; 40%. Dismantling will include proper listing and stocking of usable and non-usable items. Commissioning will be completed on furnishing the commissioning certificate from concerned utility owning department. |
| (i) Electrical Utility Shifting Km. 47.000 (Jiram Nalla) | 84.20% |  |
| (ii) Solar Pole Shifting Km. 123.000 (Kerlapal Nalla) | 15.80% |  |
| (2) PHE | 0.00% |  |

# 2	Procedure for payment for Maintenance

## The cost for maintenance shall be as stated in Clause14.1.1.

Payment for Maintenance shall be made in quarterly installments in accordance with the provisions of Clause19.7

Schedule - I

(See Clause 10.2 (iv))

# Drawings

### Drawings

In compliance of the obligations set forth in Clause 10.2 of this Agreement, the Contractor shall furnish to the Authority’s Engineer, free of cost, all Drawings listed in Annex-I of this Schedule-I.

### Additional Drawings

If the Authority’s Engineer determines that for discharging its duties and functions under this Agreement, it requires any drawings other than those listed in Annex-I, it may by notice require the Contractor to prepare and furnish such drawings forthwith. Upon receiving a requisition to this effect, the Contractor shall promptly prepare and furnish such drawings to the Authority’s Engineer, as if such drawings formed part of Annex-I of this Schedule-I.

# Annex – I

(Schedule - I)

### List of Drawings

A minimum list of drawings of the various components/elements of the Project Highway and project facilities required to be submitted by the Concessionaire is given below;

- Drawing of plan, Profile and cross-sections.

- Drawing of cross-drainage

- Drawing of Major/Minor intersections, Grade Separator and all type of structures.

- Drawing of road furniture including traffic signage, marking, safety barriers etc.

- Drawing of traffic diversion plan

- Drawing of street lighting.

- Drawing of Rain Water Harvesting unit.

- Drawing of Stair Case (Railway Portion)

- General arrangement showing area of base camp and administrative block.

- Drawing as per instruction of Authority’s Engineer.

# Schedule - J

(See Clause 10.3 (ii))

# Project Completion Schedule

### Project Completion Schedule

During Construction period, the Contractor shall comply with the requirements set forth in this Schedule-J for each of the Project Milestones and the Scheduled Completion Date. Within 15 (fifteen) days of the date of each Project Milestone, the Contractor shall notify the Authority of such compliance along with necessary particulars thereof.

### Project Milestone-I

  - Project Milestone-I shall occur on the date falling on the 255 days[35% of the Scheduled Construction Period] day from the Appointed Date (the “Project Milestone-I”).

  - Prior to the occurrence of Project Milestone-I, the Contractor shall have commenced construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 10% (ten per cent) of the Contract Price.

### Project Milestone-II

  - Project Milestone-II shall occur on the date falling on the 438 days[60% of the Scheduled Construction Period] day from the Appointed Date (the “Project Milestone-II”

  - Prior to the occurrence of Project Milestone-II, the Contractor shall have continued with construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 35% (thirty five per cent) of the Contract Price and should have started construction of all bridges

### Project Milestone-III

  - Project Milestone-III shall occur on the date falling on the 620 days [85% of the Scheduled Construction Period] day from the Appointed Date (the “Project Milestone-III”).

  - Prior to the occurrence of Project Milestone-III, the Contractor shall have continued with construction of the Project Highway and submitted to the Authority duly and validly prepared Stage Payment Statements for an amount not less than 70% (seventy per cent) of the Contract Price and should have started construction of all project facilities.

### Scheduled Completion Date

- The Scheduled Completion Date shall occur on the 730 days [Scheduled Construction Period] day from the Appointed Date.

- On or before the Scheduled Completion Date, the Contractor shall have completed construction in accordance with this Agreement.

### Extension of time

Upon extension of any or all of the aforesaid Project Milestones or the Scheduled Completion Date, as the case may be, under and in accordance with the provisions of this Agreement, the Project Completion Schedule shall be deemed to have been amended accordingly.

# Schedule - K

(See Clause 12.1 (ii))

# Tests on Completion

### Schedule for Tests

  - The Contractor shall, no later than 30 (thirty) days prior to the likely completion of construction, notify the Authority’s Engineer and the Authority of its intent to subject the Project Highway to Tests, and no later than 10(ten) days prior to the actual date of Tests, furnish to the Authority’s Engineer and the Authority detailed inventory and particulars of all works and equipment forming part of Works.

  - The Contractor shall notify the Authority’s Engineer of its readiness to subject the Project Highway to Tests at any time after 10 (ten) days from the date of such notice, and upon receipt of such notice, the Authority’s Engineer shall, in consultation with the Contractor, determine the date and time for each Test and notify the same to the Authority who may designate its representative to witness the Tests. The Authority’s Engineer shall thereupon conduct the Tests itself or cause any of the Tests to be conducted in accordance with Article 12 and this Schedule-K.

### Tests

  - Visual and physical test: The Contractor shall conduct a visual and physical check of construction to determine that all works and equipment forming part thereof conform to the provisions of this Agreement in the presence of Authority Engineer. The physical tests shall include all tests as per instruction of Authority Engineer.

  - Riding quality test: Riding quality of each lane of the carriageway shall be checked with the help of a Network Survey Vehicle (NSV) fitted with latest equipments and the maximum permissible roughness for purposes of this Test shall be [2,000 (two thousand)] mm for each kilometer.

  - Tests for bridges: All major and minor bridges shall be subjected to the rebound hammer and ultrasonic pulse velocity tests, to be conducted in accordance with the procedure described in Special Report No. 17: 1996 of the IRC Highway Research Board on Nondestructive Testing Techniques, at two spots in every span, to be chosen at random by the Authority’s Engineer. Bridges with a span of 15 (fifteen) meters or more shall also be subjected to load testing.

  - Other tests: The Authority’s Engineer may require the Contractor to carry out or  cause to be carried additional tests, in accordance with Good Industry Practice, for determining the compliance of the Project Highway with Specifications and  Standards, except tests as specified in clause 5,but shall include measuring the reflectivity of road markings and road signs; and measuring the illumination level (lux) of lighting using requisite testing equipment.

  - Environmental audit: The Authority’s Engineer shall carry out a check to determine conformity of the Project Highway with the environmental requirements set forth in Applicable Laws and Applicable Permits.

  - Safety Audit: The Authority’s Engineer shall carry out, or cause to be carried out, a safety audit to determine conformity of the Project Highway with the safety requirements and Good Industry Practice.

### Agency for conducting Tests

All Tests set forth in this Schedule-K shall be conducted by the Authority’s Engineer or such other agency or person as it may specify in consultation with the Authority.

### Completion Certificate

Upon successful completion of Tests, the Authority’s Engineer shall issue the Completion Certificate in accordance with the provisions of Article 12.

- Contractor will carry out tests with following equipment at his own cost in the presence of Authority Engineer's representative.

| Sr. No. | Key metrics of Asset |  | Equipment to be used |  | Frequency of condition survey |
| --- | --- | --- | --- | --- | --- |
| 1 | Surface defects pavement | of | Network Vehicle (NSV) | Survey | At least twice a year (As per survey months defined for the state basis rainy season) |
| 2 | Roughness of pavement |  | Network Vehicle (NSV) | Survey | At least twice a year (As per survey months defined for the state basis rainy season) |
| 3 | Strength pavement | of | Falling Weight Deflectometer(FWD) |  | At least once a year |
| 4 | Bridges |  | Mobile Bridge Inspection Unit(MBU) |  | At least twice a year (As per survey months defined for the state basis rainy season) |
| 5 | Road signs |  | Retro-reflectometer |  | At least twice a year (As per survey months defined for the state basis rainy season) |

The first testing with the help of NSV shall be conducted at the time of issue of Completion Certificate.

# Schedule - L

(See Clause 12.2)

# Completion Certificate

- I, ……………………. (Name of the Authority’s Engineer), acting as the Authority’s Engineer,   under    and   in    accordance    with    the Agreement  dated	(the

“Agreement”), for [Construction of 4 nos. Bridges at Km 47.000 (Jhiram nalla), Km. 123.000 (Kerlapal nalla), Km. 127.800 (Bodaguda nalla) and Km. 137.400 (Dubbatota nalla) on NH-30 (Old NH-221) Jagdalpur-Sukma-Konta road in the state of Chhattisgarh on Engineering, Procurement and Construction        (EPC)     basis through	(Name of Contractor),hereby

certify that the Tests in accordance with Article 12 of the Agreement have been successfully undertaken to determine compliance of the Project Highway with the provisions of the Agreement, and I am satisfied that the Project Highway can be safely and reliably placed in service of the Users thereof.

- It is certified that, in terms of the aforesaid Agreement, all works forming part of Project Highway have been completed, and the Project Highway is hereby declared fit for entry into operation on this the………day of………20…,Scheduled Completed

Date for which was the ……… day of ………20…..

SIGNED, SEALED ANDDELIVERED

For and on behalf of the Authority’s Engineer by:

(Signature)

(Name) (Designation)(Address)

# Schedule - M

(See Clauses 14.6, 15.2 and 19.7)

# Payment Reduction for Non-Compliance

### Payment reduction for non-compliance with the Maintenance Requirements

  - Monthly lump sum payments for maintenance shall be reduced in the case of non- compliance with the Maintenance Requirements set forth in Schedule-E.

  - Any deduction made on account of non-compliance with the Maintenance Requirements shall not be paid even after compliance subsequently. The deductions shall continue to be made every month until compliance is done.

  - The Authority’s Engineer shall calculate the amount of payment reduction on the basis of weight age in percentage assigned to non-conforming items as given in Paragraph2.

### Percentage reductions in lump sum payments on monthly basis

  - The following percentages shall govern the payment reduction:

| S. No. | Item/Defect/Deficiency | Percentage |
| --- | --- | --- |
| (a) | Carriageway/Pavement |  |
| (i) | Potholes, cracks, other surface defects | 15% |
| (ii) | Repairs of Edges, Rutting | 5% |
| (b) | Road, Embankment, Cuttings, Shoulders |  |
| (i) | Edge drop, inadequate cross fall, undulations, settlement, potholes, ponding, obstructions | 10% |
| (ii) | Deficient slopes, raincuts, disturbed pitching, vegetation growth, pruning of trees | 5% |
| (c) | Bridges and Culverts |  |
| (i) | Desilting, cleaning. vegetation growth, damaged pitching, flooring, parapets, wearing course, footpaths, any damage to foundations | 20% |
| (ii) | Any Defects in superstructures, bearings and sub-structures | 10% |

| S. No. | Item/Defect/Deficiency | Percentage |
| --- | --- | --- |
| (iii) | Painting, repairs/replacement kerbs, railings, parapets, guideposts/crash barriers | 5% |
| (d) | Roadside Drains |  |
| (i) | Cleaning and repair of drains | 5% |
| (e) | Road Furniture |  |
| (i) | Cleaning, painting, replacement of road signs, delineators, road markings, 200 m/km/5th km stones | 5% |
| (f) | Miscellaneous Items |  |
| (i) | Removal of dead animals, broken down/accidented vehicles, fallen trees, road blockades or malfunctioning of mobile crane | 10% |
| (ii) | Any other Defects in accordance with paragraph 1. | 5% |
| (g) | Defects in Other Project Facilities | 5% |

  - The amount to be deducted from monthly lump-sum payment for non- compliance of particular item shall be calculated asunder:

Where,

P=	Percentage of particular item/Defect/deficiency for deduction

M1= Monthly lump-sum payment in accordance para 1.2 above of this Schedule M2= Monthly lump-sum payment in accordance para 1.2 above of this Schedule L1= Non-complying length L = Total length of the road,

R= Reduction (the amount to be deducted for non-compliance for a particular item/Defect/deficiency

The total amount of reduction shall be arrived at by summation of reductions for such items/Defects/deficiency or non-compliance.

For any Defect in a part of one kilometer, the non-conforming length shall be taken as one kilometer.

# Schedule - N

(See Clause 18.1 (i))

# Selection of Authority’s Engineer

### Selection of Authority’s Engineer

  - The provisions of the Model Request for Proposal for Selection of Technical Consultants, issued by the Ministry of Finance in May 2009, or any substitute thereof shall apply for selection of an experienced firm to discharge the functions and duties of an Authority’s Engineer.

  - In the event of termination of the Technical Consultants appointed in accordance with the provisions of Paragraph 1.1, the Authority shall appoint another firm of Technical Consultants forthwith and may engage a government-owned entity in accordance with the provisions of Paragraph 3 of this Schedule-N.

### Terms of Reference

The Terms of Reference for the Authority’s Engineer (the “TOR”) shall substantially conform with Annex 1 to this Schedule N.

### Appointment of Government entity as Authority’s Engineer

Notwithstanding anything to the contrary contained in this Schedule, the Authority may in its discretion appoint a government-owned entity as the Authority’s Engineer; provided that such entity shall be a body corporate having as one of its primary functions the provision of consulting, advisory and supervisory services for engineering projects; provided further that a government-owned entity which is owned or controlled by the Authority shall not be eligible for appointment as Authority’s Engineer.

Annex – I (Schedule - N)

### Terms of Reference for Authority’s Engineer

- Scope

- TheseTermsofReference(the“TOR”)fortheAuthority’sEngineerarebeingspecified pursuant to the EPC Agreement dated ........... (the “Agreement), which has been enteredintobetweenthe[nameandaddressoftheAuthority](the“Authority”)and

.......... (the “Contractor”)# Construction of 4 nos. Bridges at Km 47.000 (Jhiram nalla), Km. 123.000 (Kerlapal nalla), Km. 127.800 (Bodaguda nalla) and Km. 137.400 (Dubbatota nalla) on NH-30 (Old NH-221) Jagdalpur-Sukma-Konta road in the state of Chhattisgarh on Engineering, Procurement, Construction (EPC) basis, and a copy of which is annexed hereto and marked as Annex-A to form part of this TOR.

# - In case the bid of Authority’s Engineer is invited simultaneously with the bid of EPC project, then the status of bidding of EPC project only to be indicated

- The TOR shall apply to construction and maintenance of the Project Highway.

### Definitions and interpretation

- The words and expressions beginning with or in capital letters and not defined herein but defined in the Agreement shall have, unless repugnant to the context, the meaning respectively assigned to them in the Agreement.

- References to Articles, Clauses and Schedules in this TOR shall, except where the context otherwise requires, be deemed to be references to the Articles, Clauses and Schedules of the Agreement, and references to Paragraphs shall be deemed to be references to Paragraphs of this TOR.

- The rules of interpretation stated in Article 1 of the Agreement shall apply, mutatis mutandis, to this TOR.

### General

- The Authority’s Engineer shall discharge its duties in a fair, impartial and efficient manner, consistent with the highest standards of professional integrity and Good Industry Practice.

- The Authority’s Engineer shall perform the duties and exercise the authority in accordance with the provisions of this Agreement, but subject to obtaining prior written approval of the Authority before determining:

  - any Time Extension;

  - any additional cost to be paid by the Authority to the Contractor;

  - the Termination Payment; or

  - issuance of Completion Certificate or

  - any other matter which is not specified in (a), (b), (c) or (d) above and which creates a financial liability on either Party.

- The Authority’s Engineer shall submit regular periodic reports, at least once every month, to the Authority in respect of its duties and functions under this Agreement. Such reports shall be submitted by the Authority’s Engineer within 10 (ten) days of the beginning of every month.

- The Authority’s Engineer shall inform the Contractor of any delegation of its duties and responsibilities to its suitably qualified and experienced personnel; provided, however, that it shall not delegate the authority to refer any matter for the Authority’s prior approval in accordance with the provisions of Clause18.2.

- The Authority’s Engineer shall aid and advise the Authority on any proposal for Change of Scope under Article13.

- In the event of any disagreement between the Parties regarding the meaning, scope and nature of Good Industry Practice, as set forth in any provision of the Agreement, the Authority’s Engineer shall specify such meaning, scope and nature by issuing a reasoned written statement relying on good industry practice and authentic literature.

### Construction Period

- During the Construction Period, the Authority’s Engineer shall review and approve the Drawings furnished by the Contractor along with supporting data, including the geo-technical and hydrological investigations, characteristics of materials from borrow areas and quarry sites, topographical surveys, and the recommendations of the Safety Consultant in accordance with the provisions of Clause 10.1 (vi). The Authority’s Engineer shall complete such review and approval and send its observations to the Authority and the Contractor within 15 (fifteen) days of receipt of such Drawings; provided, however that in case of a Major Bridge or Structure, the aforesaid period of 15 (fifteen) days may be extended upto 30 (thirty) days. In particular, such comments shall specify the conformity or otherwise of such Drawings with the Scope of the Project and Specifications and Standards.

- The Authority’s Engineer shall review and approve any revised Drawings sent to it by the Contractor and furnish its comments within 10 (ten) days of receiving such Drawings.

- The Authority’s Engineer shall review and approve the Quality Assurance Plan submitted by the Contractor and shall convey its comments to the Contractor within a period of 21 (twenty one) days stating the modifications, if any, required thereto.

- The Authority’s Engineer shall complete the review and approve of the methodology proposed to be adopted by the Contractor for executing the Works, and convey its comments to the Contractor within a period of 10 (ten) days from the date of receipt of the proposed methodology from the Contractor.

- The Authority’s Engineer shall grant written approval to the Contractor, where necessary, for interruption and diversion of the flow of traffic in the existing lane(s) of the Project Highway for purposes of maintenance during the Construction Period in accordance with the provisions of Clause10.4.

- The Authority’s Engineer shall review the monthly progress report furnished by the Contractor and send its comments thereon to the Authority and the Contractor within 7 (seven) days of receipt of such report.

- The Authority’s Engineer shall inspect the Construction Works and the Project Highway and shall submit a monthly Inspection Report bringing out the results of inspections and the remedial action taken by the Contractor in respect of Defects or deficiencies. In particular, the Authority’s Engineer shall include in its Inspection Report, the compliance of the recommendations made by the Safety Consultant.

- The Authority’s Engineer shall conduct the pre-construction review of manufacturer's test reports and standard samples of manufactured Materials, and such other Materials as the Authority’s Engineer may require.

- For determining that the Works conform to Specifications and Standards, the Authority’s Engineer shall require the Contractor to carry out, or cause to be carried out, tests at such time and frequency and in such manner as specified in the Agreement and in accordance with Good Industry Practice for quality assurance. For purposes of this Paragraph 4 (ix), the tests specified in the IRC Special Publication-11 (Handbook of Quality Control for Construction of Roads and Runways) and the Specifications for Road and Bridge Works issued by MORTH (the “Quality Control Manuals”) or any modification/substitution thereof shall be deemed to be tests conforming to Good Industry Practice for quality assurance.

- The Authority’s Engineer shall test check at least 50 (fifty) percent of the quantity or number of tests prescribed for each category or type of test for quality control by the Contractor.

- The timing of tests referred to in Paragraph 4 (ix), and the criteria for acceptance/ rejection of their results shall be determined by the Authority’s Engineer in accordance with the Quality Control Manuals. The tests shall be undertaken on a random sample basis and shall be in addition to, and independent of, the tests that may be carried out by the Contractor for its own quality assurance in accordance with Good Industry Practice.

- In the event that results of any tests conducted under Clause 11.10 establish any Defects or deficiencies in the Works, the Authority’s Engineer shall require the Contractor to carry out remedial measures.

- The Authority’s Engineer may instruct the Contractor to execute any work which is urgently required for the safety of the Project Highway, whether because of an accident, unforeseeable eventor otherwise; provided that in case of any work required on account of a Force Majeure Event, the provisions of Clause 21.6 shall apply.

- In the event that the Contractor fails to achieve any of the Project Milestones, the Authority’s Engineer shall undertake a review of the progress of construction and identify potential delays, if any. If the Authority’s Engineer shall determine that completion of the Project Highway is not feasible within the time specified in the Agreement, it shall require the Contractor to indicate within 15 (fifteen) days the steps proposed to be taken to expedite progress, and the period within which the Project Completion Date shall be achieved. Upon receipt of a report from the Contractor, the Authority’s Engineer shall review the same and send its comments to the Authority and the Contractor forthwith.

- The Authority’s Engineer shall obtain from the Contractor a copy of all the Contractor’s quality control records and documents before the Completion Certificate is issued pursuant to Clause12.2.

- Authority’s Engineer may recommend to the Authority suspension of the whole or part of the Works if the work threatens the safety of the Users and pedestrians. After the Contractor has carried out remedial measure, the Authority’s Engineer shall inspect such remedial measures forthwith and make a report to the Authority recommending whether or not the suspension hereunder may berevoked.

- In the event that the Contractor carries out any remedial measures to secure the safety of suspended works and Users, and requires the Authority’s Engineer  to inspect such works, the Authority’s Engineer shall inspect the suspended works within 3 (three) days of receiving such notice, and make a report to the Authority forthwith, recommending whether or not such suspension may be revoked by the Authority.

- The Authority’s Engineer shall carry out, or cause to be carried out, all the Tests specified in Schedule-K and issue a Completion Certificate, as the case may be. For carrying out its functions under this Paragraph 4 (xviii) and all matters incidental thereto, the Authority’s Engineer shall act under and in accordance with the provisions of Article 12 and Schedule-K.

### Maintenance Period

- The Authority’s Engineer shall aid and advise the Contractor in the preparation of its monthly Maintenance Programme and for this purpose carry out a joint monthly inspection with the Contractor.

- The Authority’s Engineer shall undertake regular inspections, at least once every month, to evaluate compliance with the Maintenance Requirements and submit a Maintenance Inspection Report to the Authority and the Contractor.

- The Authority’s Engineer shall specify the tests, if any, that the Contractor shall carry out, or cause to be carried out, for the purpose of determining that the Project Highway is in conformity with the Maintenance Requirements. It shall monitor and review the results of such tests and the remedial measures, if any, taken by the Contractor in this behalf.

- In respect of any defect or deficiency referred to in Paragraph 3 of Schedule- E, the Authority’s Engineer shall, in conformity with Good Industry Practice, specify the permissible limit of deviation or deterioration with reference to the Specifications and Standards and shall also specify the time limit for repair or rectification of any deviation or deterioration beyond the permissible limit.

- The Authority’s Engineer shall examine the request of the Contractor for closure of any lane(s) of the Project Highway for undertaking maintenance/repair thereof, and shall grant permission with such modifications, as it may deem necessary, within 5 (five) days of receiving a request from the Contractor. Upon expiry of the permitted period of closure, the Authority’s Engineer shall monitor the reopening of such lane(s), and in case of delay, determine the Damages payable by the Contractor to the Authority under Clause14.5.

### Determination of costs and time

- The Authority’s Engineer shall determine the costs, and/or their reasonableness, that are required to be determined by it under the Agreement.

- TheAuthority’sEngineershalldeterminetheperiodofTimeExtensionthatisrequired to be determined by it under the Agreement.

- The Authority’s Engineer shall consult each Party in every case of determination in accordance with the provisions of Clause18.5.

### Payments

- The Authority’s Engineer shall withhold payments for the affected works for which the Contractor fails to revise and resubmit the Drawings to the Authority’s Engineer in accordance with the provisions of Clause 10.2 (iv)(d).

- Authority’s Engineer shall-

  - within 10 (ten) days of receipt of the Stage Payment Statement from the Contractor pursuant to Clause 19.4, determine the amount due to the Contractor and recommend the release of 90 (ninety) percent of the amount so determined as part payment, pending issue of the Interim Payment Certificate; and

  - within 15 (fifteen) days of the receipt of the Stage Payment Statement  referred to in Clause 19.4, deliver to the Authority and the Contractor an Interim Payment Certificate certifying the amount due and payable to the Contractor, after adjustments in accordance with the provisions of Clause 19.10.

- The Authority’s Engineer shall, within 15 (fifteen) days of receipt of the Monthly Maintenance Statement from the Contractor pursuant to Clause 19.6, verify the Contractor’s monthly statement and certify the amount to be paid to the Contractor in accordance with the provisions of the Agreement.

- The Authority’s Engineer shall certify final payment within 30 (thirty) days of the receipt of the final payment statement of Maintenance in accordance with the provisions of Clause19.16.

### Other duties and functions

The Authority’s Engineer shall perform all other duties and functions as specified in the Agreement.

### Miscellaneous

- A copy of all communications, comments, instructions, Drawings or Documents sent by the Authority’s Engineer to the Contractor pursuant to this TOR, and a copy of all the test results with comments of the Authority’s Engineer thereon, shall be furnished by the Authority’s Engineer to the Authority forthwith.

- The Authority’s Engineer shall retain at least one copy each of all Drawings and Documents received by it, including ‘as-built’ Drawings, and keep them in its safe custody.

- Within 90 (ninety) days of the Project Completion Date, the Authority’s Engineer shall obtain a complete set of as-built Drawings, in 2 (two) hard copies and in micro film form or in such other medium as may be acceptable to the Authority, reflecting the Project Highway as actually designed, engineered and constructed, including an as- built survey illustrating the layout of the Project Highway and setback lines, if any, of the buildings and structures forming part of Project Facilities; and shall hand them over to the Authority against receipt thereof.

- The Authority’s Engineer, if called upon by the Authority or the Contractor or both, shall mediate and assist the Parties in arriving at an amicable settlement of any Dispute between the Parties.

- TheAuthority’sEngineershallinformtheAuthorityandtheContractorofanyeventof Contractor’s Default within one week of its occurrence.

# Schedule - O

(See Clauses 19.4 (i), 19.6 (i), and 19.8 (i))

# Forms of Payment Statements

### Stage Payment Statement for Works

The Stage Payment Statement for Works shall state:

  - theestimatedamountfortheWorksexecutedinaccordancewithClause19.3

    - subsequent to the last claim;

  - amounts reflecting adjustments in price for the aforesaid claim;

  - the estimated amount of each Change of Scope Order executed subsequent to the last claim;

  - amounts reflecting adjustment in price, if any, for (c) above in accordance with the provisions of Clause 13.2 (iii)(a);

  - total of (a), (b), (c) and (d)above;

  - Deductions:

- Any amount to be deducted in accordance with the provisions of the Agreement except taxes;

- Any amount towards deduction of taxes; and

- Total of (i) and (ii)above.

  - Net claim: (e) – (f)(iii);

  - The amounts received by the Contractor upto the last claim:

- For the Works executed (excluding Change of Scope orders);

- For Change of Scope Orders, and

- Taxes deducted

### Monthly Maintenance Payment Statement

The monthly Statement for Maintenance Payment shall state:

  - the monthly payment admissible in accordance with the provisions of the Agreement;

  - the deductions for maintenance work not done;

  - net payment for maintenance due, (a) minus(b);

  - amounts reflecting adjustments in price under Clause 19.12;and

  - amount towards deduction of taxes

### Contractor’s claim for Damages

Note: The Contractor shall submit its claims in a form acceptable to the Authority.

Schedule - P (See Clause 20.1) Insurance

### Insurance during Construction Period

  - The Contractor shall effect and maintain at its own cost, from the Appointed Date till the date of issue of the Completion Certificate, the following insurances for any loss or damage occurring on account of Non Political Event of Force Majeure, malicious act, accidental damage, explosion, fire and terrorism:

    - insurance of Works, Plant and Materials and an additional sum of [15 (fifteen)] per cent of such replacement cost to cover any additional costs of and incidental to the rectification of loss or damage including professional  fees and the cost of demolishing and removing any part of the Works and of removing debris of whatsoever nature; and

    - Insurance for the Contractor's equipment and Documents brought onto the Site by the Contractor, for a sum sufficient to provide for their replacement at the Site.

  - The insurance under sub para (a) and (b) of paragraph 1(i) above shall cover the Authority and the Contractor against all loss or damage from any cause arising under paragraph 1.1 other than risks which are not insurable at commercial terms.

### Insurance for Contractor's Defects Liability

The Contractor shall effect and maintain insurance cover of not less than 15% of the Contract Price for the Works from the date of issue of the Completion Certificate until the end of the Defects Liability Period for any loss or damage for which the Contractor is liable and which arises from a cause occurring prior to the issue of the Completion Certificate. The Contractor shall also maintain other insurances for maximum sums as may be required under the Applicable Laws and in accordance with Good Industry Practice.

### Insurance against injury to persons and damage to property

  - The Contractor shall insure against its liability for any loss, damage, death or bodily injury, or damage to any property (except things insured under Paragraphs 1 and 2 of this Schedule or to any person (except persons insured under Clause 20.9), which  may arise out of the Contractor's performance of this Agreement. This insurance shall be for a limit per occurrence of not less than the amount stated below with no limit on the number of occurrences.

The insurance cover shall be not less than: Rs. [*****]

  - The insurance shall be extended to cover liability for all loss and damage to the Authority's property arising out of the Contractor’s performance of this Agreement excluding:

    - the Authority's right to have the construction works executed on, over, under, in or through any land, and to occupy this land for the Works; and

    - Damage which is an unavoidable result of the Contractor's obligations to execute the Works.

### Insurance to be in joint names

The insurance under paragraphs 1 to 3 above shall be in the joint names of the Contractor and the Authority.

# Schedule-Q

(See Clause 14.10)

# Tests on Completion of Maintenance Period

### Riding Quality test:

Riding quality test: Riding quality of each lane of the carriageway shall be checked with the help of a calibrated bump integrator and the maximum permissible roughness for purposes of this Test shall be [2,200 (two thousand and two hundred only)] mm for each kilometer.

### Visual and physical test:

#### The Authority’s Engineer shall conduct a visual and physical check of construction to determine that all works and equipment forming part thereof conform to the provisions of this Agreement. The physical tests shall include measurement of cracking, rutting, stripping and potholes and shall be as per the requirement of maintenance mentioned in Schedule-E.

Schedule-R

(See Clause 14.10)

# Taking Over Certificate

I, ……………………. (Name and designation of the Authority’s Representative) under and in accordance with the Agreement dated ………… (the “Agreement”), for [Construction of 4 nos. Bridges at Km 47.000 (Jhiram nalla), Km. 123.000 (Kerlapal nalla), Km. 127.800 (Bodaguda nalla) and Km. 137.400 (Dubbatota nalla) on NH-30 (Old NH-221) Jagdalpur-Sukma-Konta road in the state of Chhattisgarh on Engineering, Procurement and Construction (EPC) basis through	(Name of Contractor),here by certify that the Tests on completion of Maintenance Period in accordance with Article 14 of the Agreement have been successfully undertaken to determine compliance of the Project Highway with the provisions of the Agreement and I hereby certify that the Authority has taken over the Project highway from the Contractor on this day.........

SIGNED, SEALED ANDDELIVERED

(Signature)                                                        (Name and designation of Authority’s Representative)

(Address)

### *****	End of the Document*****