GOVERNMENT OF CHHATTISGARH

NATIONAL HIGHWAY ZONE P.W.D.

# BID DOCUMENT

NIT NO. 57/CE/NH/TC/44-17/2024 Dt: 25.01.2024

# VOLUME – I

| NAME OF WORK | # : | Short term maintenance of Takhatpur Ex. Road from Km. 26.542 to Km. 32.093, Mungeli Ex. Road from Km. 45.786 to Km. 56.275, Pandariya Ex. Road from Km. 82.582 to Km. 87.133 and Pondi Ex. Road from Km. 103.166 to Km. 104.756 = 22.181 Km. on N.H.-130A in the state of Chhattisgarh. |
| --- | --- | --- |
| NAME AND ADDRESS OF THE CONTRACTOR WHO DOWN LOADED THE BID DOCUMENTS. | # : | # ------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------------ |

Office of the Chief Engineer

National Highway Zone, P.W.D. Chhattisgarh.

CONTENTS

## Description                                                                                                                PageNo.

Introduction                                                                                                      1

Section 1	NoticeInvitingTender                                                                                           5

Section 2	Instructions to Bidders (ITB) and Appendixto ITB	11

Section 3	Qualification Information	31

Section 4	FormsofBankGuarantees,LetterofAcceptance(LoA)andAgreement	41

Section 5	General Conditions of Contract (GCC) andContractData	51

Section 6	Addendum to General ConditionsofContract	77

Section 7	Road Maintenance Standards and Specificationsfor Road	81

Maintenance Works, Part-I and Part II

Section 8	Drawings and ScheduleofDrawings	91

Section 9	Financial Bid Form and BillofQuantities	95

# SECTION – 1

# NOTICE INVITING TENDER

NIT NO. 24/CE/NH/TC/44-17/2024 Dt: 25.01.2024 (2nd Call)

| # Availability of bid documents from | # : | # 14.05.2025 to 13.06.2025 |
| --- | --- | --- |
| # Date of Pre-bid meeting | # : | # 26.05.2025 at 15.00 Hrs |
| # Deadline for submission of original documents and bid | : | 13.06.2025 at 11:00 Hrs |
| # Opening of technical bids | # : | # 16.06.2024 at 11:30 Hrs |
| # Opening of financial bids | : | Intimated later |
| # Validity of bids | # : | # 120 Days |

OFFICE OF THE CHIEF ENGINEER,

NATIONAL HIGHWAY ZONE, PWD, RAIPUR (C.G.)

Tel:- 0771-4051075, Fax. 0771-4023057 email- cenhr@rediffmail.com

Nit No. 24/CE/NH/TC/44-17/2024 SYSTEM TENDER ID: 2025_MoRTH_859964_1  Date: 14.05.2024

NOTICE INVITING TENDER

2nd Call

- The Chief Engineer NH Zone P.W.D. Raipur Chhattisgarh on behalf of Ministry of Road Transport & Highways, Government of India (the “Authority”) hereby invites Single Percentage Rate Bids through e-tendering from experienced firms/organizations for maintenance works and activities for the following sections of the National Highways.

| Sl. No. | Section | Length (km) | Estimated Cost (incl. GST) (Rs. Lakh) | Bid Security (Rs. Lakh) | Contract Duration* (month) |
| --- | --- | --- | --- | --- | --- |
| 1. | Short term maintenance of Takhatpur Ex. Road from Km. 26.542 to Km. 32.093, Mungeli Ex. Road from Km. 45.786 to Km. 56.275, Pandariya Ex. Road from Km. 82.582 to Km. 87.133 and Pondi Ex. Road from Km. 103.166 to Km. 104.756 = 22.181 Km. on N.H.-130A in the state of Chhattisgarh | 22.181 | 226.87 | 2.27 | 12 Months |

(* out of which Quantity Based Road maintenance and road property Maintenance shall be completed in 04 months and the performance-based incident management and pavement repair shall be spread through 12 months)

## Cost of bid Documents (Non-Refundable)	: Rs. 11,800/- (Rupees Eleven thousand		 Eight Hundredonly Incl GST),

- e-Tender Processing fee (Non-Refundable)	: Nil

- Thepreliminaryrequirements(detailedrequirementsaregivenintheBidDocuments) of bidding firm/contractor for above work are mentioned as under :-

| Average Annual Turn-over during last 3 years | Work of similar nature during last 5 years (completed works satisfactorily completed not less than 90% of contract value as a prime contractor) |
| --- | --- |
| Minimum Average Annual Turn over Rs. 226.87 lakhs | Single work of Rs. 113.435 lakhs (minimum 50% of estimated cost of work) (or) Two similar works each of Rs. 79.40 lakhs (minimum 35% of estimated cost of work) (or) Three similar works each of Rs. 56.71 lakhs (minimum 25% of estimated cost of work) |

- The Scope of Work includes the routine maintenance of all the assets and facilities existing within Right of Way (ROW) on the above-mentioned section including maintenance of carriageway, shoulders, median, bridges, culverts, drains, footpaths, road signage, plantation etc., Providing Pavement Repairs and maintenance and carrying out other works as specified in the bid documents.

- To participate in the bidding, it is mandatory for the Bidders to get registered their firm with e-procurement portalhttps://eprocure.gov.in/eprocure/app to have user ID & password which has to be obtained free of cost. Following may kindly be noted:

- Registration with e-procurement portal should be valid at least up to the date of submission of BID.

- BIDs can be submitted only during the validity of registration.

The Bidders shall update their project and other details on the portal on a regular basis and apply to the tenders via the portal.

The detailed bid documents can be viewed on the website https://eprocure.gov.in from 14.05.2025 to 13.06.2025 (upto 11:00 Hrs).

- The complete BID document can be viewed / downloaded from official portal of the CPPP website (eprocure.gov.in/eprocure/app) from 14.05.2025 to 13.06.2025 (upto 11:00 Hrs). The amendments/ clarifications to the Bid Document if any, will be hosted on the above website. The bidder is required to submit, along with its BID, the cost of BID/RFP document, i.e. Rs.11,800/- (Rupees Eleven Thousand Eight Hundred only), to Employer’s account through Bharat Kosh, as mentioned below:

| S. No. | Particulars | Details |
| --- | --- | --- |
| 1. | Link of Bharat Kosh | bharatkosh.gov.in |
| 2. | Pay and Accounts Officer (PAO) | PAO Code – “002192” Regional Pay & Accounts Officer (NH) Bhopal, |
| 3. | Drawing and Disbursing Officer (DDO) | DDO Code - “205810” Engineer Liaison Officer, Ministry of Road Transport & Highway, Raipur |

- The Bid should be submitted online in the prescribed format given on the website. No other mode of submission is acceptable.

- The authorized signatory holding Power of Attorney shall only be the Digital Signatory. In case authorized signatory holding Power of Attorney and Digital Signatory are not the same, the bid shall be considered non-responsive.

- The last date for online submission of the Bid is 13.06.2025 upto 11:00 hrs (as mentioned on the e-portal only) (“Bid Due Date”). Bidder must submit its Financial Bid and Technical Bid on CPPP e-procurement portal within the above deadline. The bids would be opened on 16.06.2025 upto 11:30 hrs online at Office of the Chief Engineer NH Zone PWD, Raipur Chhattisgarh. Representatives of the bidders, who choose to attend, may attend the online opening of the bids at Office of the Chief Engineer NH Zone PWD, Raipur Chhattisgarh on the date and time as mentioned above. However, such representatives shall be allowed to attend the opening of the bids only if they produce letter of authority on the letterhead of the bidder, at the time of opening of bids as mentioned above.

- The amount of Bid Security is Rs. 2.27 Lakhs

- The period of validity of bid is 120 days from the deadline of submission of bid.

For any clarification, the office of the undersigned may be contacted.

- ATTN. OF:			Mr. M.L. Uraon

DESIGNATION: 		Chief Engineer (NH)

ADDRESS: 			NH Zone, PWD, Pension Bada, Raipur 					Chattisgarh

FAX NO : 			0771-4023057

E-MAIL ADDRESS: 		cenhr@rediffmail.com

(ii)    ATTN. OF:			Mr. Abhijeet Kumar

DESIGNATION: 		Regional Officer, MoRTH

ADDRESS: 			NH Campus, Pension Bada Raipur

FAX NO : 			0771-2436637

E-MAIL ADDRESS: 		romorthraipur@gmail.com

Chief Engineer

National Highway Zone,

Public Works Department

Pension Bada, Raipur (CG) - 492001

Phone/ Fax 0771 - 4051075, 4062744/ 4023057

e-mail: cenhr@rediffmail.com; cenhraipur@gmail.com

# SECTION-2

INSTRUCTIONS TO BIDDERS (ITB)

AND APPENDIX TO ITB

## SECTION – 2

## INSTRUCTIONS TO BIDDERS (ITB)

TABLE OF CLAUSES

| Clause | A. General | Clause | D. Submission of bids |
| --- | --- | --- | --- |
| 1. | Scope of Bid | 20. | Deadline for Submission of Bids |
|  |  | 21. | Late Submission of Documents in Physical Form |
| 2. | Source of Funds | 22. | Modification and Withdrawal of Bids |
| 3. | Eligible Bidders |  | E. Bid Opening, Clarification of bids and Evaluation |
| 4. | Qualification of the Bidder | 23. | Bid Opening, Clarification of Bids and Evaluation |
| 5. | One Bid per Bidder | 24. | Process to be Confidential |
| 6. | Cost of Bidding | 25. | Contacting the Employer |
| 7. | Site Visit | 26. | Examination of Bids and Determination ofResponsiveness |
|  | B. Bidding Documents | 27. | Correction of Errors |
| 8. | Content of Bidding Documents | 28. | Evaluation and Comparison of Financial Bids |
| 9. | Clarifications on Bidding Documents |  | F. Award of Contract |
| 10. | Amendment of Bidding Documents | 29. | Award Criteria |
|  | C. Preparation of bids | 30. | Employer’s Right to Accept any Bid and to Reject any or all Bids |
| 11. | Language of Bid | 31. | Notification of Award and Signing of Agreement |
| 12. | Documents Comprising the Bid | 32. | Performance Security |
| 13. | Bid Prices | 33. | Advances |
| 14. | Currencies of Bid and Payment |  | G.CorruptorFraudulentPractices |
| 15. | Bid Validity | 34. | Corrupt or Fraudulent Practices |
| 16. | Earnest Money/Bid Security/ Forfeiture/Debarment |  | H. Labour Laws and Fundamental breach |
| 17. | Alternative Proposals by Bidders | 35. | Labour Laws and Regulations |
| 18. | Format and Signing of Bid | 36. | Fundamental Breach and other Obligations |
| 19. | Marking of Bids |  | Appendix to ITB |

A. GENERAL

- Scope ofBid

  - TheEmployer(asdefinedintheAppendixtoITB)invitesSinglePercentageRatebids throughtheprocessofe-tenderingforworksasdescribedinthesedocumentsandreferredtoas “theWorks”.ThenameandidentificationnumberoftheWorksisasdefinedintheAppendixto ITB.

  - ThesuccessfulBidderwillbeexpectedtocompletetheWorksbytheintended

Completion Date specified in the Contract Data.

  - Throughout these Bidding Documents, the terms “bid” and “tender” and their derivatives (bidder/tenderer, bid/tender, bidding/tendering, etc.) aresynonymous.

## Source of Funds

  - The expenditure under this contract will be met by theMinistry of Road Transport & Highways through its Chief Engineer-cum-Regional Officer, MoRTH, Raipur Chhattisgarh.

## Eligible bidders

  - ThisInvitationforBidsisopentoallbiddersmeetingthequalificationrequirements

Prescribed in Clause 4 of ITB.

  - AnyentitywhichhasbeenblacklistedorbarredbytheCentraloranyStateGovernment or any public sector undertaking, autonomous body or any authority under the Central or State Government,fromparticipatinginanyproject,andthebarsubsistsasonthedateofApplication shall not be eligible to submit thebid.

## Qualification of theBidder

  - AllbiddersshallfurnishthefollowinginformationanddocumentswiththeirBidsinSection-3, Qualification Information, unless otherwise stated in the Appendix to ITB.

- Scanned copies of original documents defining the constitution or legal status, place of registration, and principal place of business; scanned copy of written power of attorney of the signatory of the Bid to commit the Bidder; and original copy ofWritten PowerofAttorneytobesubmittedintheenvelopeofphysicalform.(referClause12.2 ofITB).

- Scannedcopyoftotalmonetaryvalueofcivilengineeringconstructionandmaintenance works performed for each of the last threeyears duly certified by Chartered Accountant;

- Scannedcopyofexperiencecertificateinworksofasimilarnatureandsizeforeachof thelastfiveyearswithcertificatesfromtheconcernedofficeroftherankofExecutive Engineer or equivalent orhigher;

- Scanned copy of evidence of availability (either owned or leased or rented) of items of construction and maintenance equipment named in Clause 4.3 B(b)(i).

- Scanned copy of details of the technical personnel proposed to be employed fortheContract having the qualifications defined in Clause 4.3 B (b) (ii).

- ScannedcopyofreportsonthefinancialstandingoftheBidder,andacertificatefromChartered Accountant as a proof of turnover for the last three years;

- Scanned copy of information regarding any litigation or arbitration during the lastfive years in which the Bidder is involved, the parties concerned, the disputed amount, and the presentstatus;

- Undertaking that the bidder is not affiliated to the firm or entity that has been hired or employed by the Employer for preparation of bid documents or to supervise the contract.

  - Bids from joint ventures/consortiums are notallowed.

  - ATo qualify for award of the contract, each bidder in its name should have the following;-

### achieved a minimum average annual financial turnover (in all classes of civil engineering construction and maintenance works only) equal to the amount indicated in NIT during last three years ending 31stMarch of the previous financial year duly certified by CharteredAccountant.

- satisfactorily completed (not less than 90% of contract value), as a prime contractor or as a partner of JVfor similar works during last five years ending last day of month previous to the one in which bids are invited, either of thefollowing:

- Three similar completed works costing not less  than  amount equal to Rs. 56.71   Lakhs  each.

- Two similar completed works costing not less than amount equal to Rs. 79.40  Lakhs each.

- One similar completed work costing not less than amount equal to Rs. 113.435  Lakhs

- (The similar work constitutes construction/maintenance of roads)

The following escalation factors shall be used to bring the value of such completed works to the level of current financial year (2023-24):

| Financial Year | 2022-23 | 2021-22 | 2020-21 | 2019-20 | 2018-19 |
| --- | --- | --- | --- | --- | --- |
| Multiplying Factor | 1.1 | 1.21 | 1.33 | 1.46 | 1.61 |

  - B(a) Each bidder must upload the scanned copies of following documents along with the submission of onlinebid:

    - An affidavit on a Stamp Paper, duly attested from the Notary Public, that the Information furnished with the bid documents is correct in all respects; and

    - Such other certificates as defined inSection-3.

Failure to submit the certificates/documents as specified above shall make the bid

Non-responsive

- Each bidder must demonstrate for thiswork:

    - evidence of availability (either owned or leased or rented) of the key equipment for this work as stated in the Appendix toITB.

    - availability of personnel with qualification and experience as stated in the Appendix to ITB.

  - Bidders who meet the minimum qualification criteria will be qualified only if their available bid capacity is more than the total bid value. The available bid capacity will be calculated asunder:

Available Bid capacity = (A* N* 2.5 - B) Where.

A =Maximum value of civil engineering works executed in any one year during

the last three years (escalation factor as specified in this section shall be used to bring the maximum value of civil engineering works to the level of current financial year i.e.,2023-24) taking into account the completed as well as works in progress.

N = Number of years prescribed for completion of the works for which bid is invited.

B=Value (escalation factor as specified in this section shall be used to bring the value to the level of current financial year i.e.2023-24) of existing commitments and on-going works to be completed during the next 01 years (period of completion of the works for which bid is invited).

  - Even though the bidders meet the above qualifying criteria, they are subject to be disqualified if they have:

    - made misleading or false representations in the forms, statements, affidavits and attachments submitted in proof of the qualification requirements; and/or

    - record of poor performance such as abandoning the works, not properly completing the contract, inordinate delays in completion, litigation history, or financial failures etc. or debarring from work etc.

## One Bid per Bidder

  - EachBiddershallsubmitonlyoneBidfortheWorks.ABidderwhosubmitsmorethanOne Bid will cause such bids to be disqualified.

## Cost of Bidding

  - TheBiddershallbearallcostsassociatedwiththepreparationandsubmissionofhis Bid, and the Employer will, in no case, be responsible or liable for those costs.

## Site Visit

  - The Bidder, at his own cost, responsibility and risk, is encouraged to visit, examine and familiarize himself with the Site of Works and its surroundings including source of earth, water, road aggregates, availability of labour etc. and obtain all information that may be necessary for preparing the Bid and entering into a contract for undertaking the maintenance Works. The costs of visiting the site shall be at the Bidder’s own expense. For this purpose, he may contact the person whose contact details are given in the Appendix to ITB.

## B. BIDDING DOCUMENTS

- Content of bidding Documents

  - These to bidding documents comprises the documents listed below and addenda (if any) issued in accordance with Clause10:

## Section1:	Notice Inviting Tender

Section2:	Instructions to Bidders (ITB) and Appendix to ITB

Section3:	Qualification Information

Section4:	Forms of Bank Guarantee, Letter of Acceptance (LOA) and Agreement Section5:	General Conditions of Contract and Contract Data

Section6:	Addendum to General Conditions of Contract

Section7:	Road Maintenance Standards and Specifications for Road Maintenance Work, Part-I and Part-II

Section8:	Drawings and Schedule of Drawings

Section9:	Financial bid form and Bill of Quantities

  - The bidder is expected to examine carefully all instructions, conditions of contract, contract data, forms, scope, road maintenance Standards and Specifications, bill of quantities, etc. in the Bid Documents. Failure to comply with there quirements of Bid Documents shall beat the bidder’s own risk. Pursuant to Clause26 hereof ,Bids, which are not substantially responsive to the requirements of the Bid Documents, shall be rejected.

## Clarifications on Bid Documents

  - A prospective Bidder requiring any clarification on the Bid Documents may notify the Employer in writing or through e-tender portal at the Employer’s address indicated in the notice inviting Tender. The Employer will respond to any such request for clarification received earlier than 10 days prior to the deadline for submission of Bids. Copies of the Employer’s response will be hosted on website including a description of the queries but without identifying its source.

  - Pre-Bid Meeting

    - The Bidder’s authorized representative is invited to attend a pre-bid meeting, if it is indicated in the Appendix to ITB. The purpose of the pre-bid meeting will be to clarify issues and to answer questions on any matter that may be raised at that stage.

    - The bidder is requested to submit any questions in writing so as to reach the Employer not later than one week before the meeting.

    - Minutes of the meeting, including the text of the questions raised (without identifying the source of the enquiry) and the responses given will be posted without delay on website. Any modifications of the bid documents listed in Clause8.1,which may be come necessary as a result of the pre-bid meeting or which are required in the opinion of the Employer shall be made by the Employer exclusively through the issue of an Addendum pursuant to Clause 10 and not through the minutes of the pre-bid meeting.

    - Non-attendance at the pre-bid meeting will not because for disqualification of a bidder.

## Amendment of Bidding Documents

  - Before the deadline for submission of bids, the Employer may modify the Bidding Documents by issuing addenda.

  - Any addendum thus issued shall be part of the Bidding Documents and shall be hosted one-tendering portal. Bidders are advised to keep themselves updated of all the addenda issued on e-tendering portal by daily checking the e-tendering portal and the Employer does not assume any responsibility in case the bidder fails to do so and does not take any action, if required, with respect to any relevantaddendum.

  - To give prospective bidders reasonable time to take an addendum into account in preparing their bids, the Employer shall extend, as necessary, the deadline for submission of bids, in accordance with Clause20.3.

## C. PREPARATION OF BIDS

- Language of bid

  - All documents relating to the Bid shall be in English.

## Documents comprising the bid

  - The e-bid submitted by the bidder shall be in two separate parts namely Part-I and Part-II. Part-I shall be named Technical Bid and shall comprise of information submitted in Section-3. Part-II shall be named Financial Bid and shall comprise of Bill of Quantities-Bill no.1 to3.

  - Documents to be submitted in physical form must be delivered by [17.30 Hrs] on bid due Date [13.06.2025].

Though, the scanned copies of following documents is required to be uploaded during submission of e-bid on the e-tendering portal as per Clause 12.1 above, however, following original documents in physical form shall be submitted in a sealed envelope on or before the Bid Due Date [13.06.2025@ 17.30 Hrs] at the address indicated in Clause 20, duly superscribed "Name of Work, Bid Due Date and time". Name and address of the bidder should also be indicated on the envelope

- Copy of Acknowledgement for Tender Submission and EMD/Bid Security

- Bid Document Fee

- Written Power of Attorney of the signatory (whose digital signature certificate is

used during e-tender submission) of the bidder to commit the Bid.

- Affidavit duly notarized (as per the format provided inSection-3)

- Integrity Pact

  - The following documents, which are not submitted with the bid, will be deemed to be part of the bid.

- Notice Inviting Tender

- Instructions to the Bidders and Appendix to ITB

- General Conditions of Contract and Contract Data

- Addendum to General Conditions of Contract

- Road Maintenance Standards and Specifications for Road Maintenance Works,

- Part-I and Part-II

- Drawings and Schedule of Drawings

## Bid Prices

  - The Contract shall be for the whole Works, as described in Clause1.1 based on the Bill of Quantities- Bill no. 1 to 3 submitted by the Bidder.

  - The Bidder shall quote single percentage rate above/below the BoQ/scheduled rates on appropriate format enclosed as part of tender document on e-tender portal of the CPPP website (eprocure.gov.in/eprocure/app).

  - All duties, taxes, including GST, royalties and other levies payable by the Contractor under the Contract, or for any other cause, shall be included in the rates, prices, and total bid price submitted by the Bidder.

  - TheratesandpricesquotedbytheBiddershallbefixedforthedurationoftheContractand shall not be subject to adjustment.

## Currencies of Bid and Payment

All payments shall be made in Indian Rupees.

## Bid Validity

  - Bids shall remain valid for a period of 120 days after the deadline date for bid submission specifiedin Clause20. A bid valid for a shorter period shall be rejected by the Employer as non- responsive.

  - In exceptional circumstances, prior to expiry of the original time limit, the Employer may request that the Bidders may extend the period of validity for a specified additional period. The request and the Bidders’ responses shall be made in writing. A Bidder may refuse the request without forfeiting his Bid Security. A Bidder agreeing to the request will not be required or permitted to modify his bid, but will be required to extend the validity of his Bid Security for a period of the extension, and in compliance with Clause 16 in all respects.

## Earnest Money/Bid Security /Forfeiture/Debarment

  - The Bidder shall furnish, as part of the Bid, Earnest Money/Bid Security,in the amount as specified in the NIT in favour of the Employer in the form of Insurance Surety Bond, Account Payee Demand Draft, Banker’s Cheque or Electronic Bank Guarantee (e-Bank Guarantee).

  - The Earnest Money shall, at the bidder’s option, be in the form of Insurance Surety Bond, Account Payee Demand Draft, Banker’s Cheque or Electronic Bank Guarantee (e-Bank Guarantee) only (the other forms will not be acceptable) of any scheduled commercial bank approved by RBI having a net worth of not less than Rs. 500 crore as per the latest annual report of the bank and must be in the name of Employer. In case of foreign bank (issued by a branch in India),the networth in respect of the Indian operations shall only be taken into account. It shall be valid for 45 days beyond the validity of the bid. Any bid having Bid Security for lesser value and shorter validity period shall be treated as non-responsive.

- Bank Guarantee or Demand Draft receipts, in the name of the Employer, from following banks would be accepted: -

  - State Bank of India or its subsidiaries,

  - Any Indian Nationalized Bank

  - IDBI/ICICI Bank

  - A Foreign Bank (issued by a branch outside India) with a counter guarantee from SBI or its subsidiaries or any Indian Nationalized Bank.

  - Any Scheduled Commercial Bank approved by RBI having a net worth of not less than Rs.500 crore as per the latest Annual Report of the Bank. In the case of a Foreign Bank (issued by a branch in India), the net worth in respect of the Indian operations shall only be taken into account.

- The acceptance of the guarantees shall also be subject to the conditions that the capital adequacy of the Bank shall not be less than the latest norms prescribed by RBI.

- The bank guarantee issued by a Cooperative Bank shall not be accepted.

  - Any Bid not accompanied by an acceptable Earnest Money, shall be rejected by the Employer asnon-responsive.

  - TheEarnestMoneyofunsuccessfulbidderswillbereturnedwithin28daysoftheendof the Bid validity period specified in Sub-Clause 15.1.

  - The Earnest Money of the successful Bidder will be discharged when the Bidder has signed the Agreement and furnished the required Performance Security.

  - The Bid Security /Earnest Money will be forfeited:

- if the Bidder withdraws the Bid after its submission during the period of Bid validity;

- in the case of a successful Bidder, if the Bidder fails within the specified time limit to

  - sign the Agreement; and/or

  - furnish the required Performance Security.

  - In case of forfeiture of Bid Security, the bidder shall also be debarred from participation in the works of MoRTH and State PWD (NH) division across the Country for a period of 1 year.

## Alternative Proposals by bidders

  - Bidder shall submit offers that fully comply with the requirement of the Bidding Documents. Conditional offer or alternate offer will not be considered further in the process of evaluation and such a bid will be declared non-responsive.

## Format and signing of bid

  - The Bidder shall submit e-bid comprising the documents as described in Clause12of the ITB.

  - The documents as stipulated in Clause 12.2 (i), (ii), (iii) (iv) and (v) to be submitted in the physical form along with the security shall be typed or written in ink and shall be signed by a person duly authorized to sign on behalf of the Bidder. All the pages of the documents as mentioned here shall be signed by theperson/personssigning the Bid. Documents as mentioned here shall contain no overwriting, alterations or additions, except those to comply with instructions, issued by the Employer or as necessary to correct errors made by the Bidder, in which case such corrections shall be made by scoring out the cancelled portion, writing the correction and signing and dating it along with the stamp by the person or persons signing the Bids.

## SUBMISSION OFBIDS

## Marking of bids

  - The documents to be submitted in physical form as per Clause 12.2 ((i), (ii), (iii), (iv) and (v)) of ITB shall be submitted in a sealed Envelope super scribed as “Documents in Physical Form” at the top left corner.

In case of any discrepancy between documents submitted online and documents submitted in the physical form, the documents submitted in physical form shall prevail over the documents submitted through online process.

## Deadline for Submission of bids

  - The Bidder shall ensure that the complete e-Bid is uploaded on thee-tender portal on or before the Bid Due Date and before the time specified in NIT/e-portal. The Bidder is further required to submit Documents in Physical Form on or before the Bid Due Date and before the time of submission as specified in NIT, at the following address:

- ATTN. OF:			Mr. M.L. Uraon

DESIGNATION: 		Chief Engineer (NH)

ADDRESS: 			NH Zone, PWD, Pension Bada, Raipur 					Chhattisgarh

FAX NO : 			0771-4023057

E-MAIL ADDRESS: 		cenhr@rediffmail.com

(ii)    ATTN. OF:			Mr. Abhijeet Kumar

DESIGNATION: 		Regional Officer, MoRTH

ADDRESS: 			NH Campus, Pension Bada Raipur

FAX NO : 			0771-2436637

E-MAIL ADDRESS: 		romorthraipur@gmail.com

In the event of the specified date for the submission of Documents in Physical Form being declared a holiday for the Employer, the same will be received up to the specified time on the next working day.

  - The Employer assumes no responsibility for in ability of a bidder to submit bids through the Employer’s e-tendering portal on account of delay in submission at bidder’s end. Bidders shall ensure that they submit the bid well before the“Bid Due Date and Time of Bid-Submission”. The Employer shall not be responsible if bidder is not able to submit the bid on account of failure in network/internet connection or any other reason whatsoever.

  - The Employer may extend the deadline for submission of bids by issuing an amendment in accordance with Clause 10, in which case all rights and obligations of the Employer and the bidders previously subject to the original deadline will then be subject to the newdeadline.

## Late Submission of Documents in PhysicalForm:

  - Any document in physical form if received by the Employer after the deadline prescribedinClause20willbereturnedunopenedtotheBidderandalsothee-bidsubmittedby such Bidder shall not beconsidered.

## Modification and Withdrawal ofBids

  - Bidders may modify or withdraw their e-bids as directed on the e-tendering portal, before the Bid Due Date and time as prescribed in Clause20.

  - No bid may be modified after the deadline for online submission ofbids.

  - Withdrawal or modification of a Bid between the deadline for submission of bids and the expiration of the original period of bid validity specified in Clause 15.1 or as extended pursuant to Clause 15.2 shall result in the forfeiture of the Bid Security pursuant to Clause16.

  - Bidders may modify the prices of their bids before deadline of online submission of bid.

  - NoLateanddelayedbidsafterBidDueDateandtimeshallbepermittedine-tendering portalSystem.Timebeingdisplayedon e-TenderingPortalshallbefinalandbindingonbidders andbidshavetobesubmittedbybiddersconsideringthistimeonlyandnotthetimeaspertheir location/country.

## BID OPENING, CLARIFICATION OF BIDS ANDEVALUATION

## Bid Opening, Clarification of Bids andEvaluation

  - Bid opening shall be carried out in two stages. Firstly, Part-I ‘Technical Bid’ of all the Bidders received (except those received late) shall be opened on the date and time mentioned in Notice Inviting Tender (NIT). Part-II’ Financial Bid’ of those bidders whose technical bid has been determined to be substantially responsive shall be opened on a subsequent date through online process of e-tendering, which will be notified to suchbidders.

The Employer will open the “Technical Bid” of all the Bids received (except those received late), in the presence of the Bidders/Bidders’ representatives who choose to attend at the time, date andplacespecifiedintheNIT.Intheeventofthespecifieddateforthesubmissionofbidsbeing declared a holiday for the Employer, the Bids will be opened at the appointed time and location on the next workingday.

  - In all cases, the amount of Earnest Money, forms and validity shall be announced. Thereafter,theEmployerattheopeningastheEmployermayconsiderappropriate,willannounce the Bidders’ names and such otherdetails.

  - The Employer will prepare minutes of the Bid opening, including the information disclosed to those present in accordance with this Clause 23.

  - ThebidsaccompaniedwithvalidBid Security ,biddocumentfee, Tender processingfee willbetakenupforevaluationwithrespecttotheQualificationInformationandotherinformation furnished in Part I of the bid pursuant to Clause12.1.

Assoonaspossible,theEvaluationCommitteewillfinalizethelistofresponsivebidderswhose financial bids are eligible for consideration. However, to assist in the examination, evaluation of technical bids, the Employer may at his discretion, ask any bidder for clarification of his bid, however, no additional documents in support of clarification will beentertained.

  - The Employer shall inform the bidders about the result of technical evaluation by uploading on the web portal giving 7 days’ time for objections, if any, from the bidders. The Employer shall finalize the evaluation of technical bids after due consideration of objections receivedandintimatethebidders,whoseTechnical Bidsarefoundresponsive,ofthedate,time andplaceofopeningoftheFinancialBids.TheBidderssoinformed,ortheirrepresentative,may attend the event of opening of FinancialBids.

  - Atthetimeoftheopeningofthe‘FinancialBid’,thenamesofthebidderswhosebids were found responsive in accordance with Clause 23.5 will be announced. The financial bids of only these bidders will be opened. The responsive bidders’ names, the Bid prices, the total amountofeachbid,pursuanttoClause22andsuchotherdetailsastheEmployermayconsider appropriate will be announced by the Employer at the time of bidopening.

  - The Employer shall prepare the minutes of the opening of the FinancialBids.

## Process to beConfidential

  - Information relating to the examination, clarification, evaluation, and comparison of bids and recommendations for the award of a contract shall not be disclosed to bidders or any other person not officially concerned with such process until the award to the successful Bidder hasbeenannounced.AnyattemptbyaBiddertoinfluencetheEmployer’sprocessingofbidsor award decisions may result in the rejection of hisBid

## Contacting theEmployer

  - AnyeffortbytheBiddertoinfluencetheEmployerintheEmployer’sbidevaluation,bid comparison or contract award decisions may result in the rejection of the Bidders’ bid.

## Examination of bids and Determination ofResponsiveness

  - Duringthedetailedevaluationof“TechnicalBids”,theEmployerwilldeterminewhether eachBid.

- MeetstheeligibilitycriteriadefinedinClauses3and4;

- containstherequireddocuments inphysicalformandthedocumentsuploadedbythebidderareinorder;and

- issubstantially responsive to the requirements of the Bidding Documents. During the detailed evaluation ofthe “Financial Bids”, the responsiveness of the Bids will be further determined with respect to the remaining bid conditions, i.e., bill of quantities, Specifications and drawingsetc.

## Correction ofErrors

  - Financial Bids determined to be substantially responsive will be checked by the Employer for any arithmetic errors. Errors will be corrected by the Employer asfollows:

a)	Wherethereisadiscrepancybetweentheratesinfiguresandwords,theratesin

words will govern; and

  - TheamountstatedintheFinancialBidwillbecorrectedasperClause27.1andshall bebindingupontheBidder.IftheBidderdoesnotacceptthecorrectedamount,theBidshallbe rejected and the Bid Security shall be forfeited in accordance with Clause 16.6(b).

## Evaluation and Comparison of Financialbids

  - TheEmployerwillevaluateandcompareonlythebidsdeterminedtobesubstantially responsive in accordance with Clause26.

  - If the Bid of the successful Bidder is Seriously unbalanced in relation to the Employer’s estimate of the cost of work to be performed under the contract, the Employer may require that an Additional Performance Security in addition to Performance Security as set forth in Clause 32 may be obtained at the expense of the successful Bidder to protect the Employer against financial loss in the event of default of the successful Bidder under the Contract. The amount of the Additional Performance Security as decided by the Employer shall be final, binding and conclusive on the bidder.

## AWARD OFCONTRACT

## AwardCriteria

  - Subject to Clause 31, the Employer will award the Contract to the Bidder whose Bid has been determined to be substantially responsive according to the bidding documents and who has offered the lowest evaluated Bidprice.

## Employer’s Right to Accept any bid and to Reject any or allbids

  - Notwithstanding Clause 29, the Employer reserves the right to accept or reject any Bid, and to cancel the bidding process and reject all bids, at any time prior to the award of Contract,withouttherebyincurringanyliabilitytotheaffectedBidderorbiddersoranyobligation to inform the affected Bidder or bidders of the grounds for the Employer’saction.

## Notification of Award and Signing ofAgreement.

  - TheBidderwhoseBidhasbeenacceptedwillbenotifiedoftheawardbytheEmployer prior to expiration of the Bid validity period by e-mail or facsimile confirmed by registered letter. This letter (hereinafter and in the Part I General Conditions of Contract called the “Letter of Acceptance”) will state the sum that the Employer will pay to the Contractor in consideration of the execution, completion and maintenance of the Works, and of routine maintenance ofroadsby the Contractor as prescribed by the Contract (hereinafter and in the Contract called the “Contract Price”).

  - The notification of award will constitute the formation of the Contract, subject onlytothe furnishing of a performance security in accordance with the provisions of Clause 32.

  - The Agreement will incorporate all agreements between the Employer and the successful Bidder. It will be signed by the Employer and the successful Bidder after the performance security isfurnished.

  - Upon furnishing of the Performance Security by the successful Bidder, the Employer will promptly notify the other Bidders that their Bids have beenunsuccessful.

## Performance Security

  - Within 10 (ten) days of receipt of Letter of Acceptance, the successful Bidder shall furnish to the Employer an irrevocable and unconditional guarantee from a Bank in the form set forth in Section 4 (Form of Bank Guarantee for Performance Security) for an amount equal to 3% (three percent) of the Bid Price.In case of unbalancedbids mentioned below, the Selected Bidder, along with the Performance Security, shall also furnish to the Authority an irrevocable and unconditional guarantee from a Bank in the same form towards the Additional Performance Security for an amount calculated as under:

- If the Bid Price offered by the Selected Bidder is lower than 20% of the Estimated Project Cost, then the Additional Performance Security shall be calculated @ 20% of the difference in the (i) Estimated Project Cost (as mentioned in RFP)-20% of the Estimated Project Cost and (ii) the Bid Price offered by the Selected Bidder.

- Maximum limit of additional performance security shall be limited to 3% of the Bid price offered by the Selected Bidder.

- This Additional Performance Security shall be treated as part of the Performance Security.

- Bank Guarantee, in the name of the Employer, from following banks would be accepted: -

- State Bank of India or its subsidiaries,

- Any Indian Nationalised Bank

- lDBl/ICICI Bank

- A Foreign Bank (issued by a branch outside India) with a counter guarantee from SBI or its subsidiaries or any Indian Nationalised Bank.

- Any Scheduled Commercial Bank approved by RBI having a net worth of not less than Rs. 500 crore as per the latest Annual Report of the Bank. In the case of a Foreign Bank (issued by a branch in India), the net worth in respect of the Indian operations shall only be taken into account.

- The acceptance of the guarantees shall also be subject to the conditions that the capital adequacy of the Bank shall not be less than the latest norms prescribed by RBI.

- The bank guarantee issued by a Cooperative Bank shall not be accepted.

  - The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period.The Additional Performance Security shall be valid until 28 (twentyeight) days after Project Completion Date.

  - For avoidance of any doubt, in case of failure of submission of Performance Security within the stipulated time period, the award shall be deemed tobecancelled/ withdrawn. Thereupon all rights, privileges, claims and entitlements of the Contractor under or arising out of the Award shall be deemed to have been waived by, and to have ceased with the concurrence of the Contractor, and the Award shall be deemed to have been withdrawn by the Employer.

  - The agreement will be executed within 10 days of receipt of Performance Security and Additional performance Security, if any as per Clause above.

- Advances

33.1		The Employer will provide Mobilization Advance as provided in Part I General Conditions of Contract.

## CORRUPT OR FRAUDULENTPRACTICES

- Corrupt or FraudulentPractices

  - The bidders and their respective officers, employees, agents and advisers shall observe the highest standard of ethics during the bidding process. Notwithstanding anything to thecontrarycontainedherein,theEmployermayrejectanybidwithoutbeingliableinanymanner whatsoever to the bidder if it determines that the bidder has, directly or indirectly or through an agent, engaged in corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice in the biddingprocess.

  - Without prejudice to the rights of the Employer under Clause 34.1 hereinabove, if any bidder is found by the Employer to have directly or indirectly or through an agent, engaged or indulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice during the bidding process, such bidder shall not be eligible toparticipate inanytenderissuedbytheEmployerduringaperiodof2(two)yearsfromthedatesuchbidder isfoundbytheEmployertohavedirectlyorindirectlyorthroughanagent,engagedorindulged in any corrupt practice, fraudulent practice, coercive practice, undesirable practice or restrictive practice, as the case maybe.

  - For the purposes of this Clause 34, the following terms shall have the meaning hereinafter respectively assigned tothem:

- “corruptpractice”meanstheoffering,giving,receiving,orsoliciting,directlyorindirectly, ofanythingofvaluetoinfluencetheactionsofanypersonconnectedwiththebidding process(foravoidanceofdoubt,offeringofemploymentto,oremploying,orengaging inanymannerwhatsoever,directlyorindirectly,anyofficialoftheEmployerwhoisor has been associated in any manner, directly or indirectly, with the bidding process or has dealt with matters concerning the Contract or arising therefrom, before or after the execution thereof, at any time prior to the expiry of one year from the date such officialresignsorretiresfromorotherwiseceasestobeintheserviceoftheEmployer, shall be deemed to constitute influencing the actions of a person connected with the bidding process); engaging in any manner whatsoever, whether during the bidding processoraftertheawardoraftertheexecutionoftheContract,asthecasemaybe, any person in respect of any matter relating to the Works, who at any time has been or is a legal, financial or technical adviser of the Employer in relation to any matter concerning theWorks;

- “fraudulent practice” means a misrepresentation or omission of facts orsuppression of facts or disclosure of incomplete facts, in order to influence the bidding process;

- “coercive practice” means impairing or harming or threatening to impair or harm, directly or indirectly, any person or property to influence any person’s participation or action in the biddingprocess;

- “undesirablepractice”meansestablishingcontactwithanypersonconnectedwithor employed or engaged by the Employer with the objective of canvassing, lobbying or in any manner influencing or attempting to influence the bidding process;and

- “Restrictive practice” means forming a cartel or arriving at any understanding or arrangementamongbidderswiththeobjectiveofrestrictingormanipulatingafulland fair competition in the biddingprocess.

TheEmployerrequirestheBidder/Contractor tostrictlyobservethelawsagainstfraud and corruption enforced in India, namely Prevention of Corruption Act,1988.

## LABOUR LAWS AND FUNDAMENTALBREACH

- Labour Laws andRegulations

  - The Bidders shall be aware of the provisions of various Labour Laws, Regulations andWelfareMeasuresapplicableforConstructionWorkersinIndia,andotherobligationsstated in the Conditions ofContract.

## Fundamental breach and otherobligations

  - The Bidders shall be aware of the provisions of Fundamental Breach and other obligations stated in the Conditions ofContract.

Appendix to ITB

[THE EMPLOYER SHOULD COMPLETE THIS APPENDIX

BEFORE ISSUING THE BID DOCUMENTS]

ITB Clause Reference

1.1)	The Employeris Superintending Engineer, NH P.W.D., Bilaspur Circle, (C.G.),

1.1)	Name and identification number of Worksis“Short term maintenance of Takhatpur Ex. Road from Km. 26.542 to Km. 32.093, Mungeli Ex. Road from Km. 45.786 to Km. 56.275, Pandariya Ex. Road from Km. 82.582 to Km. 87.133 and Pondi Ex. Road from Km. 103.166 to Km. 104.756 = 22.181 Km. on N.H.-130A in the  state of Chhattisgarh

[(4.3. B(b) (i). ]	The key equipment to be deployed on contractwork.

(For bituminous pavement and earthwork)

- Deleted

- Deleted

- Deleted

- Static Roller (8/10T)					1

- Small Roller/ Compactor				1

- Bitumen/ Emulsion Sprayer				1

- Mechanical Broom (1250 sqm per hour)		1

- Air Compressor						2

- Grade/ Backhoe loader					1

- Water Tanker						2

- Dewatering Pumps					2

- Tipper/ dumper Truck					2

- Mini hot mix plant (6/10 T/Hr capacity)		1

- Deleted

- Deleted

Other equipment

Note:  The bidder must upload scanned copy of the documentary evidence in support of his owning/ leased/rented of the above equipment. In case the bidder proposes to hire or take the above equipmentonlease,heshould,alongwiththelease/rentagreement,attachtheproofofownership ofthisequipmentwiththecompany/entityfromwhomtheequipmentareproposedtobehiredon lease/rent. Any conditional evidence of deployment of above equipment or inadequate proof as requiredforanyoftheequipmentshallmakethebidnon-responsiveandfinancialbidshallnotbe opened.

[4.3 b(b)(ii)] The Number of Technical Personnel, Qualifications and Experience willbe as follows:

| S. No. | Personnel | Qualification | ParticularExperience (minimumrequirement) | No. of Persons |
| --- | --- | --- | --- | --- |
| 1 | Project Manager | Degree in CivilEngineering | 5yearsasProjectManager on Highway,Bridge construction/Maintenance works | 1 |
| 2 | SiteEngineer-cum- Surveyor Engineercum Material Engineer | Degree in CivilEngineering | 4 years on Highway Construction/Maintenance works | 1 |
| 3 | Road Safety Auditor | RoadSafety Audit Certificatefrom appropriate approved Govt.agency | 5 years experience | 3 days in every 3 months |

Note: The signed CVs must be uploaded along with the bid. Non-compliance of the above or non-furnishingoftheCVasaboveorconditionaldeploymentofanyoftheabovepersonnelorproposal toemploylessernumberofpersonnelthanaboveshallmakethebidnon-responsiveandfinancial bid shall not beopened.

## [9.2.1] - Pre-bid meeting shall be heldon 01.02.2024 at 15:00 Hrs

Photo

Format of Curriculum Vitae (CV) For Proposed Key Staff

- Proposed Position	:

- Name of Staff	:

- Date of Birth		:				(Please furnish proof of age)

- Nationality		:

- Educational Qualification:

(Summarize college/university and other specialized education of staff member, giving names of schools, dates attended and degrees obtained).

(Please furnish proof of qualification)

Contact Address with Phone and Mobile numbers:

- Membership of Professional Societies:

- Publication		:

(List of details of major technical reports/papers published in recognized national and international journals)

- Employment Record:

(Starting with present position, list in reversed order, every employment held. List of all positions held by staff member since graduation, giving dates, names of employing organization, title of positions held and locations of assignments. For experience period of specific assignment must be clearly mentioned, also given client references, where appropriate).

- Summary of the CV

(Furnish a summary of the above CV. The information in the summary shall be precise and accurate. The information in the summary will have bearing on the evaluation of the CV).

- Education:

- Field of Diploma/Graduation and year

- Field of Post Graduation and year

- Any other specific qualification

- Experience

- Total experience in highways:			Years

- Responsibilities held:

- Years

- Years

- Years

- Relevant Experience:		Years

- Permanent Employment with the Firm (Yes/No):

If yes, how many years:

If no, what is the employment Arrangement with Firm?

Certification:

- I am willing to work on the project and I will be available for entire duration of the project assignment and I will not engage myself in any other assignment during the currency of this assignment on the project.

- I, the undersigned, certify that to the best of my knowledge and belief, this bio-data correctly describes me, my qualification and my experience.

Signature of the Candidate

Place:

Date:

Signature of the Authorized Representative of the firm

Place:

Date:

Note:	Each page of the CV shall be signed in ink by both the staff member and the Authorized Representative of the firm.

# SECTION -3

# QUALIFICATION INFORMATION

SECTION -3

QUALIFICATION INFORMATION

TheinformationtobefilledinbytheBidderinthissectionanddocumentssubmittedinphysical form will be used for the purposes of post qualification as provided for in Clause 4 of the Instructions to Bidders. This information will not be incorporated in theContract.

## QUALIFICATION INFORMATION

- For Individualbidders

  - a)	Year ofConstitution

  - Legal status of Bidder (Proprietorship/Partnership or Pvt. Ltd.firm)

[Upload scanned copy of original]

  - Place ofregistration:

  - Principal place ofbusiness:

  - Power of Attorney of signatory of Bid [Upload scanned copy and also supplyOriginal

copy in envelope of physical form]]

  - Total value of Civil Engineering construction and/or maintenance works performed in the last three years (in Rs. …………Lakh).

Refer ITBClause 4.4 A (a)

(Upload scanned copies of certificate from Chartered Accountant and also supply original certificate from Chartered Accountant)

Year	Total value of work performed (Rs. Lac)

2020-21

2021-22

2022-23

  - (a) Work performed as prime contractor/ JV partner provided further that all other qualificationcriteriaaresatisfied(inthesamename)ofasimilarnatureduringthelastfiveyears as per ITBClause4.3A(b).

| Project Name | Name of the Employer* | Description of work | Value of Contract (Rs. in Lac) | Date of issue of work order | Stipulated period of completion | Actual date of completion* | Remarks explaining reasons for delay in work Completed |
| --- | --- | --- | --- | --- | --- | --- | --- |

*Uploadcertificate(s)fromtheEmployer(tobegivenbyanofficernotbelowtherankofExecutive Engineer or equivalent or higher and also supply original or certified copy in physical form envelope)

Note: 	In case of sub-contractor a certificate from the Executive Engineer or equivalent of the Prime Employer should be obtained from whom an approval for subcontractor has been obtained.

1.4 (b)Information on Bid Capacity (works for which bids have been submitted and accepted and works which are yet to be completed) as on the date 7 days before the last date for bid submission (as per Clause 4.4 of theITB).

- Existing commitments and on-going works(B)=(I+II)

- Details of Ongoing Works

| Description of work | Place &State | Contract No. | Name &Address of Employer | Valueof Contract (RsCr) | Stipulated Period of Completion | Value of works* remaining to be completed (Rs Cr) | Escalation factor | Anticipated date of completion | Escalatedvalue of remaining work duringcompletion periodofworkfor whichbidsare invited |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |

  - Upload certificate (s) from the Engineer(s)-in-Charge of the rank of Executive Engineer or equivalent & also supply original or certified copy of certificate in physical formenvelope.

- Details of works for which bid submitted and accepted (i.e. where contract signing is pending)

| Description of works | Place & State | Name & Address of Employer | Date of issue of Letter of Acceptance (LOA) * | Value given in LOA | Stipulated period for completion | Value of work during completion period of workforwhichbidsare invited |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 |

  - Upload copy ofLOA

- Bid Capacity (Bidder shall calculate, mention his bid capacity and enclose the supporting calculation)

A	=	Rs.	lakh (enclose thedetails)

N	=	years

B	=	Rs.	lakh (enclose thedetails)

available bidcapacity =	AxNx2.5 –B

=	Rs.	Lakhs

  - AvailabilityofKeyEquipmentessentialforcarrying out theWorks[Ref.Clause4.3(B) (b)(i)]. The Bidder should list all the information requestedbelow.

| Item of Equipment | Requirement |  | Availability Proposals |  | Page No of the proof attached |
| --- | --- | --- | --- | --- | --- |
|  | No. | Capacity | Owned/Leased rented | Age/ Condition |  |

Note:The bidder must upload the documentary evidence in support of his owning/leased/rented of the above equipment. In case the bidder proposes to hire or take the above equipment on lease, he should, along with the lease/rent agreement, attach the proof of ownership of these equipment with the company/entity from whom the equipment are proposed to be hired on lease/rent. Any conditional evidence of deployment of above equipment or inadequate proof as required for any of the equipment shall make the bid non-responsive and financial bid shall not beopened.

  - Qualification and Experience of Key Personnel required for administration and executionoftheContract[Ref.Clause4.3(b)(b)(ii)].uploadbiographicaldatafortechnical personnel (Refer also to Clause. 4.1 (e) of Instructions tobidders).

(Refer also to Sub Clause 9.1 of the General Conditions of Contract).

| Position | Name | Qualification | Total Professional Experience (Years) | Experience in the proposed position (Years) |
| --- | --- | --- | --- | --- |

Note: The signed CVs of the Technical Personnel must be uploaded along with the bid. Non- compliance of the above or non-furnishing of the CV as above or conditional deployment of any of the above personnel or proposal to employ lesser number of personnel than above shall make the bid non-responsive and financial bid shall not be opened.

  - Information on litigation history in which the Bidder isinvolved.

| Other Party | Employer | Cause of Dispute | Amount involved (Rs lakh) | Remarks showing Present Status |
| --- | --- | --- | --- | --- |

- Bidders should upload the scanned copy of the following affidavits/undertakings as per formats enclosed hereinafter and also send original copy of Affidavit/Undertakings:-

- Affidavit (it should be on stamp paper attested by NotaryPublic)

- Undertakingregardingavailabilityofminimumcashamountingto25%ofthevalueof work during implementation of the Contract towards workingcapital.

- Undertaking that the Bids shall remain valid for the period specified in Clause15.1

AFFIDAVIT

- I, the undersigned, do hereby certify that all the statements made in the enclosed attachments are true andcorrect.

- TheundersignedalsoherebycertifiesthatneitherourfirmM/s

have abandoned any work in India nor any contract awardedtousforsuchworkshavebeenrescinded,duringlastfiveyearspriortothedateofthis bid.

- The undersigned hereby Authorize(s) and request(s) any bank, person, firm or corporation to furnish pertinent information deemed necessary and requested by the Employer to verify this statement or regarding our competence and generalreputation.

- The undersigned understands and agrees that further qualifying information may be requested,andagreestofurnishanysuchinformationattherequestoftheEmployerandwithin the prescribedtime.

(Signed by an Authorized Representative of theFirm)

Name of theRepresentative

Name ofFirm

Date

To be notarized by Notary

## UNDERTAKING

I,theundersigneddoherebyundertakethatourfirmM/s											shall maintain availability of minimum cash amounting to25%ofthevalueoftheworkduringimplementationoftheContracttowardstheworkingcapital.

(Signed by an Authorized Representative of theFirm)

Name of theRepresentative

Name ofFirm

Date

## UNDERTAKING

I,theundersigneddoherebyundertakethatourfirmM/s									agreetoabidebythisbidforaperiodof120days after the date fixed for receiving the same and it shall be binding on us and may be accepted at any time before the expiration of thatperiod.

(Signed by an Authorized Representative of theFirm)

Name of theRepresentative

Name ofFirm

Date

# SECTION-4

FORMS OF BANK GUARANTEES

LETTER OF ACCEPTANCE (LOA) AND AGREEMENT

SECTION-4

FORMS OF BANK GUARANTEES

LETTER OF ACCEPTANCE (LOA) AND AGREEMENT

FORM OF BANK GUARANTEE FOR BID SECURITY

WHEREAS	(Name	ofTenderer) (hereinafter called the Tenderer) wishes to submit his tender for Short term maintenance of Takhatpur Ex. Road from Km. 26.542 to Km. 32.093, Mungeli Ex. Road from Km. 45.786 to Km. 56.275, Pandariya Ex. Road from Km. 82.582 to Km. 87.133 and Pondi Ex. Road from Km. 103.166 to Km. 104.756 = 22.181 Km. on N.H.-130A in the  state of Chhattisgarh after called “theTender” KNOW ALL MEN by these present thatwe		(Name ofBank)of		(Nameofcountry)havingourregisteredofficeat(		) (hereinafter called the ‘Bank’) are bound unto the ------------------------ (hereinafter called “the Employer”) in the sumofRs.		(Rupees			)*forwhichpaymentcantrulybemadetothesaidEmployer.TheBankbind themselves, their successors and assigns by these present with the common seal of the Bank thisday			of	andundertaketopaytheamountof	 Rs		(Rs.inwords		) to the Employer uponreceiptofhis first written demand without the Employer having to substantiate hisdemand.

The conditions of this obligation are:

- IfthetendererwithdrawshistenderduringtheperiodofTendervalidityspecifiedin

the Form of Tender.

Or

- If the Tenderer having been notified of the acceptance of his Tender by theEmployer

during the period of tender validity.

  - fails or refuses to execute the Form of Agreement in accordance with the Instructions to Bidders, if required;or

  - fails or refuses to furnish the Performance Security, in accordance with the Instructions to Bidders.

We undertake to pay to the Employer up to the above amount upon receipt of his first written demand, without the employer having to substantiate his demand, provided that in his demand the Employer will note that the amount claimed by him is due to him owing to the occurrence of any one of the above conditions, specifying the occurred condition or conditions.

This guarantee will remain in force up to and including the date 45 days beyond the validity of thebidasstatedintheInstructionstoBiddersorasitmaybeextendedbytheEmployer,atany timepriortotheclosingdateforsubmissionoftheTendersNoticeofwhichextensiontotheBank is hereby waived. Any demand in respect of this guarantee should be made on the Bank on or before the date of expiry of thisguarantee.

Notwithstandinganythingcontainedhereinbefore,ourliabilityunderthisguaranteeisrestricted toRs.(Rs.	inwords)andtheguaranteeshallremainvalidtill

. Unless a claim or a demand in writing is served upon us on or before

all our liability under this guarantee shallcease.

SIGNATURE OF AUTHORISED REPRESENTATIVE OF THEBANK

NAMEANDDESIGNATION	EMPLOYEECODENUMBER

SEAL OF THEBANK

SIGNATUREOFTHEWITNESS(IFTHISISTOBEWITNESSEDASPERBANK’SPOLICY)

NAME OF THEWITNESS

ADDRESS OF THEWITNESS

## FORM OF BANK GUARANTEE FOR PERFORMANCE SECURITY

To

Superintending Engineer, NH Zone P.W.D., Raipur Circle

NH Campus, Pension Bada, Raipur (C.G.),

WHEREAS……………………………………………… (name and address of contractor) hereinafter called “the Contractor” has undertaken, in pursuance of Letter of Acceptance No.………………………. Dated ………………. to execute………………………. (name of Contract and brief description of Works) (hereinafter called “the Contract”).

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee for the sum specified therein as security for compliancewith his obligations in accordance with theContract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee:

NOW THEREOF we hereby affirm that we are the guarantor and responsible to you on behalf of the Contractor, up to a total amount of Rs……………… (amount of guarantee) (Rupees…	(inwords)andweundertaketopayyou,uponyourfirstwrittendemandandwithoutcavilorargument,anysumorsumswithinthelimitsof………………..(amountofguarantee)asaforesaidwithoutyourneedingtoproveortoshowgroundsorreasonsfor your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

WefurtheragreethatnochangeoradditiontoorothermodificationofthetermsoftheContract or of the works to be performed there under or of any of the contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition ormodification.

Thisguaranteeshallbevaliduntil60daysfromthedateofexpiryoftheDefectsLiabilityPeriod.

Notwithstandinganythingcontainedhereinbefore,ourliabilityunderthisguaranteeisrestricted toRs.	(Rs.	inwords)andtheguaranteeshallremainvalidtill	. Unless a claim or a demand in writing is served upon us on or before	 all our liability under this guarantee shallcease.

Signature and seal of the Guarantor with Name, Designation, Employee Code Number and Telephone Number………………………………………………………

Name oftheIssuing	Name of theControlling

Bank/Branch-------------------	Branch/Bank------------------------------

Address andTelephoneNumber	Address and TelephoneNumber………….

Date………………………….

In the presence of (if this is to be witnessed as per bank’s policy) …………………………………

1………………………………………………………………………………………… (Name, Address andOccupation)

2………………………………………………………………………………………… (Name, Address andOccupation)

AnamountshallbeinsertedbytheGuarantor,representingthepercentageoftheContractPrice

specified in the Contract and denominated in Indian Rupees.

## FORM OF BANK GUARANTEE FOR ADDITIONAL PERFORMANCE SECURITY

To

Superintending Engineer, NH Zone P.W.D., Raipur Circle

NH Campus, Pension Bada, Raipur (C.G.),

WHEREAS……………………………………………… (name and address of contractor) hereinafter called “the Contractor” has undertaken, in pursuance of Letter of Acceptance No. ………………………. Dated ………………. to execute………………………. (name of Contract and brief description of Works) (hereinafter called “the Contract”).

AND WHEREAS it has been stipulated by you in the said Contract that the Contractor shall furnish you with a Bank Guarantee for the sum specified therein as security for compliancewith his obligations in accordance with theContract;

AND WHEREAS we have agreed to give the Contractor such a Bank Guarantee:

NOW THEREOF we hereby affirm that we are the guarantor and responsible to you on behalf of the Contractor, up to a total amount of Rs……………… (amount of guarantee) (Rupees…	(inwords)andweundertaketopayyou,uponyourfirst writtendemandandwithoutcavilorargument,anysumorsumswithinthelimitsof……………….. (amountofguarantee)asaforesaidwithoutyourneedingtoproveortoshowgroundsorreasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the Contractor before presenting us with the demand.

WefurtheragreethatnochangeoradditiontoorothermodificationofthetermsoftheContract or of the works to be performed there under or of any of the contract documents which may be made between you and the Contractor shall in any way release us from any liability under this guarantee, and we hereby waive notice of any such change, addition ormodification.

Thisguaranteeshallbevaliduntil28 (twenty eight) days after Project Completion Date.

Notwithstandinganythingcontainedhereinbefore,ourliabilityunderthisguaranteeisrestricted toRs.	(Rs.	inwords)andtheguaranteeshallremainvalidtill 	. Unless a claim or a demand in writing is served upon us on or before 	 all our liability under this guarantee shallcease.

Signature and seal of the Guarantor with Name, Designation, Employee Code Number and Telephone Number………………………………………………………

Name oftheIssuing	Name of theControlling

Bank/Branch-------------------	Branch/Bank------------------------------

Address andTelephoneNumber	Address and TelephoneNumber………….

Date………………………….

In the presence of (if this is to be witnessed as per bank’s policy) …………………………………

1………………………………………………………………………………………… (Name, Address andOccupation)

2………………………………………………………………………………………… (Name, Address andOccupation)

AnamountshallbeinsertedbytheGuarantor,representingthepercentageoftheContractPrice

specified in the Contract and denominated in Indian Rupees.

FORM OF LETTER OF APPLICATION

To,

Superintending Engineer, NH Zone P.W.D., Raipur Circle

NH Campus, Pension Bada, Raipur (C.G.),

[Address of Employer]

DESCRIPTIONOFWORKS:	BID FOR“Short term maintenance of Takhatpur Ex. Road from Km. 26.542 to Km. 32.093, Mungeli Ex. Road from Km. 45.786 to Km. 56.275, Pandariya Ex. Road from Km. 82.582 to Km. 87.133 and Pondi Ex. Road from Km. 103.166 to Km. 104.756 = 22.181 Km. on N.H.-130A in the  state of Chhattisgarh”

Dear Sir,

Having examined the Bid Document, Instructions to Bidders, Qualification Information, Scope of

works, etc. for the subject work we hereby submit our bid for the subject work.

It is certified that the information furnished in this document is true and correct. The proposal is unconditional and unqualified. We undersigned accept that the Employer reserves the right to reject any or all applications without assigning any reason.

Thanking you,

Yoursfaithfully,

(Authorized Signatory)

## For and on behalf of M/s

## FORM OF LETTER OF ACCEPTANCE

No.………………………….	Dated………………..….

To

## M/s………………………….

Sub.: …………………………. Name of Work …………………………………

Sir,

Based on your bidsubmittedon	in compliance of bidding document of [theEmployer]for execution of theworks of	, it is hereby notifiedthatyourbidforaContractPriceofRs……………(Rupeesinwords…	) has been acceptedforand on behalf of [the Employer]

You are hereby requested to furnish Performance Security plus additional security in the form detailed in Clause 32.2 of ITB for an amount equivalent to Rs…………… (Rupees in words…..…) within 10 days as per provisions of Clause 32.1 of ITB of the bid documentandsign the contract agreement failing which the actions as stipulated in Clause-32.3 of ITB shall be taken.

Thanking you,

Yours faithfully,

(………………..)

Employer

FORM OF AGREEMENT

AGREEMENT

This agreementmadethe	dayof	betweenthe Superintending Engineer, NH P.W.D., Bilaspur Circle, onbehalf of “Employer” (hereinaftercalled“theEmployer”oftheonepartand 	 (here in after called “the Contractor”) of the otherpart.

AND WHEREAS the Employer invited bids from eligible bidders for the execution of certain

works, viz………………………………………………

ANDWHEREASpursuanttothebidsubmittedbytheContractor,vide	(here in after referred to as the “BID” or “ÖFFER”) for the execution of works, the Employer by his letter ofacceptancedated	accepted the offer submitted by the Contractor for the execution and completion of such works and remedying of any defects thereon, on terms and conditions in accordance with the documents listed in Para 2below.

AND WHEREAS the Contractor by a deed ofundertakingdated	has agreed to abide by all the terms of the bid, including but not limited to the amount quoted for the execution of Contract, as stated in the bid, and also to comply with such terms and conditions as may be required from time to time.

AND WHEREAS the Contractor has agreed to undertake such works and has furnished a Performance Security pursuant to Clause 32 of ITB (Section-2).

NOW THIS AGREEMENT WITNESSETH as follows:

- In this agreement, words and expressions shall have the same meaning as are respectively assigned to them in the conditions of contract hereinafter referredto;

- Thefollowingdocumentsshallbedeemedtoformandbereadandconstruedaspart

of this agreement viz.

  - Agreement;

  - Letter ofAcceptance;

  - Contractor’sBid;

  - ContractData;

  - General Conditions ofContract;

  - Addendum to General Conditions ofContract;

  - RoadMaintenanceStandardsandSpecificationsforRoadMaintenanceWorks;

  - Drawings, ifany;

  - Bill of Quantities;and

  - Any other document listed in the ContractData.

- The foregoing documents shall be construed as complementary and mutually explanatory one with another. Should any ambiguity or discrepancy be noted, then the order of precedence of these documents shall be subject to the order as listed above and interpreted in the above order ofpriority.

- In consideration of the payments to be made by the Employer to the Contractor as hereinaftermentioned,theContractorherebycovenantswiththeEmployertoexecute and complete the works and remedy any defects therein in conformity in all respects with the provisions of thecontract.

- TheEmployerherebycovenantstopaytheContractorinconsiderationoftheexecution and completion of the works and remedying of defects therein, the Contract Price or such other sum as may become payable under the provisions of the contract at the times and in the manner prescribed by thecontract.

IN WITNESS WHEREOF the parties here to have caused this agreement to be executed the day and year above written. Signed, sealed and delivered by the said Employer through his Authorized Representative and the said Contractor through his Power of Attorney holder.

## Binding SignatureofEmployer	Binding Signature ofContractor

For and onbehalfof	For and on behalf of M/s----------------------

In thepresenceof	In the Presence of

- Name:	1.Name:

Address:	Address:

- Name:	2.Name:

Address:	Address:

# SECTION -5

GENERAL CONDITIONS OF CONTRACT (GCC) AND CONTRACT DATA

## SECTION 5

GENERAL CONDITIONS OF CONTRACT (GCC)

TABLE OF CLAUSES

| A. | General |  | 31. | Correction of Defects noticed during the Defects Liability Period |
| --- | --- | --- | --- | --- |
| 1. | Definitions |  | 32. | Uncorrected Defects |
| 2. | Interpretation |  | D. | Cost Control |
| 3. | Language and Law |  | 33. | Bill of Quantities |
| 4. | Engineer’s Decisions |  | 34. | Changes in the Quantities |
| 5. | Delegation |  | 35. | Variations |
| 6. | Communications |  | 36. | Payments for Variations |
| 7. | Subcontracting |  | 37. | Cash Flow Forecasts |
| 8. | Other Contractors |  | 38. | Payment Certificates |
| 9. | Personnel and Equipment |  | 39. | Payments |
| 10. | Employer’s and Contractor’s Risks |  | 40. | Compensation Events |
| 11. | Employer’s Risks |  | 41. | Taxes and Currencies for Payments |
| 12. | Contractor’s Risks |  | 42. | Security Deposit/Retention Money |
| 13. | Insurance |  | 43. | Liquidated Damages |
| 14. | Site Investigation Reports |  | 44. | Advance Payments |
| 15. | Queries about the Contract Data |  | 45. | Performance Security |
| 16. | Contractor to Construct the Works |  | 46. | Cost of Repairs |
| 17. | The Works to be completed by Intended Completion Date | the | E. | Finishing the Contract |
| 18. | Approval by the Engineer |  | 47. | Completion |
| 19. | Site Regulations and Safety |  | 48. | Taking Over |
| 20. | Discoveries |  | 49. | Final Account |
| 21. | Possession of the Site |  | 50. | Operation and Maintenance Manual |
| 22. | Access to the Site |  | 51. | Termination |
| 23. | Instructions |  | 52. | Payment upon Termination |
| 24. | Procedure for Dispute Resolution |  | 53. | Property |
| b. | Time Control |  | 54. | Release from Performance |
| 25. | Programme |  |  |  |
| 26. | Extension of the Intended Completion Date |  | F. | Other Conditions of Contract |
| 27. | Delays ordered by the\Engineer |  | 55. | Labour |
| 28. | Management Meetings |  | 56. | Compliance with Labour Regulations |
| C. | Quality Control |  | 57. | Drawings and Photographs of the Works |
| 29. | Identifying Defects |  | 58. | The Apprentices Act, 1961 |
| 30. | Tests |  |  |  |

A. GENERAL

- Definitions

  - Terms which are defined in the Contract Data but not defined in the Conditions of Contract keep their defined meanings. Capital initials are used to identify definedterms.

Bill of Quantities means the priced and completed Bill of Quantities forming part of the Contractor’s Bid.

Certificate of Completion is the Certificate issued by the Engineer upon completion of works or

parts thereof as applicable in accordance with Clause 47.

Compensation Events are those defined in Clause 40.

Contract is the Contract between the Employer and the Contractor to maintain the road assets and to execute, complete, and maintain the Works. It consists of the documents listed in Clause 2.3.

Contract Data defines the documents and other information, which comprise the Contract.

Contractor is a person or corporate body whose Bid to carry out the Road MaintenanceWorks and Activities has been accepted by theEmployer.

Contractor’s bid is the completed Bidding Document submitted by the Contractor to the Employer.

Contract Price is the price stated in the Letter of Acceptance and thereafter as adjusted in accordance with the provisions of the Contract.

Days are calendar days; months are calendar months.

Defect is any part of the Maintenance Works and Activities not completed in accordance with

the Contract Specifications.

Defects Liability Certificate is the certificate issued by the Engineer, after the Defects Liability

Period has ended and upon correction of Defects by the Contractor.

Defects Liability Period means the period so stipulated in the Contract Data, calculated from theCompletionDate,duringwhichtheContractorremainsresponsiblefortherectificationofany defect in the Works he hasundertaken.

EmployeristhepartyasdefinedintheContractData,whoemploystheContractortocarryout the Works. The Employer may delegate any or all functions to a person or body nominated by him for specifiedfunctions.

Engineer is the person named in the Contract Data (or any other competent person appointed by the Employer and notified to the Contractor, to act in replacement of the Engineer) who is responsibleforsupervisingtheexecutionoftheWorksandadministeringtheContractonbehalf of theEmployer.

EquipmentistheContractor’smachineryandvehiclesbroughttemporarilytotheSitetoexecute the Maintenance Works andActivities.

IntendedCompletionDateisthedate,asgivenincontractdata,onwhichitisintendedthatthe ContractorshallcompletetheWorksasperscopeunderthecontract.TheintendedCompletion Date may be revised only by the Engineer by issuing an Extension of Time after approval from theEmployer.

Letter of Acceptance means the formal acceptance of the Bid by the Employer.

Materials are all supplies, including consumables, used by the Contractor for incorporation in the Maintenance Works and Activities.

MaximumResponseTimemeansthemaximumpermissibletimewithinwhichremedialaction must be completed prior to a defect exceeding the permissible tolerance. Maximum Response Timecommencesfromthetimeofearliestdetectionofthedefectby(i)observationofthedefect by the Contractor, or (ii) notification of the defect by the Engineer, or (iii) intimation of the defect by a roaduser.

Notice to Proceed means the notice issued by the Employer to the Contractor to proceed with the work after signing of the contract pursuant to Clause 32.1 of ITB.

Permissible Tolerance means the maximum permissible amount or quantity of a defect in road-assetconditionthatwillnotbeexceededatanytime.Ifanydefectexceedsthepermissible tolerance,itshallbetreatedas“non-compliance”andtheContractorshallbepaidinaccordance with the relevant provisions in thiscontract.

Project Manager is a person appointed by the Contractor who is in charge of managing all activitiesoftheContractorundertheContract.HeisalsotheContractor’sRepresentativeforthe purpose of thisContract.

Road means the Road or package of roads in network or scattered for which the Maintenance Works and Activities are to be carried out under the Contract.

“Road Assets” include the following:

    - Main carriageway with shoulders (paved and/or earthen), medians, slip roads, service roads;

    - Road embankment including slopes, protection works, kerbs and chutedrains;

    - Roadway in cutting including slopes protection works,drains;

    - Culverts, Bridges, Over/Underpasses, retaining walls, Guide bunds, Floor protectionworks;

    - Roadsigns,roadmarkings,roaddelineators,guardrails,safetybarriers,railings, fencings, parapets, kilometer stones, 200 m stones, road boundarystones;

    - All types of drains, trees, plantations and erosion controlmeasures;

    - Roadland;

    - Any other project facility or asset forming integral part of theroad(s).

Road Maintenance Standards is the collective term for parameters which define the condition inwhichtheroadassetsarerequiredtobemaintainedandotherrequirementsregardingsafety and quality of works to be complied with by theContractor.

## Road Maintenance Works and Activities to be carried out by Contractor shall include:

Maintenance of the road specified in the BOQ and executingother items of road maintenance worksas ordered by the Engineer.

## Rectification Standard

The Contractor shall maintain the specific parts of the road aspects as specified in BOQ or as ordered by Engineer in charge and ensure road users safety and comfort. The maintenance activities shall be so planned that the defects are repaired well before they reach maximum condition as per the permissible tolerance

Site is the area defined as such in the Contract Data, where maintenance works are to be

executed.

Specifications means the Specifications of the Maintenance Works including the Road

Maintenance Standards as per the Contract.

Start Date is given in the Contract Data. It is the date when the Contractor shall commence execution of the Works.

Service Level means the defined condition in which the road assets are to be maintained by the

Contractor.

Sub-Contractor is a person or corporate body who has a Contract with the Contractor to carry out a work under the Contract, which includes part of the agreed scope of works at the Site.

Temporary Works are works designed, constructed, installed and removed by the Contractor that are needed for Works and Activities.

Time for Completion means the duration for completing the execution of maintenance works andpassingthetestsoncompletionoftheWorksoranySectionorpartthereofasstatedinthe ContractDataorasextendedbytheEngineerbyissuinganExtensionofTimeaftertheapproval from theEmployer.

VariationisaninstructiongivenbytheEngineerinwritingwhichvariesthescopeofMaintenance Works.

WorkOrderisanorderissuedbytheEngineertotheContractorforexecutionofcertainworks, specifyingthetimelimitswhichmaybeinvariancewiththeapprovedprogrammeorinvariation to the scope of work depending upon the siterequirement.

## Interpretation

  - In interpreting these Conditions of Contract, singular also means plural, male also means female or neuter and the other way around. Headings have no significance. Words have their normal meaning under the language of the Contract Unless specifically defined. The Engineer will provide instructions clarifying queries about these Conditions ofContract.

  - If part completion is specified in the Contract Data, references in the Conditions of ContracttotheWorks,theCompletionDateandtheIntendedCompletionDateapplytoanypart of the Works (other than references to the Completion Date and Intended Completion Date for the whole ofWorks).

  - The following documents shall be deemed to form and be read and construed as part of the Contract. In case any ambiguity or discrepancy is noted, then the Contract shall be interpreted in the following order ofpriority:

    - Agreement;

    - Notice to Proceed with theWork;

    - Letter ofAcceptance;

    - Contractor’sBid;

    - ContractData;

    - General Conditions ofContract;

    - RoadMaintenanceStandardsandSpecificationsforRoadMaintenanceWorks,

Part I and Part Il;

    - Priced Bill of Quantities;and

    - Any other documents listed in the ContractData.

## Language andLaw

  - The language of the Contract shall be in English and the law governing the Contract as given in ContractData.

## Engineer’sDecisions

  - The Employer shall designate and notify to the Contractor in writing the name of the Engineer.

  - Except where otherwise specifically stated, the Engineer will decide contractual matters between the Employer and the Contractor in the role representing the Employer. The Engineer shall have no authority to relieve the Contractor of any of his obligations under the Contract.

## Delegation

  - The Engineer, duly informing the Employer, may delegate any of his duties and responsibilities to other people, after notifying the Contractor and may cancel any delegation under intimation to theContractor.

## Communications

  - Communications between parties that are referred to in the Conditions shall be effective only when in writing. A notice shall be effective only when it is delivered as per Indian Law.

## Subcontracting-Deleted

## OtherContractors

  - The Contractor shall cooperate and share the Site with other Contractors, public authorities, utilities, and the Employer between the dates given in the Schedule of Other Contractors, as referred to in the Contract Data. The Contractor shall also provide facilities and services for them as described in the Schedule. The Employer may modify the Schedule of OtherContractorsandshallnotifytheContractorofanysuchmodification.TheContractorshall cooperate in such situations aswell.

  - The Contractor should take up the works in convenient reaches as decided by the Engineertoensurethatthereisleasthindrancetothesmoothflowoftrafficincludingmovement of vehicles and equipment of other Contractors till the completion ofWorks.

## Personnel andEquipment

  - The Contractor shall employ the technical personnel named in the Contract Data or other technical persons approved by the Engineer.The Engineer will approve any proposed replacementoftechnicalpersonnelonlyiftheirrelevantqualificationsandabilitiesaresubstantially equaltoorbetterthanthoseofthepersonnelstatedintheContractData.Ifthepersonnelstated intheContractDataarenotdeployedonsitebytheContractorwithin15daysofissueofnotice to proceed with the work, a penalty of 5000/- per day per person shall be levied for next 30 days, beyond which it shall be treated as a breach of Contract and action will be taken as per Clause51.

  - TheContractorshallusetheequipmentidentifiedinthebidalongwithcompetent

operators and adequate stock of spares for smooth operations.

  - If the Engineer asks the Contractor to remove a person who is a member of the Contractor’sstafforworkforce,statingthereasons,theContractorshallensurethattheperson leaves the Site within seven days and has no further connection with the Works under the Contract.

  - The Contractor shall establish, within his own organizational structure, a planning unit, staffed with suitably qualified personnel. The team will be headed by a Project Manager who will be assisted by his representatives, i.e. Site Manager and Manager, Planning. The task of this unit willbe:

    - To plan, and to verify continuously the degree of compliance by the Contractor with the specified Road Maintenance Standards and report the same to the Engineer in the format acceptable to theEngineer.

    - To maintain and update the road condition inventoryregularly.

    - To assist the Engineer in verification of thecompliance.

  - The Contractor’s planning unit mentioned under Sub-clause 9.4 shall report the level of compliance with the required Service Levels in the standard formats acceptable to the Engineer.

## .	Employer’s and Contractor’sRisks

  - The Employer carries the risks which this Contract states are Employer’s risks, and the Contractor carries the risks which this Contract states are Contractor’srisks.

## Employer’sRisks

  - The Employer is responsible for the expected risks which are (a) in so far as they directly affect the execution of the Maintenance Works and Activities included in the Contract, the risks of war, hostilities, invasion, act of foreign enemies, rebellion, revolution, insurrection or military or usurped power, civil war, riot, commotion or disorder (unless restricted to the Contractor’s employees), natural calamities and contamination from any nuclear fuel or nuclear waste or radioactive toxic,explosive.

## Contractor’sRisks

  - All risks of loss of or damage to physical property and of personal injury and death, which arise during and in consequence of the performance of the Contract other than the excepted risks, referred to in Clause 11.1, are the risks of theContractor.

## Insurance

  - The Contractor at his cost shall provide, in the joint names of the Employer and the Contractor,insurancecoverfromtheStartDatetothecompletionofdefectliabilityperiod,inthat amounts and deductibles stated in the Contract Data for the following events which are due to the Contractor’srisks:

    - Loss of or damage to the Works andMaterials

    - Loss of or damage toEquipment

    - Loss of or damage to property (except the Works Materials and Equipment) in connection with theContract

    - Third Party LiabilityInsurance

    - Automobile LiabilityInsurance

    - Workers’Compensation

    - Employer’sLiability

    - Other Insurances

  - InsurancepoliciesandcertificatesforinsuranceshallbedeliveredbytheContractorto the Engineer for the Engineer’s approval before the Start Date. All such insurance shallprovide for compensation to be payable in Indian Rupees to rectify the loss or damageincurred.

  - If the Contractor does not provide any of the policies and certificates required, the Employer may affect the insurance which the Contractor should have provided and recover the premiums the Employer had paid from payments otherwise due to the Contractor or, if no payment is due, the payment of the premiums shall be a debt due from theContractor.

  - Alterations to the terms of insurance shall not be made without the approval of the Engineer.

  - Bothpartiesshallcomplywithanyconditionsoftheinsurancepolicies.TheContractor shallensurethatwhereverapplicable,itsSub-Contractor(s)shalltakeoutandmaintainineffect adequate insurance policies for their personnel and vehicles and for works executed by them undertheContractunlesssuchSub-Contractor(s)is/arecoveredbythepoliciestakenoutbythe Contractor.

## Site InvestigationReports

  - TheContractor,inpreparingtheBid,mayrelyathisownrisksandliabilityonanySite Investigation Reports referred to in the Contract Data, supplemented by any other information available tohim.

## Queries about the ContractData

  - TheauthorizedrepresentativeoftheEmployerasstatedintheContractdatawill

Clarify queries on the Contract Data.

## Contractor to Construct theWorks

  - The Contractor’s obligations cover the carrying out of all Maintenance Works and Activities as defined in the Contract for keeping the roads in accordance with the Road Maintenance Standards.

TheContractorshallconstruct,installandmaintaintheWorksinaccordancewiththeSpecifications

and Drawings.

## The Works to be completed by the Intended CompletionDate

  - The Contractor may commence execution of the Maintenance Works and Activities on the Start Date and shall carry out the Works in accordance with the Programme submitted by the Contractor, as updated with the approval of the Engineer, and complete them by the Intended CompletionDate. The BOQ based items as per Bill No. 1 & 2 shall be completed within 2 months of the commencement of the work, however, in the performance based items in Bill No. 3 corresponding to pavement repair including potholes/ patch/ rut etc., shall have to be completed within 1 month from the commencement of the work, subsequent to which if any defects found,the payment shall be subject to deductions as per the provisions of the Contract.

## Approval by theEngineer

  - The Contractor shall prepare/propose the Maintenance Manuals as per relevant applicable Standards and Specifications and existing policies/guidelines/practices and get the same approved from theEngineer/Employer.

  - The Contractor shall submit Specifications and Drawings showing the proposed TemporaryWorkstotheEngineer,whoistoapprovethemiftheycomplywithSpecificationsand drawings.

  - The Contractor shall be responsible for design of TemporaryWorks.

  - The Engineer’s approval shall not alter the Contractor’s responsibility for design of the TemporaryWorks.

  - TheContractorshallobtainapprovalofthirdpartiestothedesignofTemporaryWorks byEngineer.

  - AllDrawingspreparedbytheContractorfortheexecutionoftemporaryorpermanent Works, are subject to prior approval by the Engineer before theiruse.

## Site Regulations andSafety

  - TheContractorshallberesponsibleforthesafetyofallactivitiesontheSite,including arrangements for smooth flow of traffic at his own cost as per guidelines of the IRC/Ministry of Road Transport & Highways. He shall provide proper barricading, diversion boards, etc. He shall be fully responsible for the safety of workers and staff at site and provide safety helmets, reflective jackets and other PPE to the workers, inspecting officers andsupervisors.

## Discoveries

  - Anythingofhistoricalorotherinterestorofsignificantvalueunexpectedlydiscovered on the Site is the property of the Employer. The Contractor shall notify the Engineer of such discoveries and carry out the Engineer’s instructions for dealing withthem.

## Possession of the Site

  - The Employer shall give possession of all parts of the Site to the Contractor on or before the start date of theContract.

## Access to theSite

  - TheContractorshallallowaccesstotheSiteandtoanyplacewhereworkinconnection withtheContractisbeingcarriedout,orisintendedtobecarriedouttotheEngineerandanyperson/persons/agency authorized by:

    - The Engineer

    - The Employer

## Instructions

  - The Contractor shall carry out all instructions of the Engineer pertaining to the maintenance works which comply with the applicable laws where the Site islocated.

  - The Contractor shall permit the Engineer/Employer to inspect the Contractor’s contemporary records in respect of invoice of bitumen, cement, aggregates and steel, if so desired by theEngineer.

## Procedure for DisputeResolution

  - Arbitration

The procedure for arbitration will be as follows:

- In case of Dispute or difference arising between the Employer and the Contractor relating to any matter arising out of or connected with this contract, such disputes  or differences shall be settled in accordance with the Arbitration and Conciliation Act, 1996 as amended vide Act of 2015. The Arbitral Tribunal shall consist of sole Arbitrator from the panel of three Arbitrators proposed by the Employer and choice of selecting one given to the Contractor. Contractor shall select one out of the three names of Arbitrators given to him within 30 days failing which the Employer shall nominate the Arbitrator out of the panel of three Arbitrators. In case the Contractor objects to the Arbitrator selected by the Employer, the Employer shall refer selection ofArbitratortotheIndianRoadsCongressfornominatingtheArbitratorforthedispute andbothpartiesagreethattheArbitratorsoselectedbyIRCshalldecidethedispute. IndianRoadsCongressshalltrytoappointArbitratorpreferablyfromthestatewhere the project is located or otherwise from adjoiningStates.

- Arbitration proceedings shall be held at Raipur, Chhattisgarh,India, and the language of the arbitration proceedings and that of all documents and communications between the parties shall beEnglish.

- ThedecisionoftheArbitratorshallbefinalandbindinguponbothparties.Thecostand expensesofArbitrationproceedingswillbepaidasdeterminedbytheArbitralTribunal However, the expenses incurred by each party in connection with the preparation, presentation,etc.ofitsproceedingsshallbebornebyeachpartyitself.Thefeesand expenses of the Arbitrator shall be shared equally by both theparties.

- PerformanceunderthecontractshallcontinueduringtheArbitrationproceedingsand payments due to the Contractor by the Employer shall not be withheld, unless they are the subject matter of arbitrationproceedings.

B. TIME CONTROL

- Programme

  - The Contractor shall submit to the Engineer for approval a programme within period specifiedinthecontractdatashowingthegeneralmethods,arrangements,order,andtimingfor all the maintenance works andactivities.

  - The Engineer may issue the work order in stages specifying the time limit for the same as and when required except the performance-based maintenanceitems.

  - An update of the Programme shall be a programme showing the actual progress achieved on each activity and the effect of progress achieved on the timing of the remaining Works, including any changes to the sequence ofactivities.

  - The Contractor shall submit to the Engineer for approval an updated Programme   at intervals. If the Contractor does not submit an updated Programme within this period, the EngineermaywithholdtheamountstatedintheContractDatafromthenextpaymentcertificate andcontinuetowithholdthisamountuntilthenextpaymentafterthedateonwhichtheoverdue Programme has beensubmitted.

  - TheEngineer’sapprovaloftheProgrammeshallnotaltertheContractor’sobligations. The Contractor may revise the Programme and submit it to the Engineer again at any time. A revised Programme shall show the effect of Variations and CompensationEvents.

## Extension of the Intended CompletionDate

  - The Engineer shall extend the Intended Completion Date only after approval of the EmployerifaCompensationEventoccursoraVariationisissuedwhichmakesitimpossiblefor CompletiontobeachievedbytheIntendedCompletionDatewithouttheContractortakingsteps to accelerate the remaining Works, which would cause the Contractor to incur additional cost.

  - The Engineer, within 14 days of receiving full justification from the Contractor for extension of Intended Completion Date, will refer to the Employer his recommendation. The Employershall,innotmorethan21daysfromthedateofreceiptofEngineer’srecommendation, communicate to the Engineer the acceptance or otherwise. The Engineer shall convey the decision of the Employer to theContractor.

## Delays Ordered by theEngineer

  - TheEngineermayinstructtheContractortodelaythestartorprogressofanyactivity within the Works. Delay/delays totaling more than 30 days will require prior written approval of theEmployer.

## Management Meetings

  - The Engineer may require the Contractor to attend a management meeting. The businessofamanagementmeetingshallbetoreviewtheplansandprogressfortheMaintenance Works.

28.2	TheEngineershallrecordthebusinessofmanagementmeetingsandprovidecopies of the record to those attending the meeting. The responsibility of the parties for actions to be taken shall be decided by the Engineer either during the management meeting or after the management meeting and to be intimated in writing to all those who attended themeeting.

## QUALITYCONTROL

- IdentifyingDefects

  - The Engineer shall check the Contractor’s work and notify the Contractor of any Defects those are found. Such checking shall not affect the Contractor’s responsibilities. The Engineer may instruct the Contractor to uncover and test any work that the Engineer considers may have aDefect.

## Tests

  - TheContractorshallsetupafieldlaboratorywithinperiodstatedincontractdataand

be solely responsible for:

- Carrying out the mandatory tests prescribed in Technical Specificationsand

- For the correctness of test/procedures, whether preformed in his laboratory or elsewhere.

  - If the Engineer instructs the Contractor to carry out a test not specified in the Specifications to check whether any work has a Defect and the test shows that it does, the Contractor shall pay for the testing charges and for any number of samples. Otherwise, the Employer shall pay for the testingcharges.

## Correction of Defects noticed during the Defects LiabilityPeriod

  - Theworkscarriedoutshallbeofveryhighstandard,requiringnomajorrepairsonthe road for at least, during defects liability period, after the date of completion ofworks.

  - If any defects including shrinkage, cracks, other faults appear in the works within the periodspecifiedhereunderafterissueof “Takingover”certificate,theEngineershallgivenotice to the Contractor of any defects before the end of the Defects Liability Period. The Defects Liability Period shall be extended for as long as the defects remain to becorrected.

  - Every time notice of a defect is given, the Contractor shall correct the notified defect at his own cost within the length of time specified in the Engineer’snotice.

  - The defect liability period is not applicable for works of routine maintenance such as pot holes/ patch repairs/ruts repairs/ cleaning and clearing etc., under performance based BOQitem.

However, for other specific items of works (if any), got executed as ordered by Engineer (if any), the Defects Liability Period shall be 36 months, counted from the Date of Completion stated in the Certificate of Completion issued in pursuance of Clause 47.

  - If during the Defects Liability Period any defect is found in the design, engineering, materials and workmanship of the Works and Services executed by the Contractor, then the Contractorshallpromptly,inconsultationandagreementwiththeEngineer,appropriatelyremedySuchdefectsatitscost,orrepair,replaceorotherwisemakegood(astheContractorshall,atits discretion,determine)suchdefectsaswellasanydamagetotheRoadcausedbysuchdefects.

  - The Contractor’s obligations under this Clause 31 shall not applyto:

- anymaterialthatissuppliedbytheEmployer,andnormallyconsumedinmaintenance, or have a normal life shorter than the Defects Liability Period statedherein;

- anydesign,Specificationorotherdata,suppliedorspecifiedbyoronbehalfofthe

Employer or any matter for which the Contractor has disclaimed responsibility herein;

  - The Employer shall offer the Contractor all reasonable opportunity to inspect the defect(s)Noticed,aswellasprovideallnecessaryaccesstotheFacilitiesandtheSitetoenable him to perform his obligations under this Clause31.

The Contractor may remove from the Site any Plant and Equipment or any part of the Facilities that are defective, if the nature of the defect, and/or any damage to the Facilities caused by the defect, is such that repairs cannot be expeditiously carried out at the Site.

## Uncorrected Defects

- If the Contractor fails to correct a Defect, to the satisfaction of the Engineer, within the time specified in the Engineer’s notice, the Engineer will assess the cost of having the Defect corrected. The Contractor will pay to the Employer this amount or the Engineer may deduct such amount from any sums due to the Contractor, on correction of the Defect together with 20 percent additional cost as the damages.

- In case of any non-compliance/ delayed compliance of maintenance standards, the damages / reduction in payment shall be applicable as provided under road maintenance Standards Part-I.

## COSTCONTROL

- Bill of Quantities

  - The Bill of Quantities shall contain the description of items, units, rates andamount.

  - TheBillofQuantitiesisusedtocalculatetheContractPrice.TheContractorispaidfor the quantity of the work done at the rates given in the Bill of Quantities with accepted/awarded tender premium for each item for the workexecuted.

Theaccepted/awardedtenderpremiumabove/belowthegrandtotalofProjectcostasperBOQ shallbeapplicableforindividualitemofworktodeterminepayableamounttoContractorsubject to contractualprovisions.

## Changes in theQuantities

34.1       The final quantity of the work done may differ from the quantity given in the Bill of Quantities. The payment shall be made for the quantities executed. Provided that the items for which lump sum rates have been quoted shall not be measured and the payments for such items not exceeding the quoted lump sum amount shall be made to the Contractor subject to meeting the specified maintenance requirements by the Contractor in accordance with the Agreement. It is agreed, beyond doubt, by the Contractor that no claims shall be entertained by the Engineer/ Employer on account of reduction to any extent, due to budgetary constraints, in quantities of measurable items.

## Variations

  - The Engineer may order Variations, with the prior approval of the Employer, he considers necessary or advisable during the progress of the Works. Such Variations shall form partoftheContractandtheContractorshallexecutethevariedworks.OralordersoftheEngineer for Variations, unless followed by written confirmation, shall not be taken intoaccount.

## Payments for Variations

  - IfratesforVariationitemsarespecifiedintheBillofQuantities,theContractorshall

carry out such work at the same rate.

  - IftheratesforVariationarenotspecifiedintheBillofQuantities,theEngineershall

derive the rate from similar items in the Bill of Quantities.

  - If the rate for Variation item cannot be determined in the manner specified inClause 36.1 or 36.2, the Contractor shall, within 14 days of the issue of order of Variation work, inform the Engineer the rate which he proposes to claim, supported by analysis of the rates. The Engineer shall assess the quotation and determine the rate based on prevailing market rates within one month of the submission of the claim by the Contractor and approval from the Employer shall be taken. As far as possible, the rate analysis shall be based on the Standard Data Book and the current Schedule of Rates of the district public works division. The decision of the Employer on the rate so determined shall be final and binding on theContractor.

## Cash FlowForecasts

  - When the Programme is updated, the Contractor shall provide the Engineer withan

updated cash flow forecast.

## PaymentCertificates

  - TheContractorshallsubmittotheEngineermonthlystatementsofthevalueofthework executedlessthecumulativeamountcertifiedpreviously,supportedwithdetailedmeasurement of the items of workexecuted.

  - The Engineer shall check the Contractor’s monthly statement within 14 days and certifytheamounttobepaidtotheContractoraftertakingintoaccountanycreditordebitforthe month inquestion.

  - The value of BOQ based itemswork executed shall be determined, based on measurements by the Engineer. In case of lump sum based items (performance based items), the work executed shall be certified by the Engineer while proposing payment for the same.

  - The value of work executed shall comprise the value of the quantities of the items in the Bill of Quantitiescompleted along with amount due to the Contractor as per the Agreement with respect to performance-based items executed as per satisfaction of the Engineer.

  - The value of work executed shall also include the valuation of Variations and CompensationEvents.

  - The Engineer/Employer may exclude any item certified in a previous certificate      or reduce the proportion of any item previously certified in any certificate in the light of latest information.

  - ThefinalbillshallbesubmittedbytheContractorwithinonemonthoftheactualdate of completion of the work; otherwise the Engineer’s certificate of the measurement and of the totalamountpayableforworkaccordinglyshallbefinalandpaymentmadeaccordinglywithina period of sixty days as far aspossible.

## Payments

  - (a) Quantity Based items as per Bill No. 1 and 2:-

The basis of payment will be actual quantities of items of work carried out and valued at the rates tendered in the BOQ along with accepted/awarded tender premium/ discount. The accepted/awarded tender premium / discount w.r.t. the grand total of the project cost shall be applicable for the individual items of work to determine payable amount to Contractor for work done subject to other contractual provisions. Any variation shall be dealt with as per contract provisions.

(b)	Performance Based Items as per Bill No.3:-

Payment for performance based activities shall be indexed on performance scale of 100 marks as given in Table below:

| Sl No | Brief Description | Weightage for performance rating | Remarks |
| --- | --- | --- | --- |
| 1 | Performance based maintenance and pavement repairs (100%) | Pot/patch repair - 50% | Length in which road is maintained without pot/patch rectifying the pot\patch within stipulated time during the month under consideration/Total length |
|  |  | Maintenance of embankment slopes/ shoulders, ensuring camber to shoulder-20% | Length in which road Shoulders/slopes maintained rectifying the shoulders/slopes within stipulated time during the month under consideration/Total length |
|  |  | Removal of rank vegetation/plants/trees branches protruding on to carriageway of obstructing sight distance-15% | Length in which road maintain removing the rank vegetation within stipulated time during the month under consideration/Total length |
|  |  | Removal of stray and dead animals (Item no. 3.5) – 15% | Length in which road maintain removing the stray and dead animals within stipulated time during the month under consideration/Total length |

Note:- Performance assessment for performance based items of work, shall be done through inspection by the Engineer-in-Charge at least two times during the month and overall rating can be done on the basis of average of assessments made during the inspection along with photographic/ videographic evidence. Theperformance based items in Bill No. 3 corresponding to pavement repair including potholes/ patch/ rut etc., shall have to be completed within 1 month from the commencement of the work, subsequent to which if any defects found, the payment shall be subject to deductions as per the provisions of the Contract.

- The Contractor shall submit photos / videos recording to the Engineer-in-Charge of condition of the Project Highway with special emphasis on performance-based items.

- For performance-based items of work, the Contractor shall be entitled for receiving payment proportionate to the average percentage of performance assessed for achievement between 80% to 100%.

- The Contractor shall not be entitled for payment for performance based maintenance if the average performance is rated less than 80%

- A percentage quoted by bidder shall be entered as a single percentage as Tender Premium % above/ tender discount % below on the estimated rates/amounts specified in the BOQ.

- When the unattended defects are corrected within a week of their communication to the contractor at the cost of the contractor and the amount along with specified damages of 20% are recovered from the contractor those defects would be considered as rectified while assessing the performance achievement.

- Road signs proposed to be installed under Quantity based maintenance in the stretch shall also come under performance-based maintenance obligation after they are installed.

- Repeated failure in rectifying the defects / deficiencies even after intimating them to the contractor may lead to termination of contract for contractor default apart from reduction in relevant payments.

- Performance based maintenance can be reduced either in terms of length or in terms of months or both for taking up any development works or other exigencies as decided by the authority and in such cases the payments would be regulated on pro- rata basis in terms of length / period in months or both. Any claims of the Contractor in this regard shall not be entertained.

NOTE: The  Performance based payments percentages are  assessed for the 12 months of work period. In case of any fore-closure of the work inview of declaration of Appointed Date for the Improvement works on the subject reach, the payments shall be reduced proportionately w.r.t the decrease in the Work period.

  - Payments shall be adjusted for deductions for advance payments, security deposit, other recoveries in terms of the Contract and taxes at source, as applicable under the law. The EmployershallpaytheContractortheamountstheEngineerhadcertified,within28daysofthe date of eachcertificate.

  - TheauthorizedrepresentativeoftheEmployershallmakethepaymentcertifiedby

the Engineer.

  - ItemsoftheWorksforwhichnorateorpricehasbeenenteredintheBillofQuantities, willnotbepaidforbytheEmployerandshallbedeemedtobecoveredbyotherratesandprices in theContract.

## CompensationEvents

  - ThefollowingshallbeCompensationEventsunlesstheyarecausedbytheContractor:

- The Engineer orders a delay or delays exceeding a total of 30days;

- The effects on the Contractor of any of the Employer’sRisks.

  - If a Compensation Event would prevent the Works being completed before the Intended Completion Date, the Intended Completion Date shall be extended. The Engineer shall decide whether and by how much the Intended Completion Date shall be extended after approval of theEmployer.

  - TheContractorshallnotbeentitledtocompensationtotheextentthattheEmployer’s interests are adversely affected by the Contractor not having given early warning or not having cooperated with theEngineer/Employer.

The Contractor will not be entitled to compensation in case the fore-closure of contract inview of declaration of appointed date for the improvement works on the subject reachand the payments shall be reduced proportionately w.r.t the decrease in the Work period.

## Taxes and Currencies forPayments

  - The rates quoted by the Contractor shall be deemed to be inclusive of the GST and otherlevies,duties,royalties,cess,toll,andothertaxesofCentralandStateGovernments,local bodies and authorities that the Contractor will have to pay for the performance of this Contract. TheEmployerwillperformsuchdutiesinregardtothedeductionofsuchtaxesatsourceasper applicablelaw.

  - All payments shall be made in IndianRupees.

## Security Deposit/RetentionMoney

  - TheEmployershallretainsecuritydepositoffivepercentoftheamountfromeachpayment due to the Contractor until Completion of the whole of the Works.

  - The security deposit/retention money and the performance security will be released to the Contractor when the Defects Liability Period if any is over, and the Engineer has certified that the Defects, if any, notified by the Engineer to the Contractor before the end of this period have beencorrected.Also, the additional performance security will be released after the Project Completion.

  - If the Contractor so desires, then the Security Deposit/retention money can be released on submission of unconditional Bank Guarantee at the following twostages:-

- At a point after the progress of work in financial terms (gross value of work done)has

reached 50% of the contract amount

- After the retention money has been deducted to the full value (5% of the contract amount).

## LiquidatedDamages

  - TheContractorshallpayliquidateddamagestotheEmployerattheratestated in the Contract Data for each day orpartthereof that the Completion Date is later than the Intended Completion Date. The total amount of liquidated damages shall not exceed the amount defined in the Contract Data. The Employer may deduct liquidated damages from payments due to the Contractor. Payment of liquidated damages shall not affect the Contractor’s otherliabilities.

Both the parties expressly agree that the liquidated damages payable by the Contractor are mutuallyagreedgenuinepre-estimatedlossandwithoutrequirement of anypoofofactualdamageslikelytobe sufferedandincurredbytheEmployerandtheEmployerisentitledtoreceivethesameandare not by way ofpenalty.

  - If the Intended Completion Date is extended after liquidated damages have been paid, the Engineer shall correct any overpayment of liquidated damages by the Contractor by adjusting in the next payment certificate. The contractor shall not be paid interest on the over payment of liquidateddamages.

## AdvancePayment-

  - The Employer will make an interestbearing advance payment to the Contractor up to 10% of Contract Price againstprovisionbytheContractorofanUnconditionalBankGuaranteeinaformandbyabank acceptable to the Employer in amounts equal to 110% of the advance payment. The guarantee shall remain effective until the advance payment has been repaid, butthe amountoftheguaranteeshallbeprogressivelyreducedbytheamountsrepaidbytheContractor. The Contractor shall take the above advance before 2nd running bill and if the contractor delays seeking the advance, the same is notpayable.

  - TheContractoristousetheadvancepaymentonlytopayforEquipment,plantand

Mobilization expenses required specifically for execution of the Works. The Contractor shalldemonstratethattheadvancepaymenthasbeenusedinthiswaybysupplyingcopiesofinvoices or other documents to theEngineer.

  - Theadvancepaymentshallberepaidwithinterest@SBIPLRapplicableonthedate ofreleaseofmobilizationadvance,bydeductingfrompaymentsotherwiseduetotheContractor. Themobilizationadvancewillberecoveredfrom3rdrunningbillupto8thrunningbillinsixequal instalmentsandtheinterestwillberecoveredfrom9th running bill.Inanycase,themobilizationadvance with interest must be recovered within ten months from the date of agreement. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, Variations, Compensation Events, or LiquidatedDamages.

## Performance Security

  - Subject to further condition in Contract Data, the Performance Security equal to 3percent of the Contract Price shall be provided to the Employer no later than the date specified in the Letter of Acceptance and shall be issued in the form given in the Contract Data and by a prescribedbank.The Performance Security shall be valid until 60 (sixty) days after the Defects Liability Period. The Additional Performance Security shall be valid until 28 (twentyeight) days after Project Completion Date.Thevalidityshallaccountforadditional3months’ timetoaccountforBG verification, signing of contract and startdate

## Cost ofRepairs

  - Loss or damage to the Works or Materials to be incorporated in the Works between the Start Date and the end of the Defects Liability Period shall be remedied/rectified by the Contractor at his cost if the loss or damage arises from the Contractor’s acts oromissions.

## FINISHING THECONTRACT

- Completion

  - The Contractor shall request the Engineer to issue a certificate of Completion ofthe

Works, and the Engineer will do so upon deciding that the Works are completed.

## TakingOver

  - TheEmployershalltakeovertheSiteandtheWorkswithinsevendaysofthe

Engineer’s issuing a certificate of Completion.

## FinalAccount

  - TheContractorshallsupplytotheEngineerwithadetailedaccountofthetotalamount that the Contractor considers payable under the Contract before the end of the Defects Liability Period.TheEngineershallissueaDefectsLiabilityCertificateandcertifyanyfinalpaymentthat is due to the Contractor within 28 days of receiving the Contractor’s account if it is correct and complete.Ifitisnot,theEngineershallissuewithin28daysaschedulethatstatesthescopeof the corrections or additions that are necessary. If the Final Account is still unsatisfactory after it has been resubmitted, the Engineer shall decide on the amount payable to the Contractor and issue a payment certificate within 28 days of receiving the Contractor’s revisedaccount.

## Operation and MaintenanceManual

  - If“asbuilt”Drawingsand/oroperationandmaintenancemanualsarerequiredrelating toconstructionworkcarriedout,theContractorshallsupplythemwithin28daysfromthedateof issue of certificate ofcompletion.

  - IftheContractordoesnotsupplytheDrawingsand/ormanualsbythestipulateddate or they do not receive the Engineer approval, the Engineer shall withhold the amount equal to Rs. 5 lakh from payments due to theContractor.

## Termination

  - The Employer or the Contractor may terminate the Contract if the other partycauses a fundamental breach of theContract.

  - Fundamental breaches of Contract include, but shall not be limited to, thefollowing:

- Fundamental Breaches by theContractor

  - the Contractor stops work or grossly neglects Routine Maintenance Works  and Services for 28 days when no stoppage of work is shown on the current programme and the stoppage has not been authorized by theEngineer;

  - the Contractor is declared as bankrupt or goes into liquidation other than for approved reconstruction oramalgamation;

  - the Engineer/Employer gives Notice that failure to correct a particular Defect is a fundamental breach of Contract and the Contractor fails to remedy the defect and correct it within the period of time determined by theEngineer;

  - the Contractor does not maintain a Security Deposit as perclause;

  - the Contractor has delayed the completion of Works by the number of days for which the maximum amount of liquidated damages can be paid, as defined in Clause43;

  - the aggregate liability of the Contractor to the Employer, exceeds the total amount specified in the Contract Data, provided that this limitation shall not apply to the cost of repairing or replacing defective works andequipment;

  - the Contractor fails to provide insurance cover as required under Clause13;

  - if the Contractor, in the judgement of the Employer, has engaged in the corrupt or fraudulent practices as defined in Clause 34 of the Instructions to Bidders in competing for or in executing theContract;

  - if the Contractor fails to set up a field laboratory with the prescribed equipment, within the period specified in the ContractData;

  - if the Contractor does not deploy any of the personnel stated in Contract Data within 45 days of issue of notice toproceed or does not replace the personnel with a personnel with equivalent qualifications/experience  ;

  - TheContractorviolatestheprovisionsofChildLabour(Prohibition&Regulation) Act,1986;

  - Any other fundamental breaches as specified in the contractdata.

  - WithoutprejudicetoanyotherrightorremedieswhichtheEmployermayhaveunder this contract upon occurrence of a Contractor’s fundamental breach of contract, the Employer shall be entitled to terminate this contract by issuing a Termination Notice to the Contractor provided that before issuing the Termination Notice, the Employer shall by a Notice inform the Contractor of its intention to issue such Termination Notice and grant 15 days to the Contractor tomakearepresentationandmayaftertheexpiryofsuch15days,whetherornotitisinreceipt of such representation issue the TerminationNotice.

  - Notwithstandingtheabove,theEmployermayterminatetheContractforconvenience.

  - If the Contract is terminated, the Contractor shall stop work immediately, make the Site safe and secure, and leave the Site as soon as reasonablypossible.

## Payment upon Termination

  - If the Contract is terminated because of a fundamental breach of Contract by the Contractor, the Engineer shall issue a certificate for the value of work done and Materials ordered less advance payments received up to the date of issue of the certificate and less the percentagetoapplytothevalueoftheworknotcompleted,asindicatedintheContractData.If thetotalamountduetotheEmployerexceedsanypaymentduetotheContractor,thedifference shallbeadebtpayabletotheEmployerandEmployermayrecoverthesamefromPerformance Bank Guarantee.

  - If the Contract is terminated at the Employer’s convenience, the Engineer shallissue a certificate for the value of work done, and a pre-determined amount specified in the contract data to cover the reasonable cost of removal of Equipment and repatriation of the Contractor’s personnel employed solely on the Works, and the Contractor’s costs of protecting and securing the Works and less advance payments received up to the date of the certificate, less other recoveries due in terms of the Contract, and less taxes due to be deducted at source as per applicablelaw.

## Property

  - All Materials on Site, Plant, Equipment, Temporary Works and Works shall be deemed to be the property of the Employer for use for completing balance work if the Contract is terminated because of the Contractor’sdefault.

## Release fromPerformance

  - If the Contract is frustrated by the outbreak of war or by any other event entirely outsidethecontroloftheEmployerortheContractor,theEngineershallcertifythattheContract hasbeenfrustrated.TheContractorshallmaketheSitesafeandstopworkasquicklyaspossible afterreceivingthiscertificateandshallbepaidforallworkcarriedoutbeforereceivingitandfor any work carried out afterwards to which a commitment wasmade.

## OTHER CONDITIONS OFCONTRACT

- Labour

  - The Contractor shall, unless otherwise provided in the Contract, make his own arrangements for the engagement of all staff and labour, local or other, and for their payment, housing, feeding and transport; and for compliance of various labourlaws/regulations.

  - The Contractor shall, if required by the Engineer, deliver to the Engineer a return in detail, in such form and at such intervals as the Engineer may prescribe, showing the staff and the numbers of the several classes of labour from time to time employed by the Contractor on Site and such other information as the Engineer mayrequire.

  - The Contractor’s personnel including equipment operators shall be appropriately qualified, skilled and experienced in their respective trades or occupations. The Engineer may require the Contractor to remove or cause to be removed any person employed on the site or the works, including the Contractor’s representative, if applicable,who

- Persists in any misconduct or lack ofcare;

- Carries out duties incompetently ornegligently;

- Falls to conform with any provision of thecontract;

- Persists in any conduct which is prejudicial to safety, health or protection of the environment.

If appropriate, the contractor shall then appoint or cause to be appointed a suitable replacement person

## Compliance with LaborRegulations

  - During continuance of the Contract, the Contractor and his sub-Contractors shall abide at all times by all existing labor enactments and rules made thereunder, regulations, notifications and bye laws of the State or Central Government or local authority and any other labourlaw(includingrules),regulations,byelawsthatmaybepassedornotificationthatmaybe issuedunderanylabourlawinfutureeitherbytheStateortheCentralGovernmentorthelocal authority. (Salient features of some of the major labour laws that are applicable to construction industry are given in Addendum to General Conditions of Contract.) The Contractor shall keep the Employer indemnified in case any action is taken against the Employer by the competent authorityonaccountofcontraventionofanyoftheprovisionsofanyActorrulesmadethereunder, regulationsornotificationsincludingamendments.IftheEmployeriscausedtopayorreimburse, suchamountsasmaybenecessarytocauseorobserve,orfornon-observanceoftheprovisions stipulated in the notifications/bye taws/Acts/Rules/regulations including amendments, if any, on the part of the Contractor, the Employer shall have the right to deduct any money due to the Contractor including his amount of performance security. The Employer shall also have right to recover from the Contractor any sum required or estimated to be required for making good the loss or damage suffered by theEmployer.

In no case shall the employees of the Contractor and the Sub-Contractor be treated as the employees of the Employer at any point of time.

## Drawings and Photographs of theWorks

  - The Contractor shall do photography/video photography of the site firstly before the start of work, secondly mid-way in the execution of different stages of work and lastly after the completion of each item of work. No separate payment will be made to the contractor forthis.

  - The Contractor shall not disclose details of Drawings furnished to him and works on which he is engaged without the prior approval of the Engineer in writing. No photograph of the works or any part thereof or plant employed thereon, except those permitted under Clause 57.1, shall be taken or permitted by the Contractor to be taken by any of his employees or   any employees of his sub-Contractors without the prior approval of the Engineer in writing. No photographs/video photography shall be published or otherwise circulated without the approval of the Engineer inwriting.

## The Apprentices Act,1961

  - The Contractor shall duly comply with the provisions of the Apprentices Act, 1961 (Ill of1961),therulesmadethereunderandtheordersthatmaybeissuedfromtimetotimeunder the said Act and the said Rules and on his failure or neglect to do so, he shall be subject to all liabilities and penalties provided by the said Act and saidRules.

## CONTRACT DATA

Items marked “N/A” do not apply in this Contract.

1.1

- TheEmployeris

SuperintendingEngineer, P.W.D., N.H. Circle Bilaspur	[Cl.1.1 ofITB]

- The Engineer is:	[Clause 1.1 ofGCC]

Designation:Executive Engineer NH Division Bilaspur

Address:  In front of District Court Bilaspur (C.G.),	[Cl.1.1]

- TheIntendedCompletionDatefor:

i.ThewholeoftheWorksis[12monthsfromCommencement Date]	[Cl.1.1, 17&26 ofGCC]

- The Site is located at [Short term maintenance of Takhatpur Ex. Road from Km. 26.542 to Km. 32.093, Mungeli Ex. Road from Km. 45.786 to Km. 56.275, Pandariya Ex. Road from Km. 82.582 to Km. 87.133 and Pondi Ex. Road from Km. 103.166 to Km. 104.756 = 22.181 Km. on N.H.-130A in the  state of Chhattisgarh]	[Sr no 1 ofNIT]

- The	Start	Date	shall	be	within	15	days	after	the	date	ofissue of the Noticetoproceed						[Cl.1.1 of GCC]

- (a) The name and identification number of the Contractis

The Worksconsistof Short term maintenance of Takhatpur Ex. Road from Km. 26.542 to Km. 32.093, Mungeli Ex. Road from Km. 45.786 to Km. 56.275, Pandariya Ex. Road from Km. 82.582 to Km. 87.133 and Pondi Ex. Road from Km. 103.166 to Km. 104.756 = 22.181 Km. on N.H.-130A in the  state of Chhattisgarh								[Cl. 1.1 ofITB]

- (a)ThelawwhichappliestotheContractisthelawofUnionofIndia.[CI.3.1ofGCC]

(b)The language of the Contract documentsisEnglish	[Cl.3.1 of GCC]

- The limit of subcontracting is NIL of initial contract price	[CI.7.1 of GCC]

- Schedule of otherContractor-NIL	[Cl.8.1 of GCC]

- The TechnicalPersonnel are	[Cl. 9.1 ofGCC]

| S. No. | Personnel | Qualification | Particular Experience (minimum requirement) | No. of Persons |
| --- | --- | --- | --- | --- |
| 1. | Project Manager | Graduate in CivilEngineering | 5 years as Project Manager on Highway, Bridge construction/ Maintenance works | 1 |
| 2. | Site Engineer-cum- Surveyor Engineer- cum- Material Engineer | Graduate in CivilEngineering | 4 years on Highway Construction/ Maintenance works | 1 |
| 3 | Road Safety Auditor | RoadSafety Audit Certificatefrom appropriate approved Govt.agency | 5 years experience |  |
|  |  | Graduate in CivilEngineering |  |  |
|  |  | Graduate in CivilEngineering |  | 3 days in every 3 months |

Roles and Responsibilities of Road Safety Auditor

Road Safety Auditor has to inspect the stretches entrusted for maintenance and identify any unsafe conditions giving their location details with chainages etc., and suggest temporary measures for immediate rectification.

He has to indicate whether the suggested immediate rectifications are covered in the BOQ item or are to be approved as variation. If so, the variation requirements are to be furnished to the Engineer in charge.

The Road Safety Auditor has to indicate the maintenance work in progress during his inspection in his inspection report and indicate whether appropriate traffic management measures including barricading, signs, markings, lanterns, reflectors etc., are in place as per the relevant IRC codes and good industry practice or not. The locations and type of maintenance work in progress and the traffic management measures adopted are to be furnished to the Engineer in charge with video graph and / or photographs in support thereof.

- Amount forinsuranceare:	[Cl.13.1 of GCC]

  - Rupees equivalent to ContractPrice.

  - Rupees equivalent to 5% of ContractPrice.

  - Rupees equivalent to 5% of ContractPrice

  - Rupees 20 lakhs for multipleincidents.

The said insurance shall include all liabilities as per Clause 13.1 and shall be deductible as per premium rate.

- Site Investigation Report-NIL	[Cl 14.1 ofGCC]

- The period for submission of the programme for approval of Engineer shall be 30 days from the issue of LetterofCommencement.	[{Cl.25.1 of GCC]

- Amount to be withheld for delays in submission of updated programme: 1% of value of work corresponding to theupdatedprogramme.	[Cl. 25.4 ofGCC].

- Theperiodforsettingupafieldlaboratorywiththeprescribedequipment

relevant to items of work in BOQ is 30 days from the date of notice to start work

## [Cl. 30.1 of GCC].

- TheDefectLiabilityPeriodwillbe36 m o n t h s  f o r periodic renewal and other improvement worksexecuted (if any)	[Cl. 31 ofGCC]

| a. Amount of liquidated damages for delay in completion of works | 0.1 percent of the remaining value of contract to be executed, rounded off to the nearest thousand, per day with the minimum of Rs. 10000/- per day |
| --- | --- |
| b. Maximum limit of liquidated damages for delay in completion of work. | 10 per cent of the Initial Contract Price rounded off to the nearest thousand [Clause.43 of GCC] |

- ThestandardformofPerformanceSecurityacceptabletotheEmployershallbean

unconditional Bank Guarantee of the type as specified in the Bidding Documents.

## [Cl. 45.1 of GCC]

- ThepercentagetoapplytothevalueofworknotcompletedrepresentingtheEmployer’s additionalcostforcompletingtheworkshallbe20percent.ThePerformanceSecurity shall also be forfeited if the Contract is terminated because of a fundamental breach of Contract bythe Contractor.	[Cl.52.1 of GCC]

- The reasonable cost of removal of equipment and repatriation of the Contractor’s personnel employed solely on the works in the event of termination of the contractat the Employer’s convenience or because of a fundamental breach of contract by the Employer is to be treated as 3 lakh.	[Cl. 52.2 ofGCC]

# SECTION 6

ADDENDUM TO GENERAL CONDITIONS OF CONTRACT

## SECTION 6

ADDENDUM TO GENERAL CONDITIONS OF CONTRACT

SALIENTFEATURESOFSOMEMAJORLABOURLAWS APPLICABLETOESTABLISHMENTS ENGAGED IN BUILDING AND OTHER CONSTRUCTIONWORKS.

- Workmen Compensation Act, 1923: The Act provides for compensation in case of injury by accident arising out of and during the course ofemployment.

- Payment of Gratuity Act; 1972: Gratuity is payable to an employee under the Act on satisfaction of certain conditions if an employee has completed the prescribed minimum years (five years) of service or more or on death the rate of prescribed minimum days’ (15 days) wages for every completed year of service. The Act is applicable to all establishments employing the prescribed minimum number (10) or moreemployees.

- Employee’s P.F. and Miscellaneous Provision Act 1952: The Act provides for monthlycontributionsbytheEmployerplusworkersattheprescribedrate(10percent or 8.33 percent). The benefits payable under the Actare:

  - Pension or family pension on retirement or death as the case maybe.

  - Deposit linked insurance on the death in harness of theworker.

  - Payment of P.F. accumulation on retirement/deathetc.

- Maternity Benefit Act, 1961: The Act provides for leave and some other benefits to women employees in case of confinement or miscarriageetc.

- Contract Labour (Regulation & Abolition) Act, 1970: The Act provides for certain welfare measures to be provided by the Contractor to contract labour and in case theContractorfailstoprovide,thesamearerequiredtobeprovided,bythePrincipal EmployerbyLaw.TheprincipalEmployerisrequiredtotakeCertificateofRegistration and the Contractor is required to take license from the designated Officer. The Act is applicable to the establishments or Contractor of Principal Employer if they employ minimum prescribed (20 or more) numbers of contractlabour.

- Minimum Wages Act, 1948: The Employer is to pay not less than the Minimum WagesfixedbyappropriateGovernmentasperprovisionsoftheActiftheemployment isascheduledemployment.Constructionofbuildings,roads,runwaysarescheduled employment.

- Payment of Wages Act, 1936: It lays down as to by what date the wages are to   be paid, when it will be paid and what deductions can be made from the wages of workers.

- Equal Remuneration Act, 1979: The Act provides for payment of equal wages for work of equal nature to male and female workers and for not making discrimination against female employees in the matters of transfers, training and promotionsetc.

- PaymentofbonusAct,1965:TheActisapplicabletoallestablishmentsemploying minimum prescribed (say, 20 or more) number of workmen. The Act provides for payments of annual bonus within the prescribed range of percentage of wages       toemployeesdrawinguptotheprescribedamountofwages,calculatedintheprescribedmanner.TheActdoesnotapplytocertainestablishments.Thenewlyset- up establishments are exempted for five years in certain circumstances. States may have different number of employmentsize.

- Industrial Disputes Act, 1947: The Act lays down the machinery and procedure for resolutionofindustrialdisputes,inwhatsituationsastrikeorlock-outbecomesillegal and what are the requirements for laying off or retrenching the employees or closing down theestablishment.

- Industrial Employment (Standing Orders) Act, 1946: It is applicable to all establishments employing minimum prescribed number of persons (say, 100, or 50). The Act provides for laying down rules governing the conditions of employment by theEmployeronmattersprovidedintheActandgetthesecertifiedbythedesignated Authority.

- Trade unions Act, 1926: The Act lays down the procedure for registration of trade unionsofworkmenandemployees.TheTradeUnionsregisteredundertheActhave been given certain immunities from civil and criminalliabilities.

- ChildLabour(Prohibition&Regulation)Act,1986:TheActprohibitsemployment ofchildrenbelow14yearsofageincertainoccupationsandprocessesandprovides for regulations of employment of children in all other occupations and processes. Employment of child labour is prohibited in building and constructionindustry.

- Inter-State Migrant  Workmen’s  (Regulation  of  Employment  &  Conditions  of Service) Act, 1979: The Act is applicable to an establishment which employs minimumprescribednumberoflabour(say,fiveormore)inter-statemigrantworkmen through an intermediary (who has recruited workmen in one state for employment  in an establishment situated in another state). The Inter-State migrant workmen, in an establishment to which this Act becomes applicable, are required to be provided certain facilities such as Housing, Medical-Aid, Travelling expenses from home upto the establishment and backetc.

- The building and Other Construction Workers (Regulation of Employment and ConditionsofService)Act,1996andtheCessActof1996:Alltheestablishments who carry on any building or other construction work and employ the minimum prescribed (say, 10 or more) number of workers are covered under this Act. All such establishmentsarerequiredtopaycessattheratenotexceeding2percentofthecost ofconstructionasmaybenotifiedbytheGovernment.Aspercurrentnotification,one percent of the cost of construction is payable by the Employer of the establishment. The Employer of the establishment is required to provide safety measures at the buildingorconstructionworkandotherwelfaremeasures,suchascanteens,first-aid facilities, ambulance, housing accommodations for workers near to the work place etc.TheEmployertowhomtheActapplieshastoobtainaregistrationcertificatefrom the Registering Officer appointed by theGovernment.

- Factories Act, 1948: The Act lays down the procedure for approval of plans before setting up a factory, health and safety provisions, welfare provisions, working hours, annual earned leave and rendering information regarding accidents or dangerous occurrences to designated authorities. It is applicable to premises employing the minimum prescribed number of persons (say, 10 persons or more) with aid of power oranotherminimumprescribednumberofpersons(say,20ormorepersons)without the aid of power engaged in manufacturingprocess.

# SECTION -7

ROAD MAINTENANCE STANDARDS AND SPECIFICATIONS FOR ROAD MAINTENANCE WORKS, PART-I AND PART-II

## SECTION-7

ROAD MAINTENANCE STANDARDS AND SPECIFICATIONS FOR ROAD MAINTENANCE WORKS, PART-I AND PART-II

PREAMBLE

The Road Maintenance Standards and Specifications shall be read in conjunction with all other documents constituting the Contract viz. Notice Inviting Tender, Instructions to Bidders; Conditions of Contract, Bill of Quantities and other related documents mentioned in the Bid Documents.

## General

The Standards and Specifications for the Road Maintenance Works and Activities as described

hereinafter shall comprise of the following:

PART-I	:	Road MaintenanceStandards

PART-II	:	Specifications for Road MaintenanceWorks

Carbonfootprintsshallbe minimizedduringtheexecutionofproject. If approved by the Employer, the environment friendly machinery like Infrared Recycling Road Maintenance as approved by CRRI/ IRC/ MoRTH shall be got deployed.

## PART-I

ROAD MAINTENANCE STANDARDS

- Inspections

  - The Contractor shall carry out weekly Inspection of project road and submit report to theEngineeronthemaintenanceworkscarriedoutduringtheweekandalsoidentifyotheritems of works with location requiring attention formaintenance.

  - Any maintenance which involves works of emergent nature and/or replacementshall beimmediatelyreportedtotheEngineerforjointassessmentandissueoftheworkorder.Such repairs shall be carried out on authorization by the Engineer except in emergency situations where it needs to be attended to urgently for safety reasons. In such situations, temporary arrangements shall be made immediately and further directions sought from theEngineer.

  - The Engineer or his authorized representativeswill monitor road condition and shall carry out at least fortnightly InspectionoftheprojectroadtoverifythattheContractorismaintainingmaintenancestandards asperContractandtomakenoteofnon-compliancesofPerformancebaseditemsofBOQ,other items of work and work orders issued for other works. Non-compliance/delayed compliance of maintenance work shall be dealt with as per provisions of GCC Clause 32.1 and maintenance standardsherein below.

## 2Maintenance Standards for performance based items

2.1 The following maintenance standards shall be achieved by the Contractor to be eligible for fullpayment:

| Item | Permissible Tolerance/Service Level | Measurement and Detection | Maximum Response Time | Rectification Standard |
| --- | --- | --- | --- | --- |
| Item no. 3.1 of Bill no 3 (repair of pot holes/edge cuts/ruts/ patches), | Not more than 5 isolated potholes/ edge cuts in a stretch of 1 km. Maximum size of pot hole/edge cut not more than 300 sq cm x 4 cm depth. | Visual inspection. Area of pot hole/ patches shall be measured by the area of rectangle enclosing the pothole. | Within two days | As per Clause 3004 of MoRTH Specifications |
|  | Max rutting – 2.5% in the sub-section. Rutting not to exceed 20 mm. | Rutting to be measured in isolated locations. |  |  |
|  | Patches not more than 5% of the surface area in a stretch of 1 km. |  |  |  |
| Item no. 3.2 of Bill no 3 (Maintenance of concrete pavement) | Not more than 3 isolated concrete panels having multiple cracks or differential settlement in a stretch of 1 km. | Visual inspection. | Within 15 days | As per Clause no. 3005 of TechnicalSpecifications |
| Item no. 3.3 of Bill no 3 (Maintenance of embankment slopes/shoulders) | Not more than 5 stretches greater than 5m each having gully erosion in embankment / cuts and edge drop in shouldersadjacent to paved area. | Visual inspection | Within 2 days | As per Clause No. clause 408 of TechnicalSpecifications |
| Item no. 3.4 of Bill no 3 (Removal of rank vegetation) | Not more than 5 stretches of 10m each rank vegetation. | Visual inspection | Within 2 days |  |
| Item no. 3.5 of Bill no 3 Removal of animals | To reach the spot where stray animal is detected / informed (to Contractor’s representatives) to be occupying the main carriageway within 30 minutes. | Necessary arrangement to be made by Contractor for regular patrolling w.r.t. removal of animals at least once in four hours for entire length ofthe highway. | Removal of dead animals/ birds and burying them at suitable location within two hours. Removal of stray animals to suitable place out of carriageway | As per directions of Hon’ble High Court, Bilaspur, Chhattisgarh and Chief Secretary, Government of Chhattisgarh |

2.2 	Deleted.

## 3Maintenance Standards for Other BOQ Items

## 3.1 Maintenance standards for cleaning, clearing and repairing roadside open/ unlined/ lined/ covered drains and  cross drainage works

## i) The work shall consist of cleaning, clearing, deepening and reshaping of roadside drains and making shallow lateral drains on shoulders to drain out the rain water/ surface water effectively from bituminous surface as well as from roadside berms.

## ii) Disposal of sediments, extraneous debris or vegetation growth, blocking flow.

## iii) Safety devices and signs shall be placed as per MoRTH Specifications for Road and Bridge Works (5th Revision) Clause No. 112.

## iv) The excavated material shall be disposed off as directed by Engineer-in-charge with all leads and lifts

## v) The drain slopes and sides shall be dressed up to original flow line and cross section.

3.2	Maintenance standards for routine maintenance of road signs and delineators

## i) The work shall consist of washing of signs, delineators, removal of posters etc. and repair to supporting structures with repainting.

## ii) The road signs and delineators should be thoroughly washed using a detergent solution followed by a lean rinse and whole face of the sign shall be dried.

## iii) Defects in supporting structures like bullet holes, surface marks or bent posts shall be repaired with appropriate tools.

## iv) Damaged area shall be cleaned and loose/flaking paint shall be removed. Bullet holes shall be filled with filler and supporting structures shall be painted with first quality enamel paint in two or more coats.

3.3 Maintenance Standards for repairing of earthen shoulders:-

i) The earthen shoulders shall be filled with subgrade quality earth and or cut suitably if the shoulders are raised above pavement level with camberof minimum 3% away from the carriageway to ensure adequate drainage.

ii) The level difference between carriageway and the earthen shoulder shall be removed through 1V 4H wedge or any other suitable method with proper watering/compaction at OMC.

## PART-II

SPECIFICATIONS FOR ROAD MAINTENANCE WORKS

- General

  - All materials, works and construction operations shall conform to the requirements laid down in the “Specifications for Road and Bridge Works” (5th Revision), Ministry of Road TransportandHighways,PublishedbyIndianRoadsCongress(IRC),NewDelhi;IRC:82“Code ofPracticeforMaintenanceofBituminousSurfacesonHighways”andIRC:SP:83Guidelinesfor Maintenance,RepairsandRehabilitationofCementConcretePavements”whereverapplicable. Where the Specification for a work is not given, sound engineering practice shall be adopted to the satisfaction of theEngineer.

“Specifications for Road and Bridge Works, Ministry of Road Transport and Highways” (5th Revision) is hereinafter referred to as MoRTH Specifications.

## Arrangement for Traffic duringConstruction

2.1Contractor shall make all arrangements for safety during construction for the maintenance work in the light of Clause 112 of MoRTH specifications providing 2 cautionary Signs at a distance of 120 m, Channel for traffic clearly marked with pavement markings/painted drums with lanterns at night, Barricades, Signs, Markings, flags, Rubber traffic cones, lights and flagmen as approved by the Engineer to ensure safety. Drop off to be treated with 1V: 4H wedge or any other suitable method.

2.2He shall provide, erect and maintain all such barricades, signs, markings, flags, lights as required or directed by the Engineer for safety of traffic passing through the section underrepairs/improvement.

2.3Allmaintenanceworksontheroadshallbecarriedoutinamannerwhichwouldcause leastinterferencetothetraffic.Instretcheswhereresurfacingorridingqualityimprovementworks are to be taken up, the Contractor during execution of work shall provide and maintain proper passagefortraffic.Whereitisnotpossibleorsafetoallowtrafficonpartwidthofthecarriageway, atemporarydiversionofproperSpecificationsshallbeconstructedbytheContractorathiscost. The Contractor shall take prior approval of the Engineer regarding traffic arrangements during construction.

2.4All arrangements for traffic during construction shall be considered as incidental to theworkandshallbeContractor’sresponsibility.TheEngineershalldeterminethepenaltytobe imposed on the Contractor for deficiency in compliance to therequirement.

## QualityControl

  - Quality control on materials and workmanship is the primary responsibility of the Contractor. Quality control shall be exercised in accordance with the Quality Plan approved by the Engineer. The Engineer may, during and after construction test the quality of materials and work in order to verify conformance with the prescribedSpecifications.

  - An attempt shall be made to attend to defects like potholes, undulations, rutting, bleeding, linear and alligator cracks and eroded edges etc. at an initial stage itself. Thermal bondedpatchesofregularrectangularshapeswithoutbumporsumpshallpreferablybeadopted.

## Specifications for RoutineMaintenance

Before any work is started, signs, barriers, etc. shall be placed and necessary arrangements made for ensuring safety of traffic and workers in the work zone, as described in Clause 2 of this Section

Preparationofthesurfacepriortoapplicationofanytreatment,shallbecarriedoutinaccordance

with the relevant Clauses of MoRTH Specifications.

Aftercompletionofthework,thesiteshallbeleftcleanedandtidy.Nostockpilesofmaterialshall be left on theroad.

## Repair and Maintenance works related to RigidPavements

All repair and maintenance works related to Rigid Pavements shall be carried out following IRC:SP:83 (Guidelines for Maintenance, Repairs & Rehabilitation of Cement Concrete Pavements).

# SECTION 8

DRAWINGS AND SCHEDULE OF DRAWINGS

SECTION-9

FINANCIAL BID FORM AND BILL OF QUANTITIES

## SECTION-9

FINANCIAL BID FORM AND BILL OF QUANTITIES

FINANCIAL BID FORM

To

(Chief Engineer NH Zone P.W.D. Raipur)

DESCRIPTION OF WORKS: BID FOR (Name of work)

Reference letter No. …………………

Dear Sir,

- Having examined the site of works and Bid Documents, comprising Instructions to Bidders, Scope of Works, Conditions of Contract, TechnicalSpecifications,BillofQuantitiesand schedules for the execution of the abovenamed works, we, the undersigned offer to executeandcompletesuchworksandremedyanydefectsthereininconformitywiththe saidbiddocumentsattenderpremiumasquotedintheFinancialBid.

- Weundertake,ifourBidisaccepted,tocommencetheworkwithinfifteen(15)daysof receiptofthe order to commence, and to complete and deliver the sections and whole of the works comprised in the contract within the period stated in the bid hereto.

- If our Bid is accepted, we will furnish Performance Security (ies) in the form of a Bank Guarantee to be jointly and severally bound on us, in accordance with the Conditions of Contract.

- We agree to abide by this Bid for a period of One Twenty(120) days from the last date fixed for Bid Submission and it shall remain binding upon us and may be accepted at any time before the expiry of that period.

- We confirm our agreement to treat the Bid document and other records connected with the works as secret and confidential documents and shall not communicate information contained therein to any person other than the person authorized by the Employer or use such information in any manner prejudicial to the safety and integrity of the works.

- Unless and until an agreement is prepared and executed, this Bid, together with your written acceptancethereof,shallconstituteabindingcontractbetweenus.

- Weunderstandthatyouarenotboundtoacceptthelowestoranybidyoumayreceive.

Datedthis	dayof	20-----

Signature	in thecapacityofdulyauthorized**

To Sign Bid for and on behalf of

(in block capital letters)

Address:

SignatureofWitness

Nameofwitness

Address ofwitness

## DESCRIPTION OF WORKS: FINANCIAL BID

| S. No. | Description | Amount |
| --- | --- | --- |
| 1 | Grand Total of BOQ | Rs. (Inwords) |
|  | I/We agree to execute the above works on the tenderpremium %above/belowtheGrand Total of the project cost as given above. | (Inwords) PercentAbove/Below |

BILL OF QUANTITIES

1.	Preamble

- The Bill of Quantities (BOQ) shall be read in conjunction with the Instructions to Bidders,ConditionsofContract,RoadMaintenanceStandardsandSpecificationsfor Road Maintenance Works.

- The quantities given in the Bill of Quantities are estimated quantities. The basis of payment will be actual quantities of items of work carried out and valued at the rates tendered in the BOQ alongwith accepted/awarded tender premium. The accepted/ awarded tender premium above/below the grand total of the project cost shall be applicableforindividualitemsofworktodeterminepayableamounttoContractorfor workdonesubjecttoothercontractualprovisions.Anyvariationshallbedealtwithas per contractprovisions.

- The rates and prices tendered in the BOQ shall include all equipment, tools, spares, labour, supervision, overheads, consumables, materials, erection, maintenance, testingofinputmaterialdelivered,profit,taxesanddutiestogetherwithgeneralrisks, liabilities and obligations set out and implied in the contract and other incidentals to comply with the requirements of Standards andSpecifications.

- Payment for performance-based activities like treatment &repair of pot holes/ruts/patchesin bituminous pavement & maintenance of concrete pavement (Item no. 3.1& 3.2), maintenance of slopes/shoulder (Item no. 3.3), Removal of rank vegetation (Item no. 3.4) and Removal of animals (Item no. 3.5)shallbeindexedonperformancescaleof100marksasgiven in Table below:

Payment for performance-based activities shall be indexed on performance scale of 100 marks as given in Table below:

| Sl No | Brief Description | Weightage for performance rating | Remarks |
| --- | --- | --- | --- |
| 1 | Performance based maintenance and pavement repairs (100%) | Maintenance of pavement Pot/patch / rut repair or repair of concrete pavement- 50% | Length in which road is maintained without pot/patch rectifying the pot\patch within stipulated time during the month under consideration/Total length |
|  |  | Maintenance of embankment slopes/ shoulders, ensuring camber to shoulder-20% | Length in which road Shoulders/slopes maintained rectifying the shoulders/slopes within stipulated time during the month under consideration/Total length |
|  |  | Removal of rank vegetation/plants/trees branches protruding on to carriageway of obstructing sight distance-15% | Length in which road maintain removing the rank vegetation within stipulated time during the month under consideration/Total length |
|  |  | Removal of stray and dead animals (Item no. 3.5) – 15% | Length in which road maintain removing the stray and dead animals within stipulated time during the month under consideration/Total length |

Note:-

Performance assessment for performance based items of work, shall be done through inspection by the Engineer-in-Charge at least two times during the month and overall rating can be done on the basis of average of assessments made during the inspection along with photographic/ videographic evidence. The performance based items in Bill No. 3 corresponding to pavement repair including potholes/ patch/ rut etc., shall have to be completed within 1 month from the commencement of the work, subsequent to which if any defects found, the payment shall be subject to deductions as per the provisions of the Contract.

- The Contractor shall submit photos / videos recording to the Engineer-in-Charge of condition of the Project Highway with special emphasis on performance-based items.

- For performance-based items of work, the Contractor shall be entitled for receiving payment proportionate to the average percentage of performance assessed for achievement between 80% to 100%.

- The Contractor shall not be entitled for payment for performance based maintenance if the average performance is rated less than 80%

- A percentage quoted by bidder shall be entered as a single percentage as Tender Premium % above/ tender discount % below on the estimated rates/amounts specified in the BOQ.

- When the unattended defects are corrected within a week of their communication to the contractor at the cost of the contractor and the amount along with specified damages of 20% are recovered from the contractor those defects would be considered as rectified while assessing the performance achievement.

- Road signs proposed to be installed under Quantity based maintenance in the stretch shall also come under performance-based maintenance obligation after they are installed.

- Repeated failure in rectifying the defects / deficiencies even after intimating them to the contractor may lead to termination of contract for contractor default apart from reduction in relevant payments.

- Performance based maintenance can be reduced either in terms of length or in terms of months or both for taking up any development works or other exigencies as decided by the authority and in such cases the payments would be regulated on pro- rata basis in terms of length / period in months or both. Any claims of the Contractor in this regard shall not be entertained.

NOTE: The performance assessment shall be carried out as per the MoRT&H Circular NO. RW/NH-33044/15/2021-S&R(P&B), dt: 16.4.2021.

** The  Performance based payments percentages are  assessed for the 12 months of work period. In case of any fore closure of the work inview of declaration of Appointed Date for the Improvement works on the subject reach, the payments shall be reduced proportionately w.r.t the decrease in the Work period.

## NOTE FOR EMPLOYER:

- The items of work given in the BOQ are indicative. Employer may include new items or delete items depending on the requirements of thework.

- The performance based items given in the BOQ are indicative and may be changed as perrequirements.

- TheratesofitemsasperapplicableScheduleofRatesarerequiredtobeworkedout and included in the BOQ and accordingly amount is to be calculated and included in theBOQ/Summary.

- RoadmaintenancestandardsgiveninPart-Iforsomeitemsofworkareindicative.

These may be amended/supplemented as per specific requirement of work.

## SUMMARY

| BILL NO. | DESCRIPTION | AMOUNT (Rs.) |
| --- | --- | --- |
| BILL NO. 1 | ROAD MAINTENANCE | 2,63,385.00 |
| BILL NO. 2 | ROAD PROPERTY MAINTENANCE | 23,91,212.00 |
| BILL NO. 3 | PERFORMANCE BASED INCIDENT MANAGEMENT AND PAVEMENT REPAIRS | 1,65,71,336.00 |
|  | TOTAL | 1,92,25,933.00 |
|  | ADD FOR GST 18% | 34,60,668.00 |
|  | GRAND TOTAL | 2,26,86,601.00 |

| S.No. / ItNo. | Item of work | Quantity |  | Rate |  | Unit | Amount |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Road Maintenance Bill No.1 |  |  |  |  |  |  |  |
| 1 10.25 Road SOR | Dressing of side shoulder/Scrapping the road side shoulder by Mechanical means (By JCB/DOZER) including excavation of raised side shoulders upto 15cm depth including remooving/cutting bushes, grass and dressing shoulder to desired camber and disposing of excavated stuff up to road boundary etc complete. as directed by Engineer In Charge. | 52677.00 | 5.00 |  |  | Sqm | 263385.00 |  |
|  |  |  | Total |  |  |  | 263385.00 |  |
|  | ROAD PROPERTY MAINTENANCE (BILLNo.2) |  |  |  |  |  |  |
| 2 8.13 Road SOR | Road Marking with Hot Applied Thermoplastic Compound with Reflectorising Glass Bads on Bituminous Surface (Providing and laying of hot applied thermoplastic compound 2.5 mm thick including reflectorising glass beads @ 250 gms per sqm area, thickness of 2.5 mm is exclusive of surface applied glass beads as per IRC:35. The finished surface to be level, uniform and free from streaks and holes. | 998.145 | 713.00 |  | Sqm. |  | 711677.00 |
| 3 8.4 Road SOR | Retro- reflectrorized Traffic signs (Retro- reflectrorized Traffic signs (Providing and fixing of retro- reflectrorized cautionary, mandatory and informatory sign as per IRC:67-2012 made of retro-reflective type sheeting vide clause 801.3, fixed over aluminum sheeting of required thickness supported on a mild steel frame of size 40 x 40 x 5 mm and mild steel angle iron post 75 mm x75 mm x 6mm firmly fixed to the ground by means of properly designed foundation with M15 grade cement concrete 45 cm x 45cm x 60cm, 60 cm below ground level as per approved drawing and painting all components of the signs and supports as per clause 7.2 of IRC:67-2012) |  |  |  |  |  |  |
|  | Made of Class-C Micro Prismatic Grade Sheeting of Type IX (for National Highways and State Highways) |  |  |  |  |  |  |
|  | With Aluminum Sheeting of 2 mm thickness |  |  |  |  |  |  |
|  | Made of Class-C Micro Prismatic Grade Sheeting of Type-XI (for National Highways and State Highways) |  |  |  |  |  |  |
|  | (iii) 75 cm equilateral triangle | 20 | 5142.00 |  | Each |  | 102840.00 |
|  | (xviii) 50 cm x 60 cm rectangular (single chevron with double plate in singe post) | 20 | 9204.00 |  | Each |  | 184080.00 |
|  | (x) 80 mm x 60 mm rectangular | 16 | 7837.00 |  | Each |  | 125392.00 |
|  | (xii) 60 cm x 45 cm rectangular | 12 | 5444.00 |  | Each |  | 65328.00 |
|  | (xv) 90 cm high octagon | 16 | 10014.00 |  | Each |  | 160224.00 |
|  | (vi) 90 cm circular | 10 | 9616.00 |  | Each |  | 96160.00 |
| 4 8.50 Road SOR | Providing & Fixing Delineator made of M.S. Hollow Rectangular Pipe (Conforming to IS: 4923) of cross section 100 mm x 80 mm, thickness 4mm, of 1.10 meter length. The top of the hollow pipe, welded and closed with 16 gauge M.S. Sheet. The height of the Delineator above ground level should be between 0.8 meter and 0.9 meter and 0.20 to 0.30 m below ground. The bottom of the delineator should be provided with holdfast of length 15cm on each side. Delineator should be painted with coat of Zinc Chromate stoving Prime and two coats of Black Stove Enamel (Oven Baked) paint with 3nos. 15 cm bands of white Retro-reflective Sheeting of Engineering Grade pasted around the pipe and 2 Nos. High intensity Grade Retro-reflective Sheeting of size 8 cm x 10cm pasted on the top of each side of Delineator and treated With HLVA & fixing the same in M-15 grade concrete block of size 45x43x30cms including transportation etc. complete. The construction and placement of the delineator must beas per IRC: 79. | 400 | 1913.00 |  | Each |  | 765200.00 |
| 5 8.51 Road SOR | Providing & Fixing Hazard Marker Type-2 Partial Retro Reflective Size 0.30 x 0.90M made of 16 gauge (1.6 mm) thick mild steel sheet Confirming to IS:2062 Painted with one cast of Zinc Chromate Stoving Primer and two coats of Black Stove Enamel (Oven Baked) paint with 10 cm bands of yellow Retro- Reflective Sheeting of Engineering Grade pasted a per IRC:79 including one MS angle Iron post of size 50x50x5 mm of 1.65 meter long duly painted with synthetic enameled paint block including bolts and fixing the same in M-15 concrete black of size 30x30x30cm, including transportation etc. Complete. | 22 | 1491.00 |  | Each |  | 32802.00 |
| 6 8.54 Road SOR | 8.54 Providing & Fixing tree studs in Square/ Round shape of 4” side/diameter made of 2 mm aluminum substrate (Confirming to IS:736 -Material Designation, 24345 or 1900) end reflective surface of High Intensity grade as specified in section 801.3 of MORT&H duly treated with HLVA and fixing the same with four Nos. high strength nails confirming to 1S:1367 on trees at site each. | 200 | 67.00 |  | Each |  | 13400.00 |
| 7 8.05 Bridge SOR | Direction and Place Identification signs upto 0.9 sqm size board. (Providing and erecting direction and place identification retro-reflectorised sign as per IRC :67 made of retro reflective type sheeting and vide clause 801.3, fixed over aluminium sheeting, 2 mm thick or Aluminum composite material sheet with overall thickness of 4mm with area not exceeding 0.9 sqm and fixed over back support frame of min 35 x 35 x 3mm Angle mounted on a mild steel circular pipe 65 NB, firmly fixed to the ground by means of properly designed foundation with M15 grade cement concrete 45 x 45 x 60 cm, 60 cm below ground level as per approved drawing) |  |  |  |  |  |  |
|  | A Made of Class-C Micro Prismatic Grade Sheeting of Type-XI (for National Highways and State Highways | 9.00 | 14901.00 |  | Sqm. |  | 134109.00 |
|  |  | SUB TOTAL |  |  |  |  | 2391212.00 |

PERFORMANCE BASED MAINTENANCE AND PAVEMENT REPAIRS - Bill No.-3

| Item No | Description of Items | Length in Km | Unit | Rate per km per month (in Rs.) | Amount (in Rs.) |
| --- | --- | --- | --- | --- | --- |
| 3.1 | Providing treatment and repair to pot holes/ruts of any depth/patch repair of all types of bitumen pavement including providing seal for filling cracks, WMM, bituminous surfacing, complete as per Technical Specification Clause 3004.2, and as per direction of Engineer by using paving grade bitumen/emulsion/cold ready mix material. The job includes removal of all failed material, trimming of completed excavation to provide firm vertical faces, cleaning of surface, painting of tack coat on the sides and base of excavation as per Clause no. 503, back filling the patch with bituminous material as per Clause no. 509. Compacting trimming and finishing the surface to form a smooth continuous surface all as per Clause no. 3004.2 of Technical Specifications. Carrying out cleaning, removing of dust/silt/thrash from carriageway and median along with cleaning of sign boards, delineators, studs with detergent. | 22.181 | 12 months | 60758.00 | 16172078.00 |
| 3.2 | Repair of localized failed areas of PQC by marking the area, removing the failed area using jack hammer, saw cutting to full depth of PQC, replacing membrane, clearing the area from dust and debris. Placing M-40 grade PQC in a depth equivalent to the existing depth of PQC and installing existing expansion joint/other joint. Repair of transverse joints of cement concrete pavement involving removal of old joint sealent and sealing with fresh sealent (Poly sulphide) including repair of spalled/broken edges of joints with Epoxy mortar complete as per Clause no. 3005 of Technical Specifications | - | - | - | - |
| 3.3 | Maintenance of cuts and fills slopes/shoulders conforming to Technical Specifications Clause no. 3002. Fill material should be brought from borrow areas located outside ROW conforming to Technical Specification no. 305. Watered and well compacted with plate compactor or power rammer with all leads and lifts as directed by the Engineer. | - | - | - | - |
| 3.4 | Removal of rank vegetation/ weeds and undesirable vegetation from shoulders, embankment slopes upto ROW (both sides) complete in all respects including breaking of clods, rough dressing and disposal of waste material and vegetation at a place outside ROW as per direction of Engineer- ln-Charge. | - | - | - | - |
| 3.5 | (a) Removal of dead animals/ birds and burying them at suitable location within two hours. (b) Removal of stray animals to suitable place out of carriageway | 22.181 | 12 Months | 1500.00 | 399258.00 |
|  | TOTAL FOR BILL NO. 3 |  |  |  | 16571336.00 |

Note:	In case of any error of Clause of  MoRTH  Specifications, the appropriate correct clause of the MoRTH Specifications shall prevail, as per the decision of Engineer-in-Charge/Employer.